## Wallstreetmojo.com
Construction Schedule Template
Prepared by Dheeraj Vaidya, CFA, FRM
dheeraj@wallstreetmojo.com
visit - www.wallstreetmojo.com

## Construction Schedule Template
STATUS
Construction Schedule |  |  |  |  | Not Started
Project Name: | Strart Date: |  | Total Duration: |  | In Progress
Complete
Project Manager: | End Date: |  |  |  | On Hold
| START DATE | END DATE | DURATION | COMMENTS
Planning | 2021-09-21 | 2021-09-30 | 10
Material Accumulation | 2021-10-01 | 2021-10-06 | 6
Foundation | 2021-10-06 | 2021-10-24 | 19
Clear Site | 2021-10-25 | 2021-10-29 | 5
Excavation | 2021-11-01 | 2021-11-13 | 13
Pour Footers | 2021-11-13 | 2021-11-15 | 3
Brick walls | 2021-10-25 | 2021-10-30 | 6
plumbing | 2021-11-19 | 2021-11-21 | 2
Frame | 2021-11-09 | 2021-12-01 | 5
roof house | 2021-11-22 | 2021-12-15 | 24
rough plumbing | 2021-12-10 | 2021-12-12 | 3
rough electrical | 2021-12-10 | 2021-12-13 | 4
wall insulation | 2021-12-27 | 2021-12-30 | 4
pleaster work | 2021-12-03 | 2021-12-07 | 5
wet area waterpoofing | 2022-01-03 | 2022-01-05 | 3
cabinets | 2022-01-23 | 2022-01-25 | 3
wall and floor tiling | 2022-01-25 | 2022-02-03 | 10
glass install | 2022-02-04 | 2022-02-04 | 1
plumbing | 2022-02-04 | 2022-02-04 | 1
electrical | 2022-02-04 | 2022-02-05 | 3
cleaning | 2022-02-06 | 2022-02-06 | 1