## Sheet1
Cairns Builders
Trade Letting Schedule
Address: | Lot 8 Rees Court, Palm Beach
Scheduled Construction Start Date: | 2021-01-11
Resource Name | Trade/Specialty | Code | Scheduled Trade Start | Tender Sent | Tender Due | Tender Received | Purchase Order Sent | Subcontract Due | Subcontract Agreement
Civil Contracting Crew | Earthmoving/Civil Contracting | CCC | Tue 12/01/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/21 | Yes
Pool Professionals Palm Beach | Pool Construction | PP | Wed 13/01/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/22 | Yes
Dirt Professionals | Soil Testing | DP | Fri 15/01/21 | Mon 19/10/20 | Fri 30/10/20 | No | No | Mon 04/01/23
The Survey Specialists | Surveying | SS | Fri 15/01/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/24 | Draft
Wet Tropics Plumbing | Plumbing | WTP | Tue 19/01/21 | Mon 19/10/20 | Fri 30/10/20 | No | No | Mon 04/01/25
Ultimate Concrete Solutions | Concreting | UCS | Wed 20/01/21 | Mon 19/10/20 | Fri 30/10/20 | No | No | Mon 04/01/26
JH Custom Glass | Glazing | JCG | Thu 11/02/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/27 | Yes
AJ Roofing Specialists | Roofing | AJ | Mon 15/02/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/28 | Awaiting Directors Signature
Electricool Services | Electrical | ES | Fri 5/03/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/29 | Sent - Awaiting Return
Hunty's Plastering | Plastering | HP | Thu 18/03/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/30 | Draft
Tippo's Tiling Professionals | Tiling | TTP | Wed 24/03/21 | Mon 19/10/20 | Fri 30/10/20 | No | No | Mon 04/01/31
Palm Beach Painting Contractors | Painting | PBPC | Mon 29/03/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/32 | Draft
Landscape and Civil Contracting Qld | Landscaping | LCC | Tue 20/04/21 | Mon 19/10/20 | Fri 30/10/20 | No | No | Mon 04/01/33
Custom Cabinet Professionals | Joinery | CCP | Wed 24/03/21 | Mon 19/10/20 | Fri 30/10/20 | Yes | Yes | Mon 04/01/34 | Yes