| - Issue | - What went well | - What didn’t go well | - Recommendation / Improvement |
| --- | --- | --- | --- |
| - Labour Strategy | - Select few guys that stayed the duration of the project | - The high turnover rate of labour hire | - Need to be employed by BMD for the next project as this will allow supervision to rely on these ‘team leaders’ |
| - Plant | - Once changed from Egans to VE Group, the communication between superintendent to plant operations manager was great | - Using Egans – poor quality of plant and operators and management | - Never use Egans again |
| - Operator Skills | - Select operators from different contractors performed well | - Select subcontractors sending operators who were not competent (hair dressers trying to operate 825 compactors and butchers trying to operate loaders) - Grader operators not knowing how to use GPS and UTS | - VOC process needs to be incorporated into our induction process and allow time for supervision to conduct VOC straight after to ensure operators are competent |
| - Grader Hire Issue | - Select operators returning to same work areas | - Poaching of good operators to different sections/projects | - We need to increase our schedule of rates for graders in order to attract better quality operators /subcontractors |
| - GPS Issue | - Having GMC to assist constantly with GPS and UTS issues - Foreman kits so supervision could double check works | - Not stopping when significant issues were identified | - Organise a better set-up and GPS system for next time instead of going with the bare minimum - Refresher courses for operators and supervision |
| - Retention of people and plant | - Select few labourers/operators have lasted the duration of the project - Same workforce going to same work areas each swing | - Keeping labourers/operators who were incompetent and could not perform the tasks they were hired for | - Review schedule of rates and BMD to employ known good labour from the project for ongoing projects - Better facilities to provide entertainment at accommodation to make people want to stay |
| - Haulage contractor issues | - Changing from hourly hire to tonnage rate | - MLH – everything about them - Lantrak – no assistance and no communication - Haul tracker app did not work in this section | - BMD supervision to manage areas of work going forward – one supervisor dedicated to managing trucks (Wade) |
| - Constructability issues |  | - Long wait times for responses from the client - Inspectors giving directions and then backflipping later on | - Stop works until directed by Client to proceed and put it back on them to find a solution to their issues |
| - Quarry Operations and Issues | - BMD supervision took control to manage the haulage - Subcontractor improved when on a tonnage rate instead of hourly | - MLH supervision – often uncontactable and unreliable (not productive or organised) - Organising of trucks from Lantrak | - Use tonnage rate straight away instead of hourly hour |
| - Accommodation | - At Camp 6 we were right nearby our area of works and did not need to travel - Food improved towards the end of the project | - No recreational facilities - Very strict under the circumstances of living - Unreliable internet and no phone reception - Sodexo charging for BBQ packs and cakes - Overpriced everything - Rooms cleaned once a swing and not to a high standard – sometimes not cleaned at all over the swing - Unprofessional and rude food servers | - Need recreational facilities for after work - Better internet and phone coverage to call home |

| - Issue | - What went well | - What didn’t go well | - Recommendation / Improvement |
| --- | --- | --- | --- |
| - Labour Strategy |  |  |  |
| - Plant |  |  |  |
| - Operator Skills |  |  |  |
| - Grader Hire Issue |  |  |  |
| - GPS Issue |  |  |  |
| - Retention of people and plant |  |  |  |
| - Haulage contractor issues |  |  |  |
| - Constructability issues |  |  |  |
| - Quarry Operations and Issues |  |  |  |
| - Accommodation |  |  |  |