CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Debbie Cremer |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | 20/09/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 45 |  | Yes | No |

Assessor Comments

Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | Specifications |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | Queensland Building and Construction Commission Act 1991 (QLD) Schedule 1B, Part 4, Division 2.33 | Maximum deposit allowed should not be more than: 10% of the contract price for a level 1 regulated contract or; 5% of the contract price for a level 2 regulated contract or; 20% of the contract price for a level 1 or 2 regulated contract under which the value of the off-site work is more than 50% of the contract price The maximum penalty is 100 units |  |

Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Steelfixer | Fixes all reinforcing steel into place for strengthening concrete slabs |  |
|  | Concreter | Pours concrete slabs, and any other concrete structures required |  |
|  | Tiler | Lays tiles on floors and walls |  |

Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

Explain the importance of determining subcontractor or plant availability for a job.

| Answer | Subcontractors need to be available at the time the trade is needed on site. As building work is very program driven, if a subcontractor is not available at the right time the whole project can be affected and there is a risk of the job stopping or being delayed and liquidated damages kicking in. A knock-on effect would be experienced where other trades starting times would be pushed out risking other subcontractors becoming unavailable at the pre-arranged times due to other work commitments. If a subcontractor cannot commit to a time schedule it’s best to get a different subbie who can be available. |  |
| --- | --- | --- |

Identify two (2) methods you might use to find a supplier for materials.

| Answer | Recommendations from other builders Internet |  |
| --- | --- | --- |

Name two (2) factors that may impact on the availability of materials.

| Answer | High demand Specialised or imported items |  |
| --- | --- | --- |

Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | AS/NZS 1680 |  |
| --- | --- | --- |

Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Crane | Lifting and moving heavy materials and equipment |  |
|  | Grader | Levelling out and pushing up earth |  |

Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | Generator | Supplying electricity |  |
|  | Power saw | Cutting timber |  |

Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | Service and maintenance documentation Invoices and receipts |  |
| --- | --- | --- |

Name five (5) temporary services that need to be organised for a building site.

| Answer | Electricity Waste Water Fencing Barricading Answer to Q13 is “True” – wouldn’t allow me to insert a tick |  |
| --- | --- | --- |

True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

Identify one (1) action you might take to facilitate site access for machinery.

| Answer | Have a cleared area designated for trucks to enter and deliver goods which is big enough to enable them to turn around safely. Ensure the area is clearly signed. |  |
| --- | --- | --- |

Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | Part 3.9 | Section D |  |

You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | Brisbane City Council - A minimum of 10 working days is required for approval. You are required to submit: - Completed request for assessment of compliance with conditions – CC11018 form - Site-specific Construction Noise Management Plan - Copy of the letter that will be provided to premises/residences who are likely to be affected |  |
| --- | --- | --- |

In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | Residential Driveway Permit | Approval body: - Brisbane City Council Documents required (self assessment): - Completed application to construct residential driveway form - Residential driveway checklist - Evidence of any existing council asset damage, e.g. photos |  |
|  | Plumbing & Drainage Permit | Approval body: - Brisbane City Council Documents required: Completed Form 1 – Permit work application for plumbing & drainage and onsite sewerage work. Floor plan, site plan and elevation plan of dwelling. Site classification report. Articulation design if required |  |

True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What document should be developed when purchasing supplies or construction materials?

| Answer | Purchase order when purchasing Delivery docket when delivering |  |
| --- | --- | --- |

True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Who should be contacted if items are missing from a delivery?

| Answer | The supplier |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | Work Health and Safety Act 2011 (QLD) Part 2, Division 1, Subdivision 1 | To eliminate risk to health and safety so far as reasonably practicable. If unable to eliminate the risk, minimise the risk so far as reasonably practicable |  |

Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | Work Health and Safety Regulation 2011 (QLD) |  |
| --- | --- | --- |

What document should be followed when disposing of hazardous materials?

| Answer | SDS – Safety Data Sheets |  |
| --- | --- | --- |

An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10m2 |  |
| --- | --- | --- |

True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | Subcontractors can flow from one project straight onto another could mean less mobilisation/demobilisation cost, less down-time as they can alternate between projects to keep them all progressing. If any issues arise, the subcontractor is still available to discuss with and solve problems. Keeps the project flowing, rather than stopping waiting for subcontractors to return from other jobs. Example: 3 bridges are to be built on a new highway. It cost $10,000 to mobilise and de-mobilise the bridge building subcontractor. If work was sequenced correctly, up to $40,000 could be saved due to the team simply having to move to the next bridge rather that de-mob then mob again late. There could potentially be a time saving as the second bridge could be started whilst part of the team is still finishing off the first bridge. |  |
| --- | --- | --- |

Provide one (1) example to explain why construction operations must be sequenced.

| Answer | If the concreters start on site and have laid the slab for a house before the plumber has been, the drains will not be in place and the slab would have to be cut to enable the drains and pipes to be installed. |  |
| --- | --- | --- |

Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 4 | Floor frame |  |
|  | 3 | Installing brick base |  |
|  | 6 | Roof trusses |  |
|  | 1 | Set out |  |
|  | 5 | Wall frames |  |

Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| - Task ID | - Task | - Preceding event | - Nodes |
| --- | --- | --- | --- |
| - A | - Make enquiries and order all materials required | - Start | - 1 |
| - B | - Wait for bricks, sand and cement to arrive | - A | - 2 |
| - C | - Clear vegetation from the site | - A | - 2 |
| - D | - Order concrete to be delivered | - A | - 2 |
| - E | - Dig the trench | - C | - 4 |
| - F | - Pour the footings | - E | - 5 |
| - G | - Footings curing time | - F | - 6 |
| - H | - Load the bricks on the site | - B | - 3 |
| - I | - Mix the mortar and lay the bricks | - H | - 7 |
| - J | - Clean rubbish from the area | - I | - 8 |
|  | - Finish | - J | - 9 |

G

F

H

E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | Microsoft Project |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

Describe the critical path.

| Answer | The critical path would be orders, clear site, dig trench, pour footings, cure footings, mix mortar & lay bricks, clean up |  |
| --- | --- | --- |

True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | Inclement weather Union activity (strikes) Re-work |  |
| --- | --- | --- |

Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

Why should you take photographs of site boundaries with neighbouring properties?

| Answer | For supporting evidence in the case of a dispute later on. |  |
| --- | --- | --- |

When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

When might a neighbouring property owner be required to refer to a condition report?

| Answer | If they believe there is damage to their property during or after the build. |  |
| --- | --- | --- |