## Sheet1
DATE. 11/08/2020 |  |  | SAFETY COMMITTEE WEEKLY INSPECTION
ITEM NO. | LEVEL | AREA |  | DESCRIPTION | TRADE | CLOSE DATE
1 | 11 | P1 |  | COVER OVER FLOOR PENNO LOOSE AND UNSECURED | FORMWORK | 2020-08-11
2 | 10 | P1 |  | INSTALL KICKBOARDS ON BOTTOM OF SCAFFOLD | FORMWORK | 2020-08-11
3 | 10 | P1 |  | JACKHAMMER WITH OUT OF DATE ELECTRICAL TAG | FLOOR GRINDERS | 2020-08-11
4 | 10 | P1 |  | LOOSE ACCESS RAMP | BUILDER | 2020-08-11
5 | 9 | P1/2 |  | SPACE AROUND PUMP NEEDLE RISK OF FALLING MATERIALS | BUILDER | 2020-08-11
6 | 9 | P2 |  | HOUSEKEEPING REQUIRED | CARPENTERS | 2020-08-11
7 | 9 | P2 |  | EXCLUSIOIN ZONE REQUIRED | FORMWORK | 2020-08-11
8 | 8 | P1 |  | SIGNAGE REQUIRED | FORMWORK | 2020-08-11
9 | 8 | P1 |  | EXPOSED PIPES RISK OF TRIPS | PLUMBERS | 2020-08-11