## Workings
Q. 7 - Plasterer + Carpenter
Ground Floor - 12 story high rise - Exceed $15,000
New electrical wiring for lights and power points already installed in pre-existing timber wall and ceiling framing
Construction Schedule/Program - select future start date - subcontractors start & finish dates
Ordering Forms for Materials - Cheops PO - Email word, edit & pdf
Schedule the work and subcontractors
Obtain quotes from subcontractors
Draft emails to each subcontractor, pdf and save detailing 1. information needed from them 2. requesting labour only quote to be submitted and advise start and finish dates. Note: Labour only quote as builder to supply all materials and consumables excl. tools, plant, equipment
The Project |  | Skirting | Architrave | Walls | Ceilings
Commercial office project with eight (8) rooms all adjacent (side-by-side) to each other | m2 | lm | lm | m2 | m2
Room 1: 6000 x 3300 | 19.8
Room 2: 3900 x 3300 | 12.87
Room 3: 4000 x 3300 | 13.2
Room 4: 4800 x 3300 | 15.84
Room 5: 5200 x 3300 | 17.16
Room 6: 7400 x 3300 | 24.42
Room 7: 8000 x 3300 | 26.4
Room 8: 9000 x 3300 | 29.7
159.39
Plasterer
1. Walls - 10mm Plasterboard sheeting
2. Ceiling - 13mm Acoustic plasterboard sheeting
Carpenter
1. Skirting - 75mm moulded skirting boards and architraves for each room
2. 8 x Window Installation - 1540 x 2650 Sliding aluminium glass window
windows to be fitted to installed load bearing timber framing
3. 8 x Doors + Furniture - Opening inwards to rooms - 2040 x 820 x 35 flush panel hollow core
Hang doors, fit jambs, door stops, fit and attach privacy set door furniture and a door open retainer and stop
4. 8 x Door and 8x window jambs - 75 x 45 treated pine

## Q. 7
SKIRTING
150lm @ $6.40 = $960.00
Room 1 | 17.78
Room 2 | 13.58
Room 3 | 13.78
Room 4 | 15.38
Room 5 | 16.18
Room 6 | 20.58
Room 7 | 21.78
Room 8 | 23.78
Sub total | 142.84
5% Waste | 7.142
Total lm | 149.982
Total Cost | 960
ARCHITRAVE
112lm x $6.40 = $716.80
| Door | Window
Room 1 | 4.9 | 8.38
Room 2 | 4.9 | 8.38
Room 3 | 4.9 | 8.38
Room 4 | 4.9 | 8.38
Room 5 | 4.9 | 8.38
Room 6 | 4.9 | 8.38
Room 7 | 4.9 | 8.38
Room 8 | 4.9 | 8.38
Sub total | 39.2 | 67.04
5% Waste | 1.96 | 3.352
Total lm | 41.16 | 70.392 | 111.552
Total Cost |  |  | 716.8
Total lm | Total $
262lm | 1676.8

## Q. 8
CEILING - 13mm Acoustic Plasterboard
167m2
Room 1 | 19.8
Room 2 | 12.87
Room 3 | 13.2
Room 4 | 15.84
Room 5 | 17.16
Room 6 | 24.42
Room 7 | 26.4
Room 8 | 29.7
Sub total | 159.39
5% Waste | 7.9695
Total m2 | 167.3595
WALL - 10mm Plasterboard
469m2
|  | Window | Door | Total
Room 1 | 61.38 | 4.081 | 1.6728 | 55.6262
Room 2 | 47.52 | 4.081 | 1.6728 | 41.7662
Room 3 | 48.18 | 4.081 | 1.6728 | 42.4262
Room 4 | 53.46 | 4.081 | 1.6728 | 47.7062
Room 5 | 56.1 | 4.081 | 1.6728 | 50.3462
Room 6 | 70.62 | 4.081 | 1.6728 | 64.8662
Room 7 | 74.58 | 4.081 | 1.6728 | 68.8262
Room 8 | 81.18 | 4.081 | 1.6728 | 75.4262
Sub total |  |  |  | 446.9896
5% Waste |  |  |  | 22.3495
Total m2 |  |  |  | 469.3391

## Q. 9
WALL - 10mm Plasterboard - 469m2
Room | Qty | Size | Qty | Size | Price | Total
1 | 12 | 1200 x 3000 | 36 | 1200 x 2400 | 14.3 | 514.8
| 6 | 1200 x 3600 | 12 | 1200 x 2700 | 20.12 | 241.44
2 | 12 | 1200 x 2400 | 12 | 1200 x 3000 | 21.32 | 255.84
| 6 | 1200 x 3600 | 48 | 1200 x 3600 | 25.24 | 1211.52
3 | 12 | 1200 x 2400 | 36 | 1200 x 4200 | 28.15 | 1013.4
| 6 | 1200 x 3600 | 144 |  |  | 3237
4 | 12 | 1200 x 2400
| 6 | 1200 x 3600
5 | 12 | 1200 x 2700
| 6 | 1200 x 3600
6 | 12 | 1200 x 4200
| 6 | 1200 x 3600
7 | 12 | 1200 x 4200
| 6 | 1200 x 3600
8 | 12 | 1200 x 4200
| 6 | 1200 x 3600
144
CEILING - 13mm Acoustic Plasterboard - 167m2
Room | Qty | Size | Qty | Size | Price | Total
1 | 5 | 1200 x 3600 | 9 | 1200 x 3600 | 56.32 | 506.88
2 | 3 | 1350 x 3600 | 29 | 1350 x 3600 | 61.2 | 1774.8
3 | 3 | 1350 x 3600 | 38 |  |  | 2281.68
4 | 4 | 1200 x 3600
5 | 4 | 1350 x 3600
6 | 6 | 1350 x 3600
7 | 6 | 1350 x 3600
8 | 7 | 1350 x 3600
| 38 |  |  |  |  | 5518.68

## Q. 11
Plastering - Subcontractor Rates
Supply & Install 13mm Plasterboard |  | $19.20/m2
Supply & Install 10mm Plasterboard |  | $18.60/m2
Square Set |  | $12.50/lm
Item | Qty | Price | Total
Ceilings - 13mm Plasterboard | 159 | 19.2 | 3052.8
Walls - 10mm Plasterboard | 447 | 18.6 | 8314.2
Square Set - lm | 150 | 12.5 | 1875
13242
Less Materials |  |  | 5518.68
Total |  |  | 7723.32
Plus GST |  |  | 772.332
Total Labour Only Cost |  |  | 8495.652
Comparison Quote - Estimating Hours
Approximate Quote | Qty | Price | Total
2 Tradesman - 3 days to Hang Sheets | 48 | 51.5 | 2472
2 Tradesman - 4 Days to Set & Sand | 64 | 51.5 | 3296
5768

## Q. 12
Doors and Door Hardware
Item | Qty | Price | Total
Hume Doors & Timber 92 x 19mm Pine Prehung Door Jamb | 8 | 32.35 | 258.8
Hume Doors & Timber 2040 x 820 x 35 Flush Primecoat Prehung Door | 8 | 48 | 384
Ryobi Silver Hydraulic Door Closer | 8 | 66.5 | 532
Ikonic Brushed Nickel Victoria Entrance Lever | 8 | 29.5 | 236
Delf Door Stop Conceal Fix Skirt Mount | 8 | 20.42 | 163.36
Total |  |  | 1574.16

## Q. 14
Carpenter
Item | Qty | Price | Total
Hume Doors & Timber 92 x 19mm Pine Prehung Door Jamb | 8 | 32.35 | 258.8
Hume Doors & Timber 2040 x 820 x 35 Flush Primecoat Prehung Door | 8 | 48 | 384
Ryobi Silver Hydraulic Door Closer | 8 | 66.5 | 532
Ikonic Brushed Nickel Victoria Entrance Lever | 8 | 29.5 | 236
Delf Door Stop Conceal Fix Skirt Mount | 8 | 20.42 | 163.36
Aluminium sliding glass window 1540 x 2650 | 8 | 587.25 | 4698
Architrave lm | 112 | 6.4 | 716.8
Skirting lm | 150 | 6.4 | 960
Total |  |  | 7948.96

## Q. 15
Rooms 6, 7, 8 - Double entry doors in lieu of Single
Item | Qty | Rate | Total
Carpenter - Labour to alter framing to suit double entry doors - 1 hour per frame | 3 | 36.4 | 109.2
Carpenter - Labour to install all doors and hardware - 3 hours per door | 9 | 36.4 | 327.6
Hume Double Door Jamb Set - 1640 x 35 Incl. 2 stiles, 1 head | 3 | 123.5 | 370.5
Hume Doors & Timber 2040 x 820 x 35 Flush Primecoat Prehung Door | 6 | 48 | 288
Ryobi Silver Hydraulic Door Closer | 6 | 66.5 | 399
Lockwood Velocity L3 Entrance Lockset | 3 | 159 | 477
Delf Door Stop Conceal Fix - Skirt Mount | 6 | 20.42 | 122.52
Barrell Bolt | 3 | 12.35 | 37.05
Architrave lm | 18 | 6.4 | 115.2
Sub Total |  |  | 2246.07
Plus Builders Margin - 10% |  |  | 224.607
Sub Total |  |  | 2470.677
Less Variation Credit - Single doors |  |  | -904.71
Sub Total |  |  | 1565.967
Plus GST |  |  | 156.5967
Total |  |  | 1722.5637
Variation Credit
Item | Qty | Price | Total
Carpenter Install all doors and hardware 2 hours per door | 6 | 36.4 | 218.4
Hume Doors & Timber 92 x 19mm Pine Prehung Door Jamb | 3 | 32.35 | 97.05
Hume Doors & Timber 2040 x 820 x 35 Flush Primecoat Prehung Door | 3 | 48 | 144
Ryobi Silver Hydraulic Door Closer | 3 | 66.5 | 199.5
Ikonic Brushed Nickel Victoria Entrance Lever | 3 | 29.5 | 88.5
Delf Door Stop Conceal Fix - Skirt Mount | 3 | 20.42 | 61.26
Architrave lm | 15 | 6.4 | 96
Credit Total |  |  | 904.71

## Q. 19
Brick Wall | 69.3 | m2
Less Windows | 4.32 | m2
| 3.24 | m2
| 0.54 | m2
| 2.172 | m2
| 1.6728 | m2
| 1.6728 | m2
| 13.6176 | m2
| 55.6824 | m2
| 2728.4376 | Bricks

## Q.21
| 56 | m2
| 2744 | Bricks
| 9.1467 | Days
| 3.0489 | Days on Site
| 72 | Hours/Tradesman | 34.2
| 24 | Hours/Labourer | 26.4
| 2462.4 | Total Tradesman
| 633.6 | Total Labourer
| 3096 | Total Labour Cost
Your bricklaying subbie indicates he will have three tradesman bricklayers on site and one labourer. Estimate the number of days the bricklayers will be on site and the labour cost if:
· Each bricklayer lays 300 face bricks a day and their labour rate is $34.20/hour for the bricklayers
· 49 bricks make up 1m²
· The labour rate is $26.40/hour for the labourer

## Q. 27
LOT 6 - PENDER STREET
A | Internal & External Pre fabricated timber walls | $
Supplier: Sunshine Hardware
Building designed to AS1684.1999 Light timber framing and AS1170 loading code
Including bracing - to be fixed as per bracing plan
Note: Studs to load bearing walls not to be notched for bracing
Plates not to be trenched for studs
Internal & External Pre fabricated walls estimated at $1480 per m2 including ancillaries
B | Concrete slab including reinforcing
Supplier Concrete: HyTec Concrete
Supplier Reinforcing: Mesh & Bar
Concretor: Glovers Concreting
Concrete Pumping: Jesse's Concrete Pumping
Foundations - 50mm Bedding Sand
100mm concrete slab with 2 layers of F11 trench mesh
N20 Reinforcing, F82 Fabric, 0.2mm visqueen membrane
Note: Additional trench mesh allowed for in corners as per Foundation Plan
Labour
| Concretor Labour - Footings 78.8 x 0.35 = 27.58m2 + Slab 262.5m2 = 290m2 x $35/m2 | 10150
| Concrete Pumping - Footings & Slab | 1090.1
Materials
| Footings - Trench Mesh - 2 Layers, Reo | 1209.5
| Slab - 50mm Bedding Sand - Qty = 262.5m2 x 0.05 x $92/m2 | 1207.5
| Slab - Visqueen Membrane | 380
| Slab - Reinforcing - SL82 | 1080
| Concrete - Footings - 71.6 lineal metres + 10% waste = 78.8 x 0.14 = 11m3 x $160/m3 | 1760
| Concrete - Slab - 238.6m3 + 10% waste = 262.5m2 x 0.10 = 26.25m3 x $160/m3 | 4200
| 11 x Bored piers @ $20 per pier | 220
21297.1
C | Timber flooring - upper floor
Supplier: Sunshine Hardware
19mm structural grade plywood flooring
HJ 200 hyspan floor joists to main floor at 450 centres
15mm compressed decking to be waterproofed and tiled
170 x 45 F17 hardwood floor joists
| Timber flooring - 125m2 + 5% waste = 131.25m2 x $85/m2 | 11156.25
D | Architrave - upper floor - 187 lineal metres incl. 10% waste
Supplier: Sunshine Hardware
Ensuite Window: 900+900+900 = 2700
Ensuite Door: 2040+720+2040 = 4800 x 2 = 9600
Bedroom 1 Window: 1200+900+1200 = 3300
Bedroom 1 Window: 1200+900+1200 = 3300
Bedroom 1 External Doors: 2100+620+620+2100 = 5440
Bedroom 1 Window: 1200+1500+1200 = 3900
Bedroom 1 Door: 2040+820+2040 = 4900 x 2 = 9800
Bedroom 1 Robe Door: 2040+720+2040 = 4800 x 2 = 9600
Bedroom 1 Robe Window: 600+600+600 = 1800
Bedroom 2 Window: 1200+2100+1200 = 4500
Bedroom 2 Door: 2040+820+2040 = 4900 x 2 = 9800
Bedroom 2 Robe Door: 2040+720+2040 = 4800 x 2 = 9600
Bedroom 2 Robe Window: 600+600+600 = 1800
Bedroom 3 Window: 1200+1800+1200 = 4200
Bedroom 3 Door: 2040+820+2040 = 4900 x 2 = 9800
Bedroom 3 Robe Door: 2040+720+2040 = 4800 x 2 = 9600
Bedroom 3 Robe Window: 600+600+600 = 1800
Bedroom 4 Window: 1200+1200+1200 = 3600
Bedroom 4 Window: 1200+1800+1200 = 4200
Bedroom 4 Cavity sliding door: 2040+820+2040 = 4900 x 2 = 9800
Linen Cupboard Door: 2040+520+520+2040 = 5120 x 2 = 10240
Linen Cupboard Door: 2040+520+520+520+520+2040 = 6160 x 2 = 12320
WC Window: 600+900+600 = 2100
WC Door: 2040+720+2040 = 4800 x 2 = 9600
Bathroom Window: 1200+1800+1200 = 4200
Bathroom Door: 2040+770+2040 = 4850 x 2 = 9700
Hallway Window: 1200+1200+1200 = 3600
| Total Architrave = 170 lineal metres + 10% waste = 187 lineal metres @ $6.40 | 1196.8
Skirting - upper floor - 65 lineal metres incl. 10% waste
Supplier: Sunshine Hardware
Bedroom 1: 4800-620-620+4200+4800+800-820+5000-720-720 = 16100
Bedroom 2: 3600+4200-720+3600-820+4200 = 14060
Bedroom 3: 3000+1540-720+3300+3000+1540-450+3300-820+450 = 11140
Bedroom 4: 4200+3000+4200-820 = 10580
Hallway: 3360-820-820+450+4000-720-770+2840 = 7520
| Total Skirting = 59.4 lineal metres + 10% waste = 65 lineal metres @ $6.40 | 416
E | Wet area tiles - upper floor - materials
Supplier: Colours Direct
15mm hardipanel , fixed to manufactuers specifications
Floors 300 x 300
Bathroom: 2.96 x 2.44 = 7.22m2 plus 10% waste = 7.94m2
WC: 1.02 x 2.195 = 2.24m2 plus 10% waste = 2.46m2
Ensuite: 3 x 2.79 = 8.37m2 plus 10% waste = 9.21m2
| Total floors = 11.67m2 @ $42/m2 | 504
Walls 250 x 100 - no detailed wet area elevations - estimate price
Bathroom: 10m2 plus 10% waste = 11m2
WC: N/A
Ensuite: 12m2 plus 10% waste = 13.2m2
| Total walls = 24.2m2 @ $44/m2 | 1056
F | Wet area tiles - upper floor only - Installation - including waterproofing
Installation: GT Tiling - $50/m2
| Floors - 11.67m2 x $50/m2 | 583.5
| Walls - 24.2m2 x $50/m2 | 1210
G | Roofing
Installation: Ascent Roofing Solutions
0.42 BMT Klip Lok zincalume trimdek roof sheeting fixed to manufactuers specification
on 38 x 75 F14 hardwood battens at 900 centres
tie down with 1-75mm No. 14 type 17 screws
120 x 35 F8 rafters at 1200 centres
400 x 100 zincalume box gutter
roof to be sarked with single sided sisalation
colorbond capping
Supply and install roofing as per drawings and specifications
14.95 x 21.070 = 315m2 - Less 7.39 x 7.46 = 55.13m2 - plus approx 10% waste
| 285m2 x $65/m2 = $18,580.70 | 18580.7
H | Aluminium windows and doors - lower floor only
Supplier: Axis Glass & Aluminuim
Windows
| Garage: 900 x 1500 | 294.65
| Laundry: 900 x 900 | 257.7
| Bathroom: 900 x 600 | 230.5
| Rumus: 1200 x 2100 | 373.85
| Kitchen: 1200 x 900 | 279.55
| Family: 2100 x 1500 | 616.5
| Dining: 2100 x 1500 | 616.5
| Lounge: 2100 x 1600 | 682.2
| Lounge: 1800 x 900 | 402.9
| Lounge: 1800 x 900 | 402.9
| Study: 1800 x 1800 | 486.75
| Hallway: 1800 x 900 | 402.9
| Total Aluminium Windows | 5046.9
I | External doors
Supplier: Sunshine Hardware
| Entry Doors: Double 2040 x 820 doors (2 of) | 616
| Garage Door: Sectional overhead door - 5000mm wide | 2239
| Garage External door: 2040 x 820 | 94
| Laundry External door: 2040 x 820 | 94
| Family Room: Aluminium sliding door 2100 x 3000 | 1848
| Family Room: Aluminium sliding door 2100 x 3600 | 2064
| Dining Room: Aluminium sliding door 2100 x 3000 | 1848
| Total External Doors | 8803
Internal doors - lower floor only
Supplier: Sunshine Hardware
2040 height x 35 thick
| Garage: 2040 x 820 | 48
| Store Room: 2040 x 820 | 48
| Laundry: 2040 x 820 | 48
| Bathroom: 2040 x 770 | 32
| Rumpus: Double doors - 2040 x 720 (2) | 96
| Pantry: 2040 x 620 | 48
| Store Room under stairs: 2040 x 720 | 48
| Lounge: Cavity slider - 2040 x 820 | 390
| Study: Flush solid core - 2040 x 820 | 48
| Total Internal Doors - lower floor only | 806
J | Internal doors - lower floor only
Installation - 2 hours per door @ $27.80/hour + 20%
| 9 x doors @ 2 hours per door = 18 hours @ $27.80 = $500.40 + 20% on costs | 600.48
K | Labour and Time Schedule
Days to complete
| Site Survey | 1
| Plumber - Internal Drainage | 3
| Electrical - Internal Power & NBN | 3
| Concretor - Slab preparation | 2
| Concreteor - Form & Steel | 2
| Pest Control | 1
| Concretor - Slab Pour | 1
| Delivery Pre Fabricated Frames & Trusses | 1
| Carpenter - Erect Ground Floor Pre Fabricated Frames | 2
| Carpenter - Floor Joists & Flooring | 2
| Carpenter - Stand Trusses | 2
| Carpenter - FEPS to Timber Joists | 1
| Scaffolder - Hang Scaffold | 1
| Roofer - Install Facia Gutter | 1
| Roofer - Install Roof | 3
| Delivery of Windows | 1
| Carpenter - Frame Tie Down | 2
| Carpenter - Ceiling Battens | 2
| Carpenter - Install sisilation and windows | 2
| Carpenter - Install External Cladding to scaffold areas | 4
| Painter - Paint External Cladding | 4
| Scaffolder - Remove scaffold | 1
| Plumbing Rough In | 3
| Electrical Rough In | 4
| NBN Rough In | 1
| Mechanical - Air conditioning Rough In | 1
| Frame Inspection | 1
| Carpenter - Install Double Garage Door | 1
| Pre-Sheet Inspection | 1
| Plasterer - Insulation | 3
| Plasterer - Wall, Ceiling Linings | 5
| Plasterer - Cornice Setting | 3
| Paint stair void area | 1
| Remove stair void | 1
| Install Stairs | 2
| Patch around Stairs | 1
| Carpentry - Fix Out | 4
| Waterproofing to wet areas | 1
| Joinery - Install Kitchen and Vanities | 2
| Tiler - Bed and Tile Wet Areas | 1
| Tiler - Tiling & Joint Sealing | 5
| Painter - Internal & Balance External Painting | 4
| Electrical - Fit Off | 4
| Plumbing - Fit Off | 4
| Mechanical - Air conditioning Fit Off | 1
| Carpenter - Install Door Hardware / Accessories | 3
| Carpenter - Install Mirrors and Shower Screens | 1
| Carpenter - Install Robes | 2
| Install Timber Stair Top Rail | 1
| Builders Clean | 1
| Defects | 5
| Carpet Installation | 2
| Final Sparkle Clean / Handover | 2