CPCCBC4007A

Plan building or construction work

ASSESSMENT SUMMARY

The assessment activities for CPCCBC4007A Plan building or construction work cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | FEI XU |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | FEI XU |
| --- | --- |
| Participant signature |  |
| Date | 18/09/2021 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 45 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

- Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | Specification |  |
| --- | --- | --- |

- Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | Queensland Building and Construction Commission Act 1991 (Qld) Schedule 1B s-33 | The building contractor under a regulated contract must not, before starting to provide the contracted services at the building site, demand or receive a deposit under the contract of more than— - for a level 1 regulated contract (other than a contract mentioned in paragraph (c))—10% of the contract price; or - for a level 2 regulated contract (other than a contract mentioned in paragraph (c))—5% of the contract price; or - for a level 1 or 2 regulated contract under which the value of the off-site work is more than 50% of the contract price—20% of the contract price. Maximum penalty—100 penalty units |  |

- Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Electrician | Arranges electricity to be connected; places wiring for lighting and power cables; Fixes switches, installs power points, wires electrical systems. |  |
|  | Plumber | Organises water supply; installs pipes and drains; installs roof and guttering; fits taps, hot water systems and toilets; ensures that downpipes are fitted and the sewer is connected |  |
|  | Gas fiotter | Places gas pipes to appliances. |  |

- Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

- Explain the importance of determining subcontractor or plant availability for a job.

| Answer | Planning of the labour requirements is of utmost importance and trades must be logically organised. For example, don’t organise for the painter if the plasterer has not started the walls. When organising plant for hire, it is essential to refer back to project management documentation, such as the Gantt Chart, to establish the dates they are required on site. |  |
| --- | --- | --- |

- Identify two (2) methods you might use to find a supplier for materials.

| Answer | Word of mouth and refered by someone you trust is the best way. Second you can post advertising or online searching |  |
| --- | --- | --- |

- Name two (2) factors that may impact on the availability of materials.

| Answer | Say covid-19 stops every busness and lockdown second is the international sea freight,also the quality of material |  |
| --- | --- | --- |

- Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | AS/NZS 1680 |  |
| --- | --- | --- |

- Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Crane | Carry yellow tongue to the floor joist |  |
|  | forklifts | Lift something heavier than people can lift |  |

- Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | wheelbarrow | To transport soil and concrete |  |
|  | Drilll | To drill the screws and brakets |  |

- Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | invoices receipts |  |
| --- | --- | --- |

- Name five (5) temporary services that need to be organised for a building site.

| Answer | Temporary electrical pole Water tapping Temporary fencing 'Tiger strips Waste bin |  |
| --- | --- | --- |

- True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

- Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

- Identify one (1) action you might take to facilitate site access for machinery.

| Answer | Check if traffic control is required, especially if large pieces of equipment such as cranes are required |  |
| --- | --- | --- |

- Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | Volume 2 section 2 | Volume 1 section D |  |

- You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | Compliance Assessment Application To be eligible for an out of hours construction approval: The proposed construction works cannot be undertaken during the prescribed daytime or evening hours (6.30am to 6.30pm Monday to Saturday) due to legitimate reasons such as pedestrian or worker safety, health or traffic reasons; and There must be a condition stipulated on a Council development approval that requires the applicant to notify or obtain approval from Council for proposed out of hours construction works. If both of these requirements are not met, Council cannot accept an out of hours construction application and as such, construction activities are to be conducted during the prescribed hours as per the Environmental Protection Act 1994 (EP Act)) |  |
| --- | --- | --- |

- In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | Plumbing and drainage | Queensland Urban Utilities Property Owner/s Consent form Property Information form Water Supply and Wastewater Works request |  |
|  | disposal permit | Brisbane City Council Application form for a disposal permit for contaminated soil |  |

- True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What document should be developed when purchasing supplies or construction materials?

| Answer | PURCHASE ORDER(PO |  |
| --- | --- | --- |

- True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Who should be contacted if items are missing from a delivery?

| Answer | supplier |  |
| --- | --- | --- |

- Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | Work Health and Safety Act 2011 S17 Schedule 3 | Management of risks A duty imposed on a person to ensure health and safety requires the person— - to eliminate risks to health and safety, so far as is reasonably practicable; and (b) if it is not reasonably practicable to eliminate risks to health and safety, to minimise those risks so far as is reasonably practicable. |  |

- Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | Work Health and Safety Regulation 2011 |  |
| --- | --- | --- |

- What document should be followed when disposing of hazardous materials?

| Answer | Safety data sheets |  |
| --- | --- | --- |

- An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10 |  |
| --- | --- | --- |

- True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | This can save a great deal of time, as the subcontractors can work on the next job while waiting for another to complete. If sub-contractors move to another location it can be difficult to ensure their return for the next stage of the project. |  |
| --- | --- | --- |

- Provide one (1) example to explain why construction operations must be sequenced.

| Answer | Withour steel frame installed,nothing else can be done until builder get form 15 16 |  |
| --- | --- | --- |

- Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

- Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 4 | Floor frame |  |
|  | 3 | Installing brick base |  |
|  | 6 | Roof trusses |  |
|  | 1 | Set out |  |
|  | 5 | Wall frames |  |

- Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| Task ID | Task | Preceding event | Nodes |
| --- | --- | --- | --- |
| A | Make enquiries and order all materials required | Start | 1 |
| B | Wait for bricks, sand and cement to arrive | A | 2 |
| C | Clear vegetation from the site | A | 2 |
| D | Order concrete to be delivered | A | 2 |
| E | Dig the trench | C | 4 |
| F | Pour the footings | E | 5 |
| G | Footings curing time | F | 6 |
| H | Load the bricks on the site | B | 3 |
| I | Mix the mortar and lay the bricks | H | 7 |
| J | Clean rubbish from the area | I | 8 |
|  | Finish | J | 9 |

G

F

H

E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

- Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | MONDAY WORKFLOWMAX |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

- What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- Describe the critical path.

| Answer | 1-2-4-5-6-7-8-9 The ‘critical path’ is defined as the shortest completion time possible to complete a job. Critical path information: • Sets out the build and its stages • Details and records the build timelines • Shows when sub contractors are due on site and for how long • Structures the supply chain of materials • Allows for delays and other supply chain problems • Caters for things like inclement weather cycles, other unpredictable problems and issues causing deferment and changes in the timelines, deferring supply of materials and labor Depending on the path you take will depend on how much float is in the job. Delays in your critical path can cause an increase in time and money |  |
| --- | --- | --- |

- True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | Resources: Unreliable labour or poor workmanship Unexpected delays: Strikes, illness, mistakes Building inspections: Failing inspections |  |
| --- | --- | --- |

- Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

- Why should you take photographs of site boundaries with neighbouring properties?

| Answer | If work is to affect neighbouring properties, you are required to compile a report on the condition of existing buildings and structures on adjacent site boundaries. Take photos to support your report – it will be helpful in the event of a dispute with a neighbour. |  |
| --- | --- | --- |

- When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

- When might a neighbouring property owner be required to refer to a condition report?

| Answer | If work is to affect neighbouring properties |  |
| --- | --- | --- |

CPCCBC4007A

Plan building or construction work

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | FEI XU |
| --- | --- |
| Participant signature |  |
| Date | 20/09/2021 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4007A

Plan building or construction work

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to plan on-site activities, including the employment of physical and human resources and the development of documentation and advice for relevant authorities: - Occasion 1: Residential projects - Occasion 2: Commercial projects The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - A construction program/schedule for a project showing: - The sequencing of the trades, etc. - Working and non-working days, etc. - Local authority construction commencement notices - Pre-construction site inspection reports or dilapidation reports - WHS policy The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document. |  |  |  |
| Resources required: Computer (ideally with project scheduling software), Building Contract, Organisational policies, Telephone, Facsimile. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: | FEI XU |  |  |
| Name of observer: | NELSON |  |  |
| Role of observer (Confirm suitability to sign) | SITE MANGER |  |  |
| Email address of observer | responsiveresponsible@gmail.com |  |  |
| Signature of observer: |  |  |  |
| Date: | 26/09/2021 |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| 1 Appraise contract documentation |  |  |  |
| - Review contract documentation, codes, standards and regulations to identify any unusual aspects of construction, use of materials or penalties. |  |  |  |
| - Determine availability of selected subcontractors to suit the job requirements. |  |  |  |
| - Assess availability of materials and confirm with suppliers. |  |  |  |
| - Identify site access requirements and limitations, taking action to facilitate entry. |  |  |  |
| - Prepare documentation for authorities controlling construction work and determine project commencement date. |  |  |  |
| - Implement procedures for controlling and recording site deliveries. |  |  |  |
| 2 Construction operation strategies |  |  |  |
| - Identify organisational strategies for implementing construction. |  |  |  |
| - Implement procedures for recording the hire of plant and equipment. |  |  |  |
| - Implement organisational WHS policies and procedures, including hazard and risk management. |  |  |  |
| - Implement procedures for the removal of existing services and hazardous materials, in accordance with Environmental Protection Agency requirements. |  |  |  |
| - Follow procedures for the control of multiple projects. |  |  |  |
| 3 Project schedule |  |  |  |
| - Sequence construction operations. |  |  |  |
| - Enter operation details into a manually prepared project schedule or computer-based software package. |  |  |  |
| - Define critical path of the project, revising as required. |  |  |  |
| - Adjust project timeframes to account for anticipated delays. |  |  |  |
| 4 Required resources |  |  |  |
| - Determine and document temporary services and site accommodation requirements. |  |  |  |
| - Determine and document plant requirements and availability, with reference to contract documentation. |  |  |  |
| - Determine and document on-site labour requirements, with reference to contract documentation. |  |  |  |
| 5 Condition reports |  |  |  |
| - Complete reports on the condition of existing buildings and structures on adjacent site boundaries. |  |  |  |
| - Forward copies of condition reports to the owners of adjacent buildings prior to commencing construction. |  |  |  |
| - Effectively communicate using the following methods: - Telephone, facsimile, email and in writing - Language/concepts appropriate to cultural differences - Non-verbal communication |  |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments

MR fei XU have some experience before work with me and he knows a lot suppliers and know how to identify access requirement and limitations, he has good sence of docu management and record site delivery numbers. In the current market, every supplier delays a lot and he is our key asset to manage anticipated delays and re-organise the labour. He has full communication skills using all methods.