Assessment Workbook 1

BSB51415 Diploma

of Project Management

The Project Life Cycle

Version 1.11 Produced 16 October 2018

Copyright © 2021 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 14 April 2016 | Version 1.0 produced following Training Package update | V1.0 |
| 22 June 2017 | Updated Table of Contents. | V1.1 |
| 16 October 2018 | Change to Practical Assessment | V1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Cover Sheet	4

Written Questions	5

Case Study	16

Instructions to Student	16

Introduction	17

Workbook Checklist	26

# Assessment Workbook Cover Sheet

| WORKBOOK: | Workbook 1 |  |  |
| --- | --- | --- | --- |
| TITLE: | The Project Life Cycle |  |  |
| FIRST AND SURNAME: | Mark Brownlie |  |  |
| PHONE: | 0421735675 |  |  |
| EMAIL: | Mbrownlie01@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Mark Brownlie |  | Signature: | Date: 30/05/21 |

# Written Questions

| - Below are the different stages of the lifecycle of a project. Match each lifecycle stage to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Stage | Description |
| C | Scoping | - It is during this phase that a project management plan is developed all comprehensive of individual plans for – cost, scope, time, quality, communication, risk and resources. Some of the important activities that mark this phase are -making WBS, development of schedule, milestone charts, GANTT charts, estimating and reserving resources, planning dates and modes of communication with stakeholders based on milestones, deadlines and important deliveries. |
| A | Planning | - It is in this phase that the project deliverable is developed and completed, adhering to the plan as developed in the previous phase. The project execution and project monitoring and Control are the 2 phases that mostly occur simultaneously. A lot of project management tasks during this phase capture project metrics through tasks like status meetings and project development updates, status reports, human resource development and performance reports. |
| B | Implementation | - A project is formally started, named and defined at a broad level during this phase. Project sponsors and other important stakeholders perform their due diligence on whether or not to undertake a project, or choose to undertake one project over another. Depending on the nature of the project, feasibility studies are conducted or as it may require. |
| E | Monitoring | - It includes a series of important tasks such as making the delivery, relieving resources, reward and recognition to the team members and formal termination of contractors in case they were employed on the project. |
| D | Closing | - This phase mostly deals with measuring the project performance and progression with respect to the project management plan. Scope verification and control to check and monitor for scope creep, change control to track and manage changes to project requirement, calculating key performance indicators for cost and time are to measure the degree of variation if any and in which case corrective measures are determined and suggested to keep project on track. |

- Consider a project that you are currently working on or you would most likely work on in the future. Provide an outline of typical project phases that would take place during the Implementation Stage of this project.

Procurement, Recruitment, Site set up, recruitment, Tunnel excavation, procurement, recruitment , Tunnel fitout, Tunnel commissioning, Handover.

| - The following are various structures in which the Implementation Stage of the project can be carried out. Match each structure to its correct descripition. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Structure |  | Description |
| D | Sequential phase-to-phase relationship | - Projects intended to respond to high levels of change and ongoing stakeholder involvement. Also very iterative and incremental but differ in iterations being very rapid (2-4 weeks) and are fixed in time and cost. |
| E | Overlapping phase-to-phase relationship | - The project scope, time and cost are determined as early in the project lifecycle as practically possible. |
| B | Predictive life cycle | - The project phases repeat one or more project activities as the project team’s understanding of the product increases. |
| C | Iterative/incremental life cycle | - In this structure, a new phase starts only when a previous phase is complete. The step-by-step nature of this approach reduces uncertainty, but may eliminate options for reducing the schedule. |
| A | Adaptive Life Cycle | - This is where a phase starts prior to the completion of a previous one. This can sometimes be applied as an example of the schedule compression technique called fast tracking. Overlapping phases may increase risk and can result in rework if a subsequent phase progresses before accurate information is available from the previous phase. |

| - Which of the following are activities that usually take place as part of the closing of a project? Select all that apply. |  |
| --- | --- |
|  | - Project evaluation |
|  | - Warrantee requirements |
|  | - Create communications log |
|  | - Develop project management plan |
| X | - Writing and delivery of project final report |
| X | - Finalisation of accounts and other financial documentation |
|  | - Delvelop project charter |
| X | - Handover of project deliverables |
| X | - Settling of financial liabilities |
| X | - Project evaluation |
|  | - Identify stakeholders |
| X | - Signing off by the project sponsor |
| X | - Finalise lessons learnt documentation and communicating it where needed |
| X | - Transition of responsibility or ownership of project deliverables or products |
| X | - Archiving of project documentation |

| - The following are different methodologies used to break project objectives into achievable project deliverables. Match each of the following to its correct description. Write the letter of your answer in the spaces provided. |  |  |
| --- | --- | --- |
| Methodology |  | Description |
| D | Project governance | - A document that formally authorises a project or a phase. It includes the initial requirements that satisfy the stakeholders’ needs and expectations. It provides the overall high level description of the strategies and goals of your project. |
| B | Project management information system | - An automated tool, such as scheduling software tool, a configuration management system, and information collection and distribution system or web interfaces to other outline automated systems. |
| A | Project charter | - A document covering all the details of the project down to a very detailed level. It can be presented in the form of a Gantt chart or any other document that displays project activities along a timeline. |
| E | Work Breakdown Structure | - It provides a management structure for the project manager and their team to deliver the project. It provides the support, processes and tools needed for the project to be delivered. |
| C | Project plan | - A document detailing the subdivision of project deliverables into smaller more manageable components. |

| - Below are different types of project governance models. Match each model to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Project governance model |  | Description |
| B | Programmatic Based | - In this model, project managers have a high level of authority to manage and control the project resources. The project manager in this structure has total authority over the project and can acquire resources needed to accomplish project objectives from within or outside the parent organization, subject only to the scope, quality, and budget constraints identified in the project. |
| C | Matrix Based | - A traditional structure in which program sector managers have formal authority over most resources. It is only suitable for projects within one program sector. |
| A | Project Based | - This model allows program units to focus on their specific technical competencies and allow projects to be staffed with specialists from throughout the organisation. |

| - List two (2) documentation that must be created to record strategies and goals for integration processes. In your own words, briefly describe each documentation. Do not exceed fifty (50) words for each discussion |  |
| --- | --- |
| Documentation | Discussion |
| PROJECT PLAN | Project plan is a broad guide for the project for the scope, time, cost, quality, human resources, communication, risk, procurement and integration. |
| PROJECT CHARTER | A Project Charter is a document that documents the stakeholders needs and expectations |

| - Consider the communication media you would utilise in project management. - List three (3) communication media you would utilise in project management. - Discuss how each communication media is applied on various projects. |  |
| --- | --- |
| Communication media | Discussion |
| Email | Emails are used for Project updates, notification of works, general internal & external communication & procurement |
| Internet Portal | Internet portals can be used for document and file collaboration for up to date information and for teams working remotely. Safely updates can also be used on this platform |
| Face to Face meetings | Face to face meetings are a successful function for daily on site communication between teams. Safety updates and work coordination’s are updates through this technique. |

| - Discuss how each of the following communication methods below is applied on various projects. - Verbal communication - Non-verbal communication - Written communication In your discussion, include at least one (1) specific example or scenario on how each communication method is applied on various projects. |  |
| --- | --- |
| Communication Method | Discussion (with at least one (1) specific example or scenario for each communication method) |
| Verbal communication | Face to face meetings or prestart. Example of a site vehicle management plan change, this can be conveyed through a verbal site pre start meeting |
| Non-verbal communication | Hand signals or light signs used to communicate. Example of the use of Cap lamp signals used underground for communication. |
| Written communication | Email communication of work activities forecast. |

| - List two (2) types of project management information systems (PMIS) and, in your own words, discuss how each is applied in project management. Do not exceed 50 words for each discussion. |  |
| --- | --- |
| Information systems | Application |
| Computer Based PMIS | Computer based pmis is used as a large storage system for up dated plans, budgets and programming |
| Web based pmis | Web based pmis are used when employees are working remotely from site and updates can be made real time. |

| - The following are methods used to evaluate information systems and communication processes. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Method |  | Description |
| D | System quality | - A performance measure to evaluate the efficiency of an investment (such as in this case, resources used to facilitate project communication). It measures the return on an investment relative to the investment’s cost. |
| B | Information quality | - The information system is assessed in terms of accuracy of output, promptness of output, precision of output, reliability of output, arrival of output, output completions, and output format |
| A | ROI | - It is a useful tool for performing retrospective analyses of the characteristics of internal communication. With the help of this model we can obtain several interpretations of the characteristics of project communications which help improve the communication process and also the project management process. |
| C | Internal Communication Analysis Model | - The information system is assessed in terms of response time, accessibility, realization of user’s demands, correction of mistakes, model and data safety, system documentation and procedures, system flexibility and system compatibility. |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You will be working in this project in every case study assessment throughout this course. The project involves the landscaping of a new eco-resort. The company has hired you on the basis of your ability to analyse project methodology, not on your knowledge of the nature of the landscaping work they perform. At this stage of the project the project charter and project plan have already been developed. You have been assigned to examine the project plan before the project launches in three months’ time. In particular you have been asked the following questions which you will need to provide answers for upon examination of the project charter and the project plan. The documents you need to complete the succeeding tasks can be accessed by accessing the following links: Project Charter version 1 (.pdf) Project Plan version 1 (.pdf) Project Gantt Chart (.mpp) Project Gantt Chart (.pdf) Project Network Diagram (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

| - List all personnel (name, title / designation, and company) who are required to sign off on the Project Plan before the project is endorsed for commencement. Discuss why each personnel you listed are required to sign off on the Project Plan. Do not exceed fifty (50) words for each discussion. |  |  |
| --- | --- | --- |
| Personnel | Title / Designation, Company | Discussion |
| Susan Wills | Program Manager – Massive EcoDevelopment Corporation | As the Program manager of Eco Developments coroporation Susan must sign off that she agrees with the scope, time, costs, Quality and procurement of the plan. |
| Stephen Lyons | Planning Manager - Cascade Peak Shire Council | As the planning manager of the council Stephen needs to sign off that he agrees the plan meets the councils needs and requirements for approval. |
| Sam Ng | Project Manager – Awesome Landscapes Pty Ltd | As the Project manager of Awesome landscapes Sam needs to agree to project scope, time, cost, quality, human resources, communications, risk, procurement and integration |
| Kate Chan | Project Manager - Timber Home Construction Ltd | Kate needs to agree to the scope, time, cost, quality, human rescourses, communication, risk, procurement and intergration. |
| Kim Nguyen | Director – Awesome Landscapes Pty Ltd | As Director of Awsome Landscapes Kim needs to approve any change requests to the project plan and needs to approve costs and risk. |

- Review the Project Plan. - Does the Project Plan show evidence that the project has been appropriately approved for commencement? - Does the Project Plan show evidence that it has been distributed to all stakeholders who are required to have a copy? Guidance: If it has been approved and distibuted, indicate which section(s) or page(s) in the Project Plan indicate so. If not, explain what needs to be done to have the project approved for commencement.

- Yes, Sign off The project plan only becomes valid once signed off by the following members of the project steering committee. Name Position Signature Date Susan Wills Program Manager – Massive EcoDevelopment Corporation SusanWills 28 May 2016 Stephen Lyons Planning Manager - Cascade Peak Shire Council S.Lyons 28 May 2016 Kate Chan Project Manager - Timber Home Construction Ltd Kate Chan 28 May 2016 Kim Nguyen Director – Awesome Landscapes Pty Ltd Kim Nguyen 28 May 2016 Sam Ng Project Manager – Awesome Landscapes Pty Ltd Sam Ng 28 May 2016. All in which have signed off.

- Yes, Distribution List The project plan must be distributed to all members of the project steering committee. Name Position Signature Date Susan Wills Program Manager – Massive EcoDevelopment Corporation SusanWills 28 May 2016 Robert Hinson Project Manager – Massive EcoDevelopment Corporation R.Hinson 28 May 2016 Stephen Lyons Planning Manager - Cascade Peak Shire Council S.Lyons 28 May 2016 Kate Chan Project Manager - Timber Home Construction Ltd Kate Chan 28 May 2016 Kim Nguyen Director – Awesome Landscapes Pty Ltd Kim Nguyen 28 May 2016 Sam Ng Project Manager – Awesome Landscapes Pty Ltd Sam Ng 28 May 2016 all in which have signed off

- How will the Project Outcomes be reported?

The outcomes of all internal and external audits are to be included in the Project progress reports

- List all personnel (name, title/designation, company) who must have a copy of the Project Progress Reports. Discuss why each personnel you listed must have a copy of the Project Progress . Do not exceed fifty (50) words for each discussion.

| Personnel | Title / Designation, Company | Discussion |
| --- | --- | --- |
| Stephen Lyons | Planning Manager - Cascade Peak Shire Council) | To ensure that the project is progressing as approved by the council |
| Kate Chan | Project Manager - Timber Home Construction Ltd | To ensure they are progressing in construction to the agreed timeline |
| Kim Nguyen | Director – Awesome Landscapes Pty Ltd | To ensure the quality, time line of the project is progressing as planned and costs in accounted for. |
| Sam Ng | Project Manager – Awesome Landscapes Pty Ltd | To ensure the timeline, risk, quality and budget is as expected |
| Robert Hinson | Project Manager – Massive EcoDevelopment Corporation | To ensure the timeline, cost and quality of the project is as expected |
| Susan Wills | Program Manager – Massive EcoDevelopment Corporatio | To ensure time, cost and procurement is accounted for. |

| - At which stage of the project life cycle is the project? Assume the current date is 7 May 20xx, where 20xx is the current year. |  |
| --- | --- |
|  | - Scoping |
| X | - Planning |
|  | - Monitoring |
|  | - Implementation |
|  | - Closing |

- Discuss how Massive Eco-development Corporation is going to maintain effective integration between the three projects? Your discussion must be 100 – 200 words in length. Guidance: Why have the three projects been planned separately rather than being integrated into one single project? Discuss factors that ensure the effective running of the three projects running together as separate projects.

The 3 project have been planned seperatly to reduce the construction impact. To intergrate the 3 projects they can begin the next project on near completion of the previous. Example of beginning the excavation of utility services when access roads are complete and whilst retaining walls are being completed.

| - In your own words, discuss each of the following processes involved in the Closing Stage of the project. Do not exceed 150 words for each discussion. |  |
| --- | --- |
| Payment of Remaining Invoices | This involves scrutinising the final submitted invoices of contractors and determing payments involved for for final budget. These must be paid prior to project closure |
| Project Closure Meeting Documentation | This shows the lessons learnt, audit reports and results of the project |
| Pre-meeting Audit | This must be evaluated by a independent project auditor prior to the final project meeting |
| Final Project Meeting | This meeting is held in which all project steering committee member are to attend. Each member will receive a copy of the project completion report, final version of the project plan, prohect archives checklist and formal acceptance and closure. |
| Final Project Invoice | After successful completion od the final p[roject documentation, Awesome landscapes can then raise a invoice for massive Eco development Corporation for the final contract payment. |
| Project Archival | All project documentation can be archived Upon payment of the final contract payment by Massive Eco-development Corporation |

- How will the project be monitored?

The project will be monitored through Council, internal and external Audits. The outcome of the audits will be included in the status reports.

- Review the objectives of the project. - Do the objectives of the project align with the business objectives of Awesome Landscapes? Explain your reasoning. - Do the objectives of the project align with business objectives of project sponsor organisation? Explain your reasoning. Each discussion must be between 50 – 150 words.

- Yes, Completing the planting and landscaping to ensure the resort blends in perfectly with the natural forest and Ensure the forest flora and fauna is minimally impacted by the construction project are two main objectives which align.

- Yes, with the need of the cabins to be built at the mountain in a eco friendly design minimising the impact of the setting. The Objectives of the project plan reiterate this for the design.

- Sam has a gut feeling there will be some changes to the project once it commences. A rumour is spreading that there are going to be some additional chalets built requiring the construction of three more retaining walls than what appears in the project plan. He has specifically asked if he can approve and sign off on the extra construction himself knowing there is quite a big contingency budget to the project. Explain the procedure Sam would follow regarding the construction of the three additional retaining walls. Your discussion must not exceed 500 words. Guidance Answer Sam’s question by providing in your own words a specific procedure for the approval of the construction of three additional retaining walls. When mentioning any people in the procedure, list them by name and job title.

Sam must detail all the changes into a change request and this will be negotiated between the project manager (Awesome Landscaping) and the program manager (Massive Eco-Development. The draft change request will then be sent to the planning manager of Cascade Peak Shire Council who will advise if a new Council approval is needed as part of the proposed changes. If a Council approval is needed, the program manager (Massive Eco-Development) will then commence the application process as needed. Once Council approvals have been granted for the additional retaining walls, the matters within the change request will be modified within the project plan, and other project documentation as required. The project plan must include all change requests along with an up to date change register. The changes in the project documentation must be clearly colour coded by highlighted text. The change request and all modified documentation are then examined at a face to face meeting by Susan Wills (Program Manager – Massive Eco-Development Corporation), Stephen Lyons (Planning Manager - Cascade Peak Shire Council), Kate Chan (Project Manager - Timber Home Construction Ltd), Kim Nguyen (Director – Awesome Landscapes Pty Ltd), Sam Ng, Project Manager – Awesome Landscapes Pty Ltd and any other stakeholders directly impacted on the change request. The change request will then be signed off by Susan Wills (Program Manager – Massive Eco-Development Corporation), Stephen Lyons (Planning Manager - Cascade Peak Shire Council), and Kim Nguyen (Director – Awesome Landscapes Pty Ltd). The changes of the additional 3 retaining walls can then be communicated and implemented by the project manager (Awesome).

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document