BSBPMG514

Manage project cost

ASSESSMENT SUMMARY

The assessment activities for BSBPMG514 Manage project cost cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Ben Dudman |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

BSBPMG514

Manage project cost

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Ben Dudman |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 17 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

Explain the ‘Plan Cost Management’ process.

| Answer | Plan Cost Management is the process which establishes policies, procedures and documentation regarding project costs (including planning, managing, expending and controlling). |  |
| --- | --- | --- |

Identify seven (7) types of information which might be included in a cost management plan.

| Answer |  | Information type |  |
| --- | --- | --- | --- |
|  | 1 | Structure of cost accounts |  |
|  | 2 | Authorisation levels |  |
|  | 3 | Units of measure to be used |  |
|  | 4 | Variance control thresholds |  |
|  | 5 | Earned Value management methods |  |
|  | 6 | Reporting frequency |  |
|  | 7 | Procedures for non-project related costs |  |

Explain how the work breakdown structure and work packages can be used to determine resource requirements for individual tasks.

Answer

The WBS breaks the project deliverables down into work packages and individual tasks. From this breakdown, it can be easier to assign resources.

Explain the different costing methods between costing a deliverable that is purchased complete and new and a deliverable that is constructed in-house.

| Answer | Purchased deliverables can be costed using market price plus any extra charges for delivery, etc. Costing deliverables which are constructed in-house is more complicated as all elements required for the deliverable need to be estimated. This includes raw materials, labour, etc. |  |
| --- | --- | --- |

Describe the difference between top-down and bottom-up budgeting when managing a project.

| Answer | In “bottom-up” budgeting, the cost of each work package can be estimated and aggregated for a total project budget. In “top-down” budgeting, a total budget is determined for the project using analogous, parametric or some other form of estimation and this budget is split amongst the work packages in the WBS. |  |
| --- | --- | --- |

Explain the concept of ‘analogous estimating’. Identify one (1) problem that may exist with analogous estimating.

| Answer | Analogous estimating involves comparing the current project with a similar previous project. One problem with this method is that estimating can be inaccurate if the two projects are dissimilar or not close in time. |  |
| --- | --- | --- |

Explain the concept of ‘parametric estimation’. Provide one (1) one example to support your response.

| Answer | Parametric estimation is method which involves using a statistical relationship to calculate a project’s costs. An example of this is a cost per kilometre to restore a rural road. |  |
| --- | --- | --- |

Explain what is meant by a ‘time-phased budget’.

| Answer | Time phased budgets are budgets divided over the duration of the project (i.e. weekly, monthly or yearly). Each specified interval becomes a control point where actual costs can be compared with budgeted costs. |  |
| --- | --- | --- |

Describe what is meant by a ‘contingency reserve’ in project budgeting.

| Answer | Contingency reserve is the amount of money allocated for potential risks identified in the project. It is expected that some of these risks will occur but it is uncertain which ones and to what extent. |  |
| --- | --- | --- |

Discuss the purpose of a management reserve in project budgeting.

| Answer | A management reserve is additional project funding which can be added to the project baseline if unexpected costs are incurred. |  |
| --- | --- | --- |

Using the information below, develop a single period budget for building a shed in the form of a spreadsheet. 

You may use the embedded template on the following page (refer to Handout 3, if encountering problems with the embedded file), or insert your own spreadsheet.

Planning permission $200 Preparing ground Trenching machine 8 hours X $140 Labour 8 hours X $28 Slab $3200 Shed cost $4500 Labour – 5 labour days X 8 hours per day X $28 Installing electrics Electrician $90 X 3 hours Electrical goods $185 Work bench $500 Cupboards Cupboard packs $250 - Constructing cupboards – labour 2 hours X $32/hr - Variance threshold is 10%

| Answer |  |  |
| --- | --- | --- |

Identify significant variances (those above your variance threshold) for the following actual costs for the project budget developed in Q11. 

It is recommended to use the same spreadsheet from the previous question.

Planning permission $200 Preparing ground Trenching machine 8 hours X $140 Labour 8 hours X $32 Slab $3400 Shed cost $4500 Labour – 5.5 labour days X 8 hours per day X $32 Installing electrics Electrician budget $110 X 3 hours Electrical goods $185 Work bench $650 Cupboards Cupboard packs $250 - Constructing cupboards – labour 2 hours X $32/hr

| Answer |  |  |
| --- | --- | --- |

Identify any significant budgeting errors identified from the variance analysis of budget costs and actual costs given in Q11. and Q12.

| Answer | Preparing ground (labour) AC = $256, EV = $224, Variance = $32 (14%) Actual labour rates were $4/hr more than budgeted. Shed (labour) AC = $1408, EV = $1120, Variance = $288 (26%) Work took half a day longer than allowed for in the budget and was $4/hr more expensive. Electrician AC = $330, EV = $270, Variance = $60 (22%) Electrician was $20/hr more expensive than budget. Work Bench AC = $650, EV = $500, Variance = $150 (30%) |  |
| --- | --- | --- |

Define the following terms relating to variance.

| Answer | Term | Definition |  |
| --- | --- | --- | --- |
|  | Cost variance | A coast variance is where the budgeted cost is greater or less than the actual cost. |  |
|  | Schedule variance | Schedule variance is where the project is behind or ahead of schedule at a time control point. This will result in the project actual costs differing from the Planned Value at that control point. |  |

Identify three (3) reasons for cost variances.

| Answer |  | Information type |  |
| --- | --- | --- | --- |
|  | 1 | Cost of project consumables has increased. |  |
|  | 2 | Increased labour required to complete a task (hours). |  |
|  | 3 | Increased labour rates or rates inaccurately estimated. |  |

Explain the purpose of a variance threshold.

| Answer | Variance threshold is the dollar value or percentage variance that must be investigated. This ensures that time is not wasted on investigating minor variances and ensuring that any variances significant variances are investigated and corrective actions are implemented. |  |
| --- | --- | --- |

Identify three (3) accounting measures a project manager should take when closing the project’s cost management.

| Answer | Measure | Description |  |
| --- | --- | --- | --- |
|  | 1 | Make sure that all costs are accrued into the project’s costs before closing. |  |
|  | 2 | Final figures should be compared with the final project cost baseline. Significant variances should be explained and lessons learnt should be reported |  |
|  | 3 | The project manager should ensure that access to project accounts is closed. |  |

BSBPMG514

Manage project cost

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name |  |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 |  |  |

Assessor Comments

BSBPMG514

Manage project cost

| Practical Task 1 |  |  |
| --- | --- | --- |
| Description of task: A suitable observer is to verify the participant’s ability to identify, analyse and refine project costs to produce a budget, and to use this budget as the principal mechanism to control project cost. The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - Quotes - Project estimates - Variations - Tenders The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document |  |  |
| Resources required: Computer |  |  |
| Assessment of task |  |  |
| Name of participant: |  |  |
| Name of observer: |  |  |
| Role of observer (Confirm suitability to sign): |  |  |
| Email address of observer: |  |  |
| Signature of observer: |  |  |
| Date: | Click here to enter a date. |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |
| 1 Develop cost-management plan |  |  |
| - Within delegated authority, develop a cost-management plan to ensure clarity of understanding and ongoing management of project finances. |  |  |
| 2 Determine project costs |  |  |
| - Seek input from stakeholders and guidance from others when determining resource requirements for tasks identified in the work breakdown structure. |  |  |
| - Estimate project costs to enable project budget to be prepared within agreed tolerances. |  |  |
| - Develop a project budget. |  |  |
| 3 Monitor and control project costs |  |  |
| - Implement agreed financial-management processes and procedures to monitor actual expenditure against budget. |  |  |
| - Select and use cost-analysis methods and tools to identify cost variations and evaluate alternative actions. |  |  |
| - Implement and monitor agreed actions to maintain financial objectives. |  |  |
| - Provide accurate and timely financial reports. |  |  |
| 4 Complete cost-management processes |  |  |
| - Conduct appropriate activities to signify financial completion. |  |  |
| - Use available records to review project outcomes and determine effectiveness of project cost management. |  |  |
| - Review cost-management issues and document improvements. |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |

observer Comments