CPCCBC4007A

Plan building or construction work

ASSESSMENT SUMMARY

The assessment activities for CPCCBC4007A Plan building or construction work cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Glenn Parrish |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Glenn Parrish |
| --- | --- |
| Participant signature |  |
| Date | 7/08/2020 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 45 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

- Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | Project Plans |  |
| --- | --- | --- |

- Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | Queensland Building and Construction Commission Act 1991 Part 4, Division 2, 33 | Level 1 contract 10% Level 2 contract 5% Level 1 or 2 where off site work is more than 50% of contract price 20% Maximum penalty 100 penalty units |  |

- Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Bricklayer | Erecting brick walls |  |
|  | Plasterer | Installs internal wall sheets and cornice |  |
|  | Tiler | Installs wall and floor tiles |  |

- Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

- Explain the importance of determining subcontractor or plant availability for a job.

| Answer | In order to complete the job on time without costly delays |  |
| --- | --- | --- |

- Identify two (2) methods you might use to find a supplier for materials.

| Answer | Internet Word of mouth |  |
| --- | --- | --- |

- Name two (2) factors that may impact on the availability of materials.

| Answer | Whether or not they come from overseas or interstate Whether or not they are a specialised or unique product |  |
| --- | --- | --- |

- Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | AS/NZS 1680 |  |
| --- | --- | --- |

- Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Excavator | Site preparation, digging footings, digging plumbing and electrical trenches. |  |
|  | Crane | Craning roof trusses, swimming pools, materials. |  |

- Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | Scaffolding | Safe erection of block walls, roof and guttering |  |
|  | Concrete mixer | Mixing concrete |  |

- Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | Invoices and receipts Whs paperwork relating to the plant |  |
| --- | --- | --- |

- Name five (5) temporary services that need to be organised for a building site.

| Answer | Water Electricity Fencing Toilets Skip bins |  |
| --- | --- | --- |

- True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

- Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

- Identify one (1) action you might take to facilitate site access for machinery.

| Answer | Erect barriers, traffic control |  |
| --- | --- | --- |

- Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | Volume 2 Part 3.9, Safe Movement and Access | Volume 1 Section D, Access and Egress |  |

- You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | Operational Works/Compliance Assessment SmartForm Construction Noise Management Plan Minimum 10 working days |  |
| --- | --- | --- |

- In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | Building approval | Local council Building Plans |  |
|  | Plumbing Approval | Local council Hydraulic plans |  |

- True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What document should be developed when purchasing supplies or construction materials?

| Answer | Purchase Order |  |
| --- | --- | --- |

- True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Who should be contacted if items are missing from a delivery?

| Answer | Supplier |  |
| --- | --- | --- |

- Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | The Work Health and Safety Act Sections 17-18 | That risks should be identified and eliminated, so far as reasonably practicable, or otherwise minimised |  |

- Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | The Work Health and Safety Regulation 2011 |  |
| --- | --- | --- |

- What document should be followed when disposing of hazardous materials?

| Answer | MSDS |  |
| --- | --- | --- |

- An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10m2 |  |
| --- | --- | --- |

- True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | It can save time by sub-contractors moving to another location and having to organise them to return for the next stage |  |
| --- | --- | --- |

- Provide one (1) example to explain why construction operations must be sequenced.

| Answer | It is impossible for a tiler to tile a bathroom if the plumbing, electrical and subsequently the walls in place |  |
| --- | --- | --- |

- Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

- Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 4 | Floor frame |  |
|  | 3 | Installing brick base |  |
|  | 6 | Roof trusses |  |
|  | 1 | Set out |  |
|  | 5 | Wall frames |  |

- Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| Task ID | Task | Preceding event | Nodes |
| --- | --- | --- | --- |
| A | Make enquiries and order all materials required | Start | 1 |
| B | Wait for bricks, sand and cement to arrive | A | 2 |
| C | Clear vegetation from the site | A | 2 |
| D | Order concrete to be delivered | A | 2 |
| E | Dig the trench | C | 4 |
| F | Pour the footings | E | 5 |
| G | Footings curing time | F | 6 |
| H | Load the bricks on the site | B | 3 |
| I | Mix the mortar and lay the bricks | H | 7 |
| J | Clean rubbish from the area | I | 8 |
|  | Finish | J | 9 |

G

F

Hoad

E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

- Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | Microsoft Excel |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

- What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- Describe the critical path.

| Answer | 1,2,4,5,6,7,8,9 |  |
| --- | --- | --- |

- True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | Weather Delays Supply Delays Labour Delays |  |
| --- | --- | --- |

- Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

- Why should you take photographs of site boundaries with neighbouring properties?

| Answer | In the event of a dispute with the neighbour |  |
| --- | --- | --- |

- When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

- When might a neighbouring property owner be required to refer to a condition report?

| Answer | If any damage has occurred during construction |  |
| --- | --- | --- |

CPCCBC4007A

Plan building or construction work

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name |  |
| --- | --- |
| Participant signature |  |
| Date | Click here to enter a date. |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4007A

Plan building or construction work

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to plan on-site activities, including the employment of physical and human resources and the development of documentation and advice for relevant authorities: - Occasion 1: Residential projects - Occasion 2: Commercial projects The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - A construction program/schedule for a project showing: - The sequencing of the trades, etc. - Working and non-working days, etc. - Local authority construction commencement notices - Pre-construction site inspection reports or dilapidation reports - WHS policy The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document. |  |  |  |
| Resources required: Computer (ideally with project scheduling software), Building Contract, Organisational policies, Telephone, Facsimile. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: |  |  |  |
| Name of observer: |  |  |  |
| Role of observer (Confirm suitability to sign) |  |  |  |
| Email address of observer |  |  |  |
| Signature of observer: |  |  |  |
| Date: |  |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| 1 Appraise contract documentation |  |  |  |
| - Review contract documentation, codes, standards and regulations to identify any unusual aspects of construction, use of materials or penalties. |  |  |  |
| - Determine availability of selected subcontractors to suit the job requirements. |  |  |  |
| - Assess availability of materials and confirm with suppliers. |  |  |  |
| - Identify site access requirements and limitations, taking action to facilitate entry. |  |  |  |
| - Prepare documentation for authorities controlling construction work and determine project commencement date. |  |  |  |
| - Implement procedures for controlling and recording site deliveries. |  |  |  |
| 2 Construction operation strategies |  |  |  |
| - Identify organisational strategies for implementing construction. |  |  |  |
| - Implement procedures for recording the hire of plant and equipment. |  |  |  |
| - Implement organisational WHS policies and procedures, including hazard and risk management. |  |  |  |
| - Implement procedures for the removal of existing services and hazardous materials, in accordance with Environmental Protection Agency requirements. |  |  |  |
| - Follow procedures for the control of multiple projects. |  |  |  |
| 3 Project schedule |  |  |  |
| - Sequence construction operations. |  |  |  |
| - Enter operation details into a manually prepared project schedule or computer-based software package. |  |  |  |
| - Define critical path of the project, revising as required. |  |  |  |
| - Adjust project timeframes to account for anticipated delays. |  |  |  |
| 4 Required resources |  |  |  |
| - Determine and document temporary services and site accommodation requirements. |  |  |  |
| - Determine and document plant requirements and availability, with reference to contract documentation. |  |  |  |
| - Determine and document on-site labour requirements, with reference to contract documentation. |  |  |  |
| 5 Condition reports |  |  |  |
| - Complete reports on the condition of existing buildings and structures on adjacent site boundaries. |  |  |  |
| - Forward copies of condition reports to the owners of adjacent buildings prior to commencing construction. |  |  |  |
| - Effectively communicate using the following methods: - Telephone, facsimile, email and in writing - Language/concepts appropriate to cultural differences - Non-verbal communication |  |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments