CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

The assessment activities for CPCCBC4003A Select and prepare a construction contract, CPCCBC4016A Administer a construction contract & CPCCBC4032A Apply contract law to sales processescover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Matt Cumiskey |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for CPCCBC4003A | Competent | Not Yet Competent |
| Outcome for CPCCBC4016A | Competent | Not Yet Competent |
| Outcome for CPCCBC4032A | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Matt Cumiskey |
| --- | --- |
| Participant signature |  |
| Date | 14/01/2020 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 51 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

Order the following elements of an agreement from 1 to 4.

| Answer | Element Number | Element |  |
| --- | --- | --- | --- |
|  | 2 | Acceptance |  |
|  | 4 | Consideration |  |
|  | 3 | Intention of legal consequences |  |
|  | 1 | Offer |  |

When would an offer be considered to have lapsed?

| Answer | An offer will lapse: - When the time for acceptance expires; - If the offer is withdrawn before it is accepted; or - After a reasonable time in the circumstances (generally the greater the value of the contract, the longer the life of the offer) |  |
| --- | --- | --- |

What happens to the offer if new terms are suggested?

| Answer | If new terms are suggested then that is regarded as a counter offer which can be accepted or rejected. |  |
| --- | --- | --- |

What does it mean when a contract is supported by ‘valuable consideration’?

| Answer | Supported by valuable consideration means: - One party promises to do something in return for a promise from another party - Consideration is what each party gives to the other as the agreed price for the other’s promises - Usually the consideration is the payment of money |  |
| --- | --- | --- |

Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

| Answer | 2 parties who may be deemed to not have the capacity to enter into a contract are: - Persons suffering from a mental disability - Intoxicated individuals |  |
| --- | --- | --- |

- Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

| Answer | Consent is an act of reason and deliberation. A person who possesses and exercises sufficient mental capacity to make an intelligent decision demonstrates consent by performing an act recommended by another. Consent is implied in every agreement. Apparent consent may be negated because of mistake, fraud, innocent misrepresentation, duress or undue influence, all of which are defences to the enforcement of the contract. |  |
| --- | --- | --- |

Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

| Answer | The Queensland building industry regulator is the Queensland Building and Construction Commission. Its primary role is to uphold regulatory compliance and work with consumers and licensees. It is focused on ensuring safety across the industry. The QBCC offer a number of pro-forma building contracts via their website which can be used for domestic work only (not commercial). They can also assist in situations where a contractor has completed defective works by directing them to be fixed or completed. |  |
| --- | --- | --- |

Under what laws are domestic building contracts regulated?

| Answer | On 1 July 2015 Schedule 1B of the Queensland Building and Construction Commission Act 1991 (‘the QBCC Act’) came into force. This legislation replaced the Domestic Building Contracts Act 2000 (‘the DBC Act’) and applies to domestic building contracts entered into from 1 July 2015. This legislation sets out contract requirements for the erection or construction of a detached dwelling (i.e. a single, free-standing home or duplex) or the renovation, alteration, extension, improvement or repair of a home, and for other domestic building work associated with a home, such as building a driveway, fence or swimming pool. |  |
| --- | --- | --- |

Domestic building contracts must be put in writing once the work exceeds what value?

| Answer | Domestic building contracts must be put in writing once the value of the work exceeds $3000. |  |
| --- | --- | --- |

A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

| Answer | The QBCC Act requires that commercial contracts for building work over $10,000 must be in writing before work starts. |  |
| --- | --- | --- |

Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

| Answer | Under the QBCC Act (Schedule 1B, Section 15), contractors must give the Owner a signed copy of the entire contract (including any plans and specifications) within 5 business days after entering the contract |  |
| --- | --- | --- |

What are the benefits of having a written contract in place between parties?

| Answer | Benefits of having a written contract in place between parties are: - Provides proof of what was agreed to by both parties - Helps to prevent future misunderstandings or disputes by making the contract agreement clear from the beginning - Gives both parties security and peace of mind by having the terms of the agreement down on paper knowing that the terms cannot change |  |
| --- | --- | --- |

Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Clauses |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Acceptances | 1 - F | A | Provide specific reasons that allow the contract period to be adjusted |  |
|  | 2 | Cost adjustments | 2 - E | B | A provision for which remedies can be sought if breached |  |
|  | 3 | Extensions of time | 3 - A | C | Specifically outlines the tasks to be completed as part of the construction work |  |
|  | 4 | Payments | 4 - D | D | Outlines the requirements for deposits |  |
|  | 5 | Scope of work | 5 - C | E | Address the risk of rise/fall of expenses |  |
|  | 6 | Term | 6 - B | F | Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding |  |

Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Contract estimate |  |
|  |  | Contract request |  |
|  |  | Preliminary agreement |  |

True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

| Answer | Contract name | Description |  |
| --- | --- | --- | --- |
|  | New Home Construction Contract | This contract is used for the construction of an entire home. |  |
|  | Natural Disaster Contract | Designed to help you organise repairs to a home, duplex or home unit after a natural disaster not exceeding $3300 |  |
|  | Commercial Building Contract | A cost-plus contract for use on commercial building projects, where a lump sum price cannot be established, however a fair and reasonable estimate is given. |  |
|  | Commercial Minor Works Contract | A lump sum contract for minor commercial work up to the value of $100,000 |  |

Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

| Answer | Commercial Minor Works Contract |  |
| --- | --- | --- |

Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

| Answer | Level 2 – Renovation, Extension and Repair contracts For renovations, extensions and routine repairs on existing homes for contracts $20,000 and over |  |
| --- | --- | --- |

Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

| Answer | Topics | Definition |  |
| --- | --- | --- | --- |
|  | Builder’s Licence | You should only deal with a QBCC-licensed contractor. If you engage an unlicensed contractor, your building work may not be covered under the Queensland Home Warranty Scheme. Before committing, check the contractor’s licence and history via the Online Licence Search on the QBCC website or by calling the QBCC. |  |
|  | Contract price | The contract price must be stated on the first page of the contract schedule. For contracts priced at $20,000 or more, the contract must also contain a warning about any provisions that may alter the contract price and if the price includes any allowances (items or services for which the price is not fixed at the time the contract is signed), the allowances must be stated in the contract schedule. Allowances should be kept to a minimum as the final cost often exceeds the estimate in the contract. |  |
|  | Building approvals and inspections | Building inspections and approvals are the responsibility of a building certifier. Mandatory building inspections may be required at certain stages of construction. The contractor must give you copies of any certificates of inspection as soon as practicable after they receive them from the certifier. You can check the certifier’s licence via QBCC’s Online Licence Search. |  |
|  | Practical completion and handover | You are not required to pay the final contract payment until all of the contracted work has been completed in accordance with the contract including any plans and specifications, all legal requirements, and either without any defects or omissions, or with only minor defects or minor omissions that will not unreasonably affect occupation. If you believe there are any minor defects or minor omissions, the contractor must give you a ‘defects document’ (listing agreed and non-agreed matters). This document should be compiled by you and the contractor during a handover inspection. Check your contract to see if it imposes any extra requirements on the contractor for practical completion. |  |
|  | Implied warranties | Under sections 19 to 26 of Schedule IB of the Act, a range of warranties are deemed to be part of all regulated domestic building contracts even if not stated in the contract. The warranty period is six years for structural defects; one year for all other defects. |  |

- Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Engineer specifications |  |
|  |  | Plans, drawings and specifications |  |
|  |  | Prime Cost Items Schedule |  |
|  |  | Processes for applying for extensions of time |  |
|  |  | Product catalogues |  |
|  |  | Project timelines and schedules |  |
|  |  | Provisional Sums Schedule |  |
|  |  | Rise and fall calculations |  |
|  |  | Site conditions report |  |
|  |  | Soil and sedimentation report |  |

What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

| Answer | A prime cost is limited to the cost of supplying the relevant item, and does not include the cost of any work that relates to it (such as its installation). In contrast, provisional sums include allowances for both the supply item and all related work to be performed by the contractor. An example of something on a prime cost item schedule is: Detailed description of Prime Cost item; Contractor’s best estimate price, and breakdown of estimate; PLUS, Contractor’s margin ($ or % amount) 10% if nothing is stated; Total for prime cost item (incl. margin & GST). Number of items or quantity of materials; Cost per unit (excl GST). Supply of floor tiles for living area; 100m2; $40/m2; 100m2x$40= $4000+10% margin = $4400 (excl. GST); $4400 + 10% GST =$4840. An example of something on an allowance for provisional sums is: Description of contracted service covered by the Provisional Sum; Contractor’s best estimate of cost of providing the contracted service excl. GST. Include the estimated quantity and unit cost of materials (if any), estimated labour cost, and any other costs (e.g. equipment hire).; PLUS, Contractor’s margin ($ or % amount) - 10% if nothing is stated; Total for Provisional Sum (incl. margin & GST). Removal of asbestos; 30m2 @ $60/m2 excl. GST = $1,800 (incl. preparation, removal & disposal); $1,800 + 10% margin = $1,980 (excl. GST); $1,980 + 10% GST = $2,178. |  |
| --- | --- | --- |

Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

| Answer | Cost adjustments apply to long-term costs and some specific costs (e.g. labour and materials, currency exchange rates for overseas-purchased goods, duties, taxes, shipping). |  |
| --- | --- | --- |

True or False (Tick your response): Variations can be requested by both the client and the builder.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

| Answer | When a customer asks for a time extension or ‘variation’ to the contract it requires: - A variation in writing - You to issue an ‘extension of time’ form – essentially asking the client to grant you an extension of the contract period to allow for delays caused by the variations - The specific reasons for an extension of time are set out in the general conditions of the building contract and include reasons such as: inclement weather and delays caused by the owner, such as changes in the scope of works - You should be familiar with the General contract conditions to you know what time extensions you are entitled to over the contract period |  |
| --- | --- | --- |

Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

| Answer | Fair Trading Act 1989 4A Application of Act (1) This Act applies to and in relation to— (a) persons carrying on business within Queensland; or (b) bodies corporate incorporated or registered under the law of Queensland; or (c) persons ordinarily resident in Queensland; or (d) persons otherwise connected with Queensland. (2) Subject to subsection (1), this Act extends to conduct, and other acts, matters and things, occurring or existing outside or partly outside Queensland (whether within or outside Australia). |  |
| --- | --- | --- |

Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

| Answer | At the time of entering into the contract, the credit provider must provide a contract to the consumer. During the term of the contract, the credit provider is required to provide the consumer with periodical statements of account. |  |
| --- | --- | --- |

What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

| Answer | You may withdraw from the contract within five business days of receiving copies of the signed contract (including any plans and specifications) and this guide. However, there are costs for home owners in withdrawing (generally $100 plus any out-of-pocket expenses reasonably incurred by the contractor up to the time of withdrawal). You must also advise the contractor in writing. |  |
| --- | --- | --- |

What are the maximum deposits recommended for a residential building project?

| Answer | The maximum deposit allowed is: 1. 10% where the total contract price is under 2. $20,000 5% where the price is $20,000 or more 3. 20% for a contract of any price where the value of the work to be performed off-site is more than 50% of the total contract price. |  |
| --- | --- | --- |

Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

| Answer | Progress payment stages: - Base stage (excl. 5% deposit) – 15% - Frame stage – 20% - Enclosed stage – 25% - Fixing stage – 20% - Practical completion stage – 15% |  |
| --- | --- | --- |

- You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

| Answer | No, the deposit should not be accepted as the deposit must not exceed 5% of the contract price if the contract price is higher than $20,000. |  |
| --- | --- | --- |

- Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

| Answer | Breach | Explanation |  |
| --- | --- | --- | --- |
|  | Breach of condition under contract | If a condition of the contract is breached the contract becomes null and void. |  |
|  | Breach of warranty under contract | A breach of a warranty will not of itself entitle a party to terminate or, more properly, accept repudiation of the contract and recover damages. It will only entitle the innocent party to recover damages. ... However, the innocent party will be entitled to damages to compensate it for the breach. |  |

What does repudiation of a contract mean?

| Answer | Repudiation occurs when a party to a contract is unwilling to perform their contractual obligations – through acknowledgement or their actions are totally inconsistent with their obligations under the contract. |  |
| --- | --- | --- |

True or False (Tick your response): In the event of repudiation, the injured party has two options:

- Continue with the contract

- Accept the repudiation and move to terminate the contract

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

| Answer | The injured party should act with caution because if the situation is not deemed to be a repudiation, by acting the terminate the contract the injured party may themselves be repudiating the contract and could be liable to pay damages. |  |
| --- | --- | --- |

What does ‘abandonment of contract’ mean?

| Answer | Abandonment of contract is when both parties have conducted themselves in such a way that the original construct is no longer valid. |  |
| --- | --- | --- |

A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

| Answer | Cause - Where one party fails to meet the terms of the contract (e.g. due to poor performance) the aggrieved party’s action may be deemed a termination for cause. Convenience - Where a party is unwilling to perform under the agreement (i.e. for reasons other than poor performance), this may be deemed a termination of convenience. |  |
| --- | --- | --- |

Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

| Answer |  | Yes |  |  |
| --- | --- | --- | --- | --- |
|  |  | No |  |  |

If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

| Answer | A sender can send a notice to complete after the completion date, provided they were ready, willing and able to complete their side of the contract. Therefore, the sender must be in a position to carry out anything they both agreed to under the contract. |  |
| --- | --- | --- |

True or False (Tick your response): Where the notice given (as per Q39. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

| Answer | Final payment is made at practical completion, this is when: - all contracted work is completed in accordance with all relevant laws, legal requirements and with the plans and specifications - any minor defects or minor omissions are recorded on a signed defects document - the house is reasonably suitable for habitation (where the contract requires this). Some contracts (including the New Home Construction Contract) require the contractor to provide all certificates of inspection (including the 'final' certificate) before they receive final payment. A contractor must repair any defects noticed at handover, or within 12 months of when the work is finished. You must notify the contractor of any such defects within 12 months of when you notice them. |  |
| --- | --- | --- |

Explain the concept ‘conditions for completion at the cost of the contractor’.

| Answer | The amount of money (damages) required to complete performance (finish the job) when a contract has been breached by the failure to perform. For example: When a general contractor breaches by not completing a house, the cost of completion is the actual cost of bringing in a new builder to finish what is left to do. |  |
| --- | --- | --- |

Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

| Answer | A warranty against defects must concisely state: - what the person who gives the warranty must do so that the warranty may be honoured; and - what the consumer must do to entitle the consumer to claim the warranty; |  |
| --- | --- | --- |

Name one (1) person you should consult if you are considering ousting a contractor from a building site.

| Answer | You should consult your lawyer to understand your rights and obligations about ousting a contractor from a building site. |  |
| --- | --- | --- |

What document should you refer to if you are considering ousting a contractor from a building site?

| Answer | You should refer to your contract if you are considering ousting a contractor from a building site. |  |
| --- | --- | --- |

How should you handle a customer complaint?

| Answer | When handling a customer complaint, you should: - Deal with the complaint immediately - Stay calm - Identify the problem - Decide what can be done - Arrange a second opinion to confirm your view - Keep records - Fix the problem |  |
| --- | --- | --- |

How do you reduce the risk of dispute?

| Answer | Some way to reduce the risk of dispute are: - Confirm details in writing - Read contracts before signing them - Develop good communication and relationships - Be organised - Know your legal obligations |  |
| --- | --- | --- |

What is the process for dispute resolution?

| Answer | The process for dispute resolution should be: - Seek legal advice to understand your rights and obligations - Make a complaint to the Queensland Building and Construction Commission (QBCC) - Should you dispute the decision made by QBCC you should then contact Queensland Civil and Administrative Tribunal (QCAT) |  |
| --- | --- | --- |

- During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

| Answer | Good evening Samantha, After I received your email concerning the bath in the bathroom, I reviewed the white goods and chattels list selected by you, the specifications, materials order and the receivable orders sheet. These all seem to indicate that the correct bath was installed. If you are unhappy with it, we can definitely look at getting it changed, however this would be a variation that would be carried out at your expense. Please let me know what you decide or if there is anything I can do to help you further with this matter. Thanks Matt Cumiskey |  |
| --- | --- | --- |

Where would you find any possible penalties associated with a build?

| Answer | Unlawful building work resulting in possible penalties is detailed in Section 42 of the QBCC Act (1991). |  |
| --- | --- | --- |

Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

| Answer | Building certifiers inspect and approve building work and make sure it complies with the relevant aspects of approved building plans and appropriate building standards. They can work for local government, or in a private practice as a private certifier. In most cases, you are responsible for engaging the private certifier on your client’s behalf. However, homeowners can directly appoint a private certifier. Standard process is for a builder to engage a licensed certifier to complete an inspection and provide a compliance certificate. The certificate should be stored by the builder with other documentation until the handover process takes place, at which the certificate and other documentation can be provided to the owner. |  |
| --- | --- | --- |

- Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:

  - The land has been secured and paid for by the Clients.

  - Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.

  - Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured.

  - Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list.

  - The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.

  - The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.

  - Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build.

  - The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.

  - The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.

  - The construction period excluding inclement weather and possible delays is 23 weeks

  - Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).

  - Prime costs are required for the solar hot water system and ducted air conditioning

  - Provide fictitious details for all other sections of the contract.

  - 18 solar panels are to be installed on the roof

| Answer |  |  |
| --- | --- | --- |

CPCCBC4003A Select and prepare a construction contract

CPCCBC4016A Administer a construction contract

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | Matthew Cumiskey |
| --- | --- |
| Participant signature |  |
| Date | 10/02/2020 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to apply contract law to residential and/or commercial construction sales processes. The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - Copy of a contract issued to sub-contractor for your project with relevant AS code on the front - Proof of consultation with sub-contractor regarding contract and contract terms, inclusions and omissions (emails) - Copy of HSE minimum requirements sent as contract condition - Construction contracts that have been developed, signed off, or contributed to by the candidate - Proof of correspondence with client regarding construction contract. Redact sensitive information as required. The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment. |  |  |  |
| Resources required: Two (2) pre-contract agreements; two (2) sales contracts (e.g. QBCC contracts), telephone, facsimile machine, computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: | Matt Cumiskey |  |  |
| Name of observer: |  |  |  |
| Role of observer (Confirm suitability to sign) |  |  |  |
| Email address of observer |  |  |  |
| Signature of observer: |  |  |  |
| Date: | Click here to enter a date. |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Explain to the client: - Essential terms and elements of a valid contract - Types and purposes of agreements employed with the industry (including sales contracts and pre-contract agreements) - The range of documents that collectively make up a contract (including construction schedules, reports, specifications) - The importance of the contract to sales process - Implications of legislation, regulations and codes of practice (including Australian Consumer Law) |  |  |  |
| - Discuss and agree upon clauses of a pre-contract agreement, including payment or deposit. |  |  |  |
| - Ensure the pre-contract agreement is signed and processed according to organisational requirements. |  |  |  |
| - Select appropriate contract and seek expert advice in the preparation of the contract, considering: - Contract rise and fall amounts - Schedule of progress payments - Processes for applying of extensions of time |  |  |  |
| - Break down contract clauses/terms/conditions with the client, including: - Rights, liabilities and potential penalties of parties under the contract - Definitions of building work, common contract terms and procedures, considering – - Practical completion and issuing a final certificate - Defects liability and completion at the cost of the contractor - Effect of ousting the contractor from the building or site - Cooling off periods - Provisional sum and prime cost allowances - Measures to be taken in the event of an anomaly in the rendering of the contract, considering – - Variations - Circumstances that bring about a breach and termination of contract, considering – - Unreasonable/vexatious notice - Abandonment of a contract - Methods for resolving contractual disputes |  |  |  |
| - Effectively communicated with clients, subcontractors, colleagues and external parties using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication - Using technology (including telephone, facsimile, email) - In writing (including drafting responses to queries about contracts) |  |  |  |
| The participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments