Apply project risk management techniques

Templates

Contents

Stakeholder Analysis Template	2

Communications Plan Template	3

Communication Requirements Analysis Worksheet	4

Contract Change Control System Checklist and Worksheet	5

Contract Performance Report Template	6

Generic Change Request Template	7

Lessons Learned Documentation Template	8

Project Change Control System Development Checklist and Worksheet	9

Project Change Request Tracking Report	10

Project Status Review Meeting Guideline Sheet	11

Project Risk Prioritisation Worksheet/Template	12

Project Risk Categorisation Worksheet	14

Project Risk Review Matrix	15

Project Change Request Template	16

Rating Impacts for a Risk	17

Risk Brainstorming Session Worksheet	18

Risk Identification – SWOT Analysis	19

Risk Management Plan Template	21

Risk Response Plan Template	23

Schedule Change Control System Development Checklist and Worksheet	24

Schedule Change Request Template	25

Workaround Planning Worksheet	26

# Stakeholder Analysis Template

| # Project Name: Single-Storey Residential Dwelling – Springfield, Queensland |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: Abbie H |  |  |  |  |
| # Date: 8/8/25 |  |  |  |  |
| Project Stakeholder | Specific Information Needs | Best Source of Information Needed | Planned Method of Delivery | Timing Considerations |
| Project Manager | Progress updates and risk reports | Risk register and progress reports | Meetings and emails | Weekly |
| Customer #1 | Milestones achieved, quality standards | Progress reports | Written reports and meetings | Monthly or as requested |
| Customer #2 | Design and construction updates | Progress reports and design documents | Meetings and emails | Monthly |
| Customer #3 | Compliance with agreed specifications | Compliance and progress updates | Written reports | As required |
| Performing Organisation | Budget adherence and project performance | Financial and progress documentation | Internal reports | Monthly |
| Project Team Members | Task responsibilities and deadlines | Project plans and schedules | Emails and meetings | Weekly |
| Sponsor | Overall progress and financial updates | Financial and project status reports | Presentations and written updates | Quarterly |
| Senior Executive | High-level project performance overview | Executive summaries | Presentations and emails | Quarterly or as required |
| Other Internal Stakeholders | Operational impact and resource needs | Internal project updates | Internal meetings and reports | As required |
| Other External Stakeholders | Compliance with local regulations | Compliance and progress documentation | Written reports | As required |

# Communications Plan Template

| # Project Name: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |  |
| # Date: |  |  |  |  |  |  |
| Key Stakeholders (Distribution Schedule) | Stakeholder Issues | Key Messages to Communicate | Communication Methods to be Used (written, one-on-one, electronic, meetings, etc.) | Description of Specific Communications (content, format, level of detail, etc.) | Timing Issues (see also Bar Chart, Project Schedule) | Other |
| Client |  | Milestone achievements and quality | Written reports, meetings | High-level progress report and photos | Monthly |  |
| Senior Management | Budget tracking and resource allocation | High-level project status | Presentations, executive summaries | Financial updates, overall project performance summary | Quarterly or as required |  |
| Sponsor | Financial updates and project progress | Budget adherence, milestone achievements | Presentations, written updates | Detailed financial reports and milestone updates | Quarterly |  |
| Project team members | Task allocation and risk updates | Task responsibilities and deadlines | Written, meetings, emails | Status reports, risk logs, and action items | Weekly updates |  |
| Employees | Safety and work updates | Project safety protocols and schedules | Meetings, emails | Safety briefings and role-specific updates | Weekly |  |
| Subcontractors | Task schedules and safety requirements | Progress timelines and safety standards | Written, one-on-one | Task checklists and safety briefings | Daily |  |
| Suppliers | Delivery schedules and material specs | Delivery schedules and material specs | Emails and phone calls | Delivery schedules and material requirements | As required |  |
| Unions | Workplace safety and compliance | Compliance with safety standards | Written reports | Compliance updates and safety adherence reports | As required |  |
| Government Agencies | Compliance with building and zoning regulations | Adherence to regulations | Written reports | Compliance documentation and required permits | As required |  |
| News Media | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |  |
| Community | Impact of construction activities | Noise and traffic management updates | Noticeboards, community meetings | Notices regarding construction schedules, noise, and safety | As required |  |
| Other – Local Council | Compliance with local regulations | Adherence to building codes | Written, meetings | Compliance documentation | As required |  |

# Communication Requirements Analysis Worksheet

| # Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| General Area of Communication Need | Information Needed, and for Whom? | Optimum Information Format(s) | How is this communication essential to success of project? | Decision to implement Yes/No |
| Project Organisation Relationships | Roles, responsibilities, reporting lines for project team (builders, certifiers, designers) | Org charts, contact lists, project briefs | Ensures clarity in task ownership and accountability | Yes |
| Stakeholder Responsibility Relationships | Expectations, deliverables, and timelines for stakeholders (owners, builders, certifiers) | Stakeholder matrix, Gantt charts, meeting minutes | Aligns stakeholder expectations and reduces conflict | Yes |
| Sponsor Relationships | Funding sources, budget approvals, sponsor expectations | Budget reports, sponsor updates, formal agreements | Maintains financial control and sponsor confidence | Yes |
| Senior Executive Relationships | Oversight, strategic alignment, risk management | Executive summaries, dashboards, risk registers | Ensures project aligns with broader organisational goals | Yes |
| Disciplines, Departments, Specialties, etc. | Coordination between trades (plumbing, electrical, structural) and consultants | Technical drawings, scopes of work, coordination meetings | Prevents clashes and ensures compliance with NCC Class 1a standards | Yes |
| Logistics of Project Staffing by Location | Site access, staff schedules, safety protocols | Site maps, rosters, WHS documentation | Ensures safe and efficient site operations | Yes |
| External: Media | Project milestones, community impact, promotional updates | Press releases, social media posts, newsletters | Builds public trust and transparency | No (unless public interest is high) |
| External: Community | Noise, traffic, environmental impact, construction schedule | Community notices, signage, council updates | Maintains good neighbour relations and avoids complaints | Yes |
| External: Government, Regulatory Agencies | Compliance with Building Regulation 2021, NCC, QDC, QBCC licensing | Formal submissions, inspection reports, certificates | Ensures legal compliance and avoids penalties | Yes |
| Other | Insurance, sustainability, bushfire/flood zone assessments | Policy documents, certificates, environmental reports | Protects project viability and ensures resilience | Yes |

# Contract Change Control System Checklist and Worksheet

| # Project Name: |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| # Date: |  |  |
| Determine those responsible for approving or rejecting proposed contract changes: Be sure to provide for appropriate review of all changes. Commercial Manager/ Project Director – Primary approver for scope and budget changes Site Supervisor – Approves minor site-related changes Client Representative – Required for changes affecting design or cost Legal/Contracts Team – Reviews compliance and contractual implications |  |  |
| Define any types of changes qualifying for automatic approval without review: Minor material substitutions of equal or better quality Adjustments to delivery dates within a 3-day window Administrative corrections (e.g., typos, formatting) |  |  |
| Define steps by which contracts may be changed, including: |  |  |
| Paperwork Change Request Form submitted by contractor or consultant Supporting documentation (drawings, cost estimates, impact analysis) |  |  |
| Tracking systems Logged in project management software (e.g., Procore or Buildertrend) Unique change ID assigned for traceability |  |  |
| Dispute resolution procedures Initial review by Contracts Administrator Escalation to Project Manager and Legal if unresolved Mediation clause invoked if necessary |  |  |
| Approval levels required <$5,000: Commercial Manager $5,000–$20,000: Project Director $20,000 or design-impacting: Client Representative and Legal |  |  |
| Describe how contract changes will be integrated with the project's integrated change control system: All approved changes are updated in the master contract and project schedule Budget adjustments reflected in financial tracking tools Notifications sent to all affected stakeholders Change log maintained for audit and review |  |  |
| Additional Remarks: All changes must comply with Queensland Building and Construction Commission (QBCC) guidelines Changes impacting compliance (e.g., NCC, QDC) require regulatory review |  |  |
| Submitted | Name/Title: Abbie Heaslip, Assistant Contracts Administrator | Date: 8/8/25 |
| Approval | Name/Title: Commercial Manager | Date: 8/8/25 |

# Contract Performance Report Template

| # Project Name: |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| # Date: |  |  |
| # Status of Vendor Performance, relative to project/contract objectives: |  |  |
| # Scope (On Scope? If not, how serious) On scope. All deliverables are aligned with the original contract. Minor adjustments (e.g., material substitutions) have been approved and documented. |  |  |
| # Schedule (On schedule? Ahead or behind by how much, etc.) Slightly behind schedule by approximately 4 working days due to weather delays and late delivery of roofing materials. Recovery plan in place with adjusted subcontractor hours. |  |  |
| # Cost (On budget? Under or over by how much, etc.) On budget. Current expenditure is within 2% of projected costs. Contingency fund remains untouched. |  |  |
| # Quality Meets quality standards. All inspections passed to date (foundation, framing, plumbing rough-in). No defects reported. Materials used meet or exceed specifications. |  |  |
| # Progress Report (What is completed, what is in process, key changes made, etc.): Completed: Site prep, slab pour, framing, roofing structure In Process: Electrical rough-in, plumbing, insulation Key Changes: Switched to Colorbond roofing due to supplier issue (approved change), minor layout adjustment in ensuite for accessibility |  |  |
| Forecasting (Estimate of future project status and progress): Project expected to be back on track within 2 weeks No major risks identified Next milestones: Lock-up stage by end of August, internal fit-out by mid-September |  |  |
| Other Issues or Comments: Community feedback positive; no complaints received Awaiting final approval from council on driveway crossover Vendor communication has been responsive and proactive |  |  |
| Submitted | Name/Title: Abbie Heaslip, Assistant Contracts Administrator | Date: 8/8/25 |
| Approved | Name/Title: Site Manager | Date: 8/8/25 |

# Generic Change Request Template

| Project Name: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |
| Date: |  |  |  |  |  |
| Person(s) Requesting Change: Site Supervisor – Springfield Project |  |  |  |  |  |
| Change Number: CC-005 |  |  |  |  |  |
| Type of Change Requested: |  |  |  |  |  |
|  | Project Scope Change |  | Project Budget Change |  | Project Schedule Change |

|  | Project Procurement/Contract Change |  | Other (specify) |
| --- | --- | --- | --- |
| # Detailed Description of Change: Request to modify the ensuite bathroom layout to improve accessibility. This involves repositioning the shower and widening the doorway to comply with AS 1428.1 standards for mobility access. |  |  |  |
| # Reason for Change Requested: # Client has requested improved accessibility for a family member with mobility challenges. The change will enhance usability without affecting structural integrity. |  |  |  |

| # Effect on Project Cost: |  |  |
| --- | --- | --- |
| Projected Cost Overrun of approximately: 3.5 % |  |  |
| Estimated Cost Reduction of approximately: % |  |  |
| # Effect on Schedule: |  |  |
| Planned Project Completion Date: 30/09/25 |  |  |
| New Project Completion Date: 4/10/25 |  |  |
| Additional Remarks: Change approved by client Updated drawings submitted to certifier No impact on compliance or council approvals |  |  |
| Approval | Project Manager: | Date: 8/8/25 |
| Approval | (Other): Client | Date: 8/8/25 |

# Lessons Learned Documentation Template

| # Project Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Number: LL-003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: Supplier Lead Time Risk Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: Assistant Contracts Administrator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group:* |  |  |  | Initiating |  | Planning |  | Executing |  |  |  | Controlling |  |  |  |  |  | Closing |  |  |
| Specific Project Management Process Being Used: Procurement and Schedule Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific Practice, Tool or Technique Being Used: Vendor performance tracking and contingency planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the action undertaken? Roofing supplier was changed mid-project due to unavailability of originally specified material. A contingency supplier was engaged after a delay. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? Project experienced a 4-day delay and required a scope change approval for material substitution. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result: No delay and seamless transition to alternate supplier with pre-approved materials. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? Early identification of high-risk suppliers and pre-approval of alternate materials during planning phase. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific Lesson Learned? Always assess supplier reliability and lead times during procurement planning. Include backup suppliers and pre-approved alternatives in contract documentation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? Monitor supplier performance and delivery history. Flag any materials with long lead times or limited availability. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? Conduct supplier risk assessments and maintain a list of approved alternates. Communicate potential risks to stakeholders early. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? Apply to upcoming procurement for internal fit-out materials and landscaping supplies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used in a future project? Incorporate into procurement planning templates and vendor evaluation criteria for all residential builds. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learned: (check one) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Executive(s) |  |  | Project Manager(s) |  |  |  | Project Team(s) |  |  |  |  |  |  | All Staff |  |  |  |  |
|  |  |  | Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learned be disseminated? (check all that apply) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | e-mail |  |  | Intranet/Web site |  |  |  | Tip Sheet/FAQ |  |  |  |  |  |  | Library |  |  |  |  |
|  |  |  | Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Have you attached reference(s), example(s) and/or additional material(s)? |  |  |  |  |  |  |  |  |  |  |  |  |  | yes |  |  |  |  | no |
| Name(s) of attachment(s): - Supplier Delay Report – Roofing (Hypothetically would attach if it was not simulation project) - Approved Material Substitution Form (Hypothetically would attach if it was not simulation project) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Project Change Control System Development Checklist and Worksheet

# Project Name:

Prepared by:

# Date:

Determine those responsible for approving or rejecting proposed project changes: Be sure to provide for appropriate review of all changes. # Commercial Manager – Reviews and approves changes related to cost, contracts, and procurement # Project Director – Final authority on all project changes, especially those affecting scope, schedule, or client deliverables # Client Representative – Required for changes impacting design or budget # Site Supervisor – Can approve minor site-related adjustments # Contracts Administrator – Ensures documentation and compliance

Define Roles and Responsibilities of approving person or body: Commercial Manager: Evaluates financial and contractual implications of proposed changes Project Director: Oversees strategic alignment and approves major changes Client Representative: Approves changes that affect client expectations or budget Contracts Administrator: Manages documentation, tracking, and compliance Site Supervisor: Identifies and initiates minor change requests from site

Get key stakeholder agreement on roles and responsibilities (list stakeholders): Project Director Commercial Manager Client Representative Site Supervisor Contracts Administrator Subcontractors (as needed for technical input)

Define any types of changes qualifying for automatic approval without review: Administrative corrections (e.g., typos, formatting) Material substitutions of equal or better quality with no cost/schedule impact Minor schedule shifts (≤2 days) due to weather or site access

Define steps by which contracts may be changed, including:

Paperwork Submit Change Request Form with supporting documents (drawings, cost estimates, impact analysis) Reviewed and signed by relevant parties

Tracking Systems Logged in project management software (e.g., Procore or Buildertrend) Assigned unique change ID for traceability

Dispute Resolution procedures Escalation to Commercial Manager If unresolved, referred to Project Director and Legal Mediation clause invoked if necessary

Approval levels required <$5,000: Site Supervisor $5,000–$20,000: Commercial Manager $20,000 or design-impacting: Project Director and Client Representative

Describe how contract changes will be integrated with the project's integrated change control system: # All approved changes are updated in the master contract, project schedule, and budget # Change log maintained and reviewed weekly # Notifications sent to all affected stakeholders # Changes reflected in project documentation and communicated during team meetings

# Project Change Request Tracking Report

| Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| Project Manager: |  |  |  |  |
| Project Change Request Administrator: |  |  |  |  |
| Change Number | Change Name | Change Requestor | Status of Change | Comments |
| CC-001 | Ensuite Layout Adjustment | Site Supervisor | Approved | 1. Improved accessibility layout approved by client. |
|  |  |  |  | 2. |
| CC-002 | Roofing Material Substitution | Site Supervisor | Approved | 1. Switched to Colorbond due to supplier delay. |
|  |  |  |  | 2. |
| CC-003 | Driveway Crossover Revision | Client Representative | Pending | 1. Awaiting council approval for revised location. |
|  |  |  |  | 2. |
| CC-004 | Additional Power Points | Electrician | Approved | 1. Client requested extra outlets in kitchen. |
|  |  |  |  | 2. |
| CC-005 | Landscape Design Update | Client | Under Review | 1. Client submitted new preferences for backyard layout. |
|  |  |  |  | 2. |

# Project Status Review Meeting Guideline Sheet

| # Project Name: |  |  |  |
| --- | --- | --- | --- |
| Prepared by: |  |  |  |
| # Date: |  |  |  |
| # Meeting Participants: Site Supervisor, Client Representative, Contracts Administrator |  |  |  |
| # Date of Meeting: 12 August 2025 |  |  |  |
| # Status of Project Work to Date, Including Progress Reported This Period: |  |  |  |
| Site preparation, slab pour, framing, and roofing structure completed Electrical and plumbing rough-in underway Minor delay due to weather and roofing material substitution Budget remains within 2% of forecast No quality issues reported |  |  |  |
| # Special Problems or Issues to be Addressed: |  |  |  |
| Issue: |  | Who Will Address: |  |
| Driveway crossover approval delay |  | Client Representative |  |
| Landscape design revision |  | Contracts Administrator |  |
| Schedule recovery plan |  | Site Supervisor |  |
| Supplier lead time risk |  | Procurement Officer |  |
| # Plans For Next Period: Complete electrical and plumbing rough-in Begin insulation and internal wall lining Submit final driveway plans to council Confirm landscape design and irrigation specs |  |  |  |
| # Other Notes and Concerns: Community feedback remains positive No safety incidents reported Risk register to be updated with supplier performance notes |  |  |  |
| Status Report Forwarded to: |  |  |  |
| # Name: | # Title: Commercial Manager |  | # Date: 12/8/25 |
| # Name: | # Title: Project Director |  | # Date: 12/8/25 |
| # Name: | # Title: |  | # Date: |

# Project Risk Prioritisation Worksheet/Template

# Project Name:

Prepared by:

# Date:

### By Rank:

| Identified Risk | Low Risk (Check √) | Medium Risk (Check √) | High Risk (Check √) | Work Breakdown Structure Level |
| --- | --- | --- | --- | --- |
| Supplier delays |  |  |  | Procurement |
| Weather disruptions |  |  |  | Site Preparation & External Works |
| Regulatory approval delays |  |  |  | Compliance & Approvals |
| Material substitutions |  |  |  | Procurement |

### By Required Response:

| Identified Risk | Can Be Handled Later (specify planned response) | Requires Immediate Response! (specify planned actions and who is assigned responsibility) |
| --- | --- | --- |
| Material substitutions | Maintain list of pre-approved alternatives | Review and approve substitutions; Procurement Officer to action |
| Weather disruptions | Add buffer days to schedule; monitor forecast | Adjust daily work plans; Site Supervisor to manage |
| Regulatory approval delays | Monitor council timelines; follow up weekly | Expedite submission and request priority processing; Client Representative to follow up |

### By Area of Expected Impact:

| Area of Impact | Identified Risks affecting this area | Level of Risk: High, Medium, Low | Basis for High-Risk Assessments |
| --- | --- | --- | --- |
| Cost | Supplier delays, design changes, material costs | Medium | Supplier delays may require more expensive alternatives; client changes can increase scope and cost |
| Schedule | Weather disruptions, regulatory delays | High | Delays in approvals and weather can significantly impact the construction timeline |
| Functionality | Design changes, client requests | Medium | Late-stage design changes can affect usability and layout |
| Quality | Material substitutions, labour availability | Low | Substitutions are pre-approved; skilled labour is available but must be scheduled carefully |

# Project Risk Categorisation Worksheet

# Project Name:

Prepared by:

# Date:

NOTE: List all identified project risks within each category. Retain this information for reference throughout the risk management process:

Technical, quality, or performance risks—such as reliance on unproven or complex technology, unrealistic performance goals, changes to the technology used or to industry standards during the project. Material substitutions affecting performance or compliance Design changes impacting layout or accessibility Potential mismatch between specified and delivered materials Quality assurance delays due to inspection scheduling

Project-management risks—such as poor allocation of time and resources, inadequate quality of the project plan, poor use of project management disciplines. Inadequate contingency planning for supplier delays Poor coordination between subcontractors Incomplete documentation of client-requested changes Schedule compression leading to resource strain

Organisational risks—such as cost, time, and scope objectives that are internally inconsistent, lack of prioritisation of projects, inadequacy or interruption of funding, and resource conflicts with other projects in the organisation. Budget constraints limiting flexibility Scope creep from client requests Delays in internal approvals for change requests Competing priorities with other projects affecting resource allocation

External risks—such as shifting legal or regulatory environment, labour issues, changing owner priorities, country risk, and weather. Force majeure risks such as earthquakes, floods, and civil unrest generally require disaster recovery actions rather than risk management. Weather disruptions (rain affecting slab pour and framing) Regulatory delays (council approval for driveway crossover) Labour shortages due to regional demand Changes in local building codes or compliance requirements

# Project Risk Review Matrix

| # Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| # Meeting Date: |  |  |  |  |
| # Purpose of Meeting: |  |  |  |  |
| CHANGES IN RISK FACTORS: Notes |  |  |  |  |
| Identified Risk | Changes in Probability Of Occurrence | Changes in Priority | Changes in Ownership/ Responsibility | Changes in Needed Response |
| Supplier delays | Increased due to recent shortages | Elevated to High | Assigned to Procurement Officer | Immediate engagement of backup suppliers |
| Weather disruptions | Stable | Remains Medium | No change | Continue monitoring and adjust schedule daily |
| Regulatory approval delays | Increased due to council backlog | Elevated to Medium | Assigned to Client Representative | Expedite submissions and follow-up weekly |
| Material substitutions | Stable | Lowered to Low | No change | Maintain pre-approved list and monitor availability |
| Design changes requested by client | Increased due to ongoing feedback | Elevated to Medium | Assigned to Design Consultant | Schedule regular review meetings |
| Labour availability | Stable | Remains Low | No change | Maintain contact with labour hire agencies |
| # Additional Notes/Comments/Agreements/Next Steps: Risk register to be updated weekly Procurement team to prepare contingency plans for critical materials Council liaison to be prioritised for driveway and landscaping approvals WHS team to review safety protocols in light of upcoming fit-out phase |  |  |  |  |

# Project Change Request Template

| # Project Name: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |
| # Date: |  |  |  |  |  |
| # Changes are being made to the following: |  |  |  |  |  |
|  | Project Charter |  |  | Project Management Approach |  |
|  | Scope Statement |  |  | Work Breakdown Structure |  |
|  | Performance Measurement Baselines |  |  | Major Milestones and Target Dates |  |
|  | Key Staff |  |  | Risk Management Plan |  |
|  | Scope Management Plan |  |  | Schedule Management Plan |  |
|  | Cost Management Plan |  |  | Quality Management Plan |  |
|  | Staffing Management Plan |  |  | Communications Management Plan |  |
|  | Risk Response Plan |  |  | Procurement Management Plan |  |
| Changes to Supporting Detail? (explain): Yes – updated drawings and revised milestone schedule |  |  |  |  |  |
| Description of Changes being made: 1. Ensuite Layout Adjustment Risk Issues Prompting Changes: Accessibility concerns raised by client Corrective Action: Reposition shower and widen doorway to meet AS 1428.1 standards |  |  |  |  |  |
| 2. Roofing Material Substitution Risk Issues Prompting Changes: Supplier unable to deliver original material Corrective Action: Switch to Colorbond roofing, pre-approved by client |  |  |  |  |  |
| 3. Driveway Crossover Revision Risk Issues Prompting Changes: Council feedback on original location Corrective Action: Submit revised plans and await approval |  |  |  |  |  |
| Stakeholders being notified: Yes |  |  |  |  |  |
| Name/Title: Site Manager |  | Signature: SC |  |  | Date: 11/8/25 |
| Name/Title: |  | Signature: |  |  | Date: |

# Rating Impacts for a Risk

| # Project Name: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |
| # Date: |  |  |  |  |  |
| Evaluating Impact of a Risk on Major Project Objectives (ordinal scale or cardinal, non-linear scale) |  |  |  |  |  |
| Project Objective | Very Low .05 | Low .1 | Moderate .2 | High .4 | Very High .8 |
| Cost | Insignificant Cost Increase | <5% Cost Increase | 5–10% Cost Increase | 10–20% Cost Increase | >20% Cost Increase |
| Schedule | Insignificant Schedule Slippage | Schedule Slippage <5% | Overall Project Slippage 5–10% | Overall Project Slippage 10–20% | Overall Project Schedule Slips >20% |
| Scope | Scope Decrease Barely Noticeable | Minor Areas of Scope Are Affected | Major Areas of Scope Are Affected | Scope Reduction Unacceptable to the Client | Project End Item Is Effectively Useless |
| Quality | Quality Degradation Barely Noticeable | Only Very Demanding Applications Are Affected | Quality Reduction Requires Client Approval | Quality Reduction Unacceptable to the Client | Project End Item Is Effectively Unusable |

The impacts on project objectives can be assessed on a scale from Very Low to Very High or on a numerical scale.
The numerical (cardinal) scale shown here is non-linear, indicating that the organization wishes specifically
to avoid risks with high and very-high impact.

# Risk Brainstorming Session Worksheet

| # Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| # Session Facilitator: Commercial Manager |  |  |  |  |
| Title/Position: Contracts Administrator |  |  |  |  |
| # Participating Group: Site Supervisor, Procurement Officer, Client Representative |  |  |  |  |
| # Location: Springfield Site Office |  |  |  |  |
| Identified Risk | Probability of Occurrence | Potential Impact | Proposed Actions | Identified by Whom? |
| Supplier delays | High | High | Engage backup supplier | Procurement Officer |
| Weather disruptions | Medium | Medium | Add buffer days to schedule | Site Supervisor |
| Regulatory approval delays | Medium | High | Expedite submissions and follow-up weekly | Client Representative |
| Labour availability | Low | Medium | Maintain contact with labour hire agencies | Site Supervisor |
| Material substitutions | Medium | Low | Maintain pre-approved list | Procurement Officer |
| Design changes by client | Medium | Medium | Schedule regular review meetings | Client Representative |
| Safety incident on site | Low | Medium | Conduct refresher training | WHS Officer |

# Risk Identification – SWOT Analysis

# Project Name:

Prepared by:

# Date:

Project Manager:

SWOT Analysis Facilitator:

SWOT Analysis Participants:

SWOT Analysis Recorder:

Date of SWOT Analysis:

Project Strengths: (What potential strengths exist about the project, the project team, the sponsor, the organisation structure, the client, the project schedule, the project budget, the product of the project, etc.?) - Experienced construction and project team - Clear and well-defined project scope - Strong client engagement and communication - Use of familiar, proven construction methods - Good relationship with local council and suppliers

Project Weaknesses: (What potential weaknesses exist about the project, the project team, the sponsor, the organisation structure, the client, the project schedule, the project budget, the product of the project, etc.?) - Limited flexibility in budget for unexpected changes - Dependence on a small pool of suppliers - Tight schedule with minimal float - Incomplete pre-approval of alternate materials - Limited internal resources for rapid change implementation

Project Opportunities: (What potential opportunities exist in regard to achieving the project requirements, the product requirements, the project schedule, the project resources, the project quality, etc.?) - Positive community perception and goodwill - Potential for future residential projects in the area - Incorporation of sustainable and energy-efficient features - Upskilling of team through new compliance training - Streamlining procurement processes for future builds

Project Threats: (What potential threats exist in regard to achieving the project requirements, the product requirements, the project schedule, the project resources, the project quality, etc.?) - Weather-related delays (e.g., rain during slab or framing) - Delays in council approvals (e.g., driveway crossover) - Rising material costs or shortages - Labour availability fluctuations - Changes in building regulations or compliance standards

# Risk Management Plan Template

# Project Name:

Prepared by:

# Date:

# Description of Risk Management Methodology to be Used: A proactive and integrated approach using qualitative and quantitative analysis, regular reviews, and stakeholder engagement.

# Approaches Risk identification through workshops and site observations Prioritisation using impact/probability matrix Mitigation planning and contingency allocation

# Tools Risk register Risk matrix Buildertrend project management software

# Data Sources Historical project data Supplier performance records Weather forecasts Council approval timelines

# Roles and Responsibilities: Contracts Administrator: Maintains risk register Site Supervisor: Identifies and reports site risks Client Representative: Reviews risks affecting scope or budget Procurement Officer: Manages supplier-related risks

# Risk Management Action #1:

# Team Leader Contracts Administrator

# Team Members Site Supervisor, Procurement Officer

# Support Client Representative

# Risk Management Action #2:

# Team Leader Site Supervisor

# Team Members WHS Officer, Labour Coordinator

# Support Contracts Administrator

# [Add sections as needed]

# Budget: Contingency fund allocated: 5% of total project budget

# Timing: (Describe how risk management will relate to the project life cycle, and at what points it will be reviewed during the execution of the project) Risk management will be reviewed at each project milestone: Post-site prep Post-framing Pre-fit-out Final inspection

Risk Response Plan Template

# Project Name:

Prepared by:

# Date:

# Description of Risk Identified: Supplier delays affecting roofing materials

# Person(s) Responsible: Procurement Officer, Contracts Administrator

# Results from Risk Analysis: High probability, moderate impact on schedule and cost

# Agreed Responses (avoidance, transference, mitigation, acceptance):

Response #1 Mitigation – Engage backup supplier

Response #2 Acceptance – Allow 3-day buffer in schedule

Response #3 Transference – Include delay clause in supplier contract

# Residual Risk Level: Low

# Action Steps: Confirm alternate supplier availability Update schedule and notify stakeholders Amend contract terms

# Budget & Time for Response: Estimated cost increase: 3.5% Schedule impact: 4 days

# Contingency/Fallback Plans: Use pre-approved substitute materials if backup supplier unavailable

# Schedule Change Control System Development Checklist and Worksheet

# Project Name:

Prepared by:

# Date:

Determine those responsible for approving or rejecting proposed schedule changes: Be sure to provide for appropriate review of all changes. Site Supervisor (minor changes) Contracts Administrator (moderate changes) Client Representative (major changes)

Define categories of schedule changes qualifying for automatic approval without review: Weather-related delays ≤2 days Minor internal task rescheduling Non-critical path adjustments

Describe how schedule change control will be integrated with the integrated change control system: All changes logged in Buildertrend Reviewed weekly during status meetings Updates reflected in master schedule and communicated to stakeholders

Define steps by which schedule documents may be changed, including:

Paperwork Submit Schedule Change Request Form with justification

Tracking Systems Log change in Buildertrend with unique ID

Dispute Resolution Procedures Escalate to Contracts Administrator; mediation if unresolved

Approval Levels Required ≤2 days: Site Supervisor 3–7 days: Contracts Administrator 7 days or milestone impact: Client Representative

# Schedule Change Request Template

| # Project Name: |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| # Date: |  |  |
| # Person(s) Requesting Change: Site Supervisor |  |  |
| # Change Number: SCH-001 |  |  |
| # Detailed Description of Schedule Change: Delay in roofing installation due to supplier issue |  |  |
| # Reason for Schedule Change Requested: Original supplier unable to deliver on time; alternate supplier engaged |  |  |
| # Effect on Project Cost: |  |  |
| Projected Cost Overrun of approximately: 3.5 % |  |  |
| Estimated Cost Reduction of approximately: % |  |  |
| # Overall Effect on Schedule: |  |  |
| Planned Project Completion Date: 30/9/25 |  |  |
| New Project Completion Date: 4/10/25 |  |  |
| Additional Remarks: Change approved by client; updated schedule shared with all stakeholders |  |  |
| Approval | Project Manager: RW | Date: 11/8/25 |
| Approval | (Other): Client Rep | Date: 12/8/25 |

# Workaround Planning Worksheet

# Project Name:

Prepared by:

# Date:

# Description of Emerging Risk Identified: Delay in roofing material delivery

# Person(s) Responsible: Procurement Officer

# Results from Risk Analysis (if applicable): High probability, moderate impact

# Description of Plan to Respond (avoidance, transference, mitigation, acceptance): Mitigation – Engage alternate supplier and adjust schedule

# Description of Residual Risk Level: Low

# Action Steps: Confirm alternate supplier availability Update delivery schedule Notify site team and client

# Budget & Time for Response: Estimated cost increase: 3.5% Schedule impact: 4 days

# Contingency/Fallback Plans: Use pre-approved substitute materials if alternate supplier unavailable

Additional Notes: No impact on compliance or council approvals