CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Kayla Watson |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | Click here to enter a date. |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 45 |  | Yes | No |

Assessor Comments

Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | Scope of Works |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | Queensland Building and Construction Commission Act 1991 (Qld) - “Division 2 Payments relating to contracts” | Maximum Deposit Amounts – Level 1 regulated contract: 10% of contract price Level 2 regulated contract: 5% of contract price Level 1 or 2 regulated contract under which the value of the off-site work is more than 50% of the contract price, 20% of contract price. Maximum penalty – 100 penalty units |  |

Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Plumbing | Organises water supply, installs pipes and drains, installs roof and guttering, fits taps, hot water systems & toilets, ensure downpipes are fitted and sewer is connected |  |
|  | Electrician | Arranges electricity to be connected, places wiring for lighting and power cables, fixed switches, installs power points, wires electrical systems. |  |
|  | Bricklaying | Installs brick base (sub-base brickwork, dwarf walls and piers), installs walls |  |

Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

Explain the importance of determining subcontractor or plant availability for a job.

| Answer | It is important for creating an accurate project schedule and determining a timeframe for the job. It is also important to know availability to ensure the job process goes smoothly and no unexpected delays are caused. There is also no point in hiring a subbie or plant if they are not available in the time required to do the job. |  |
| --- | --- | --- |

Identify two (2) methods you might use to find a supplier for materials.

| Answer | Call around to different suppliers to check material availability Obtain quotes from different suppliers to compare pricing |  |
| --- | --- | --- |

Name two (2) factors that may impact on the availability of materials.

| Answer | Location of site Outsourcing |  |
| --- | --- | --- |

Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | AS/NZS 1680 |  |
| --- | --- | --- |

Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Scissor Lift | To access areas too high to reach with a ladder |  |
|  | Excavator | Digs trenches in-ground |  |

Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | Lifting Gear and Harnesses | To ensure safety when working at heights or in confined spaces |  |
|  | Jackhammers | To remove concrete in a small area. |  |

Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | Invoices Plant Risk Assessments |  |
| --- | --- | --- |

Name five (5) temporary services that need to be organised for a building site.

| Answer | Water Tapping to supply water to site Electrical pole or power box Temporary fencing Barricades Tiger strips |  |
| --- | --- | --- |

True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

Identify one (1) action you might take to facilitate site access for machinery.

| Answer | Excavation works |  |
| --- | --- | --- |

Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | Volume 2 Section 3 Part 3.9 | Volume 1 Section D Part D3 |  |

You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | Submit an Operational Works/Compliance Assessment SmartForm. Must submit a site-specific Construction Noise Management Plan, a copy of the letter that will be provided to premises/residents who would likely be affected. A Minimum of 10 working days is required for council to asses an application. |  |
| --- | --- | --- |

In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | Lane or Road Closure Permit | Traffic management plan for temporary lane/road closure, copy of development assessment approval, must complete online application for temporary road occupation form. Approval Body is BCC. |  |
|  | Footpath Closure Permit | Site plan sketch, approval plans, site photos, traffic management plan, and an application/notice to work on council property online form. Approval body is BCC. |  |

True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What document should be developed when purchasing supplies or construction materials?

| Answer | A Purchase Order |  |
| --- | --- | --- |

True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Who should be contacted if items are missing from a delivery?

| Answer | The Supplier |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | The Work Health and Safety Act 2011 Section 17-18 | A duty imposed on a person to ensure H&S requires the person to eliminate risks to H&S, so far as is reasonably practicable, and if not reasonably practicable, to minimise those risks so far as is reasonably practicable. |  |

Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | Work Health and Safety Regulation 2011 (Qld) |  |
| --- | --- | --- |

What document should be followed when disposing of hazardous materials?

| Answer | Safety Data Sheets (SDS) |  |
| --- | --- | --- |

An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10 |  |
| --- | --- | --- |

True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | It helps with minimising skilled labour from moving off-site when there is work to be done on nearby projects. This saves a great deal of time, as the subbies can work on the next job while waiting for another to complete. If the subbies move to another location it can be difficult to ensure their return for the next stage of the project. |  |
| --- | --- | --- |

Provide one (1) example to explain why construction operations must be sequenced.

| Answer | Sequencing is important as if you’re not aware of the activities that must be done on the project, you cannot successfully plan. You could also be doing activities that disadvantage the projects timeline or may become irrelevant in the future. You could be doing smaller jobs first and then realise that you’ve run out of time or money to complete the job. |  |
| --- | --- | --- |

Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 3 | Floor frame |  |
|  | 4 | Installing brick base |  |
|  | 6 | Roof trusses |  |
|  | 1 | Set out |  |
|  | 5 | Wall frames |  |

Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| - Task ID | - Task | - Preceding event | - Nodes |
| --- | --- | --- | --- |
| - A | - Make enquiries and order all materials required | - Start | - 1 |
| - B | - Wait for bricks, sand and cement to arrive | - A | - 2 |
| - C | - Clear vegetation from the site | - A | - 2 |
| - D | - Order concrete to be delivered | - A | - 2 |
| - E | - Dig the trench | - C | - 4 |
| - F | - Pour the footings | - E | - 5 |
| - G | - Footings curing time | - F | - 6 |
| - H | - Load the bricks on the site | - B | - 3 |
| - I | - Mix the mortar and lay the bricks | - H | - 7 |
| - J | - Clean rubbish from the area | - I | - 8 |
|  | - Finish | - J | - 9 |

G

F

Ha

E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | Microsoft Excel |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

Describe the critical path.

| Answer | The shorted completion time possible to complete a job. |  |
| --- | --- | --- |

True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | Weather Material Delivery Resources e.g. unreliable labour |  |
| --- | --- | --- |

Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

Why should you take photographs of site boundaries with neighbouring properties?

| Answer | Take photos to support your report on the condition of existing neighbouring properties as it will be helpful in the event of a dispute with a neighbour. |  |
| --- | --- | --- |

When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

When might a neighbouring property owner be required to refer to a condition report?

| Answer | Prior to commencing construction, to see the site status before work commences and to identify if any damage has occurred through the construction process. |  |
| --- | --- | --- |