Project  Plan

11 Balfour st

backyard makeover project

Nigel phillips

Wyreema small projects

Version 1 – 13-03 -2021

# Document Management

## Distribution list

The project plan must be distributed to all members of the project steering committee:

| Name | Position | Signature | Date |
| --- | --- | --- | --- |
| Nigel Phillips | Project manager -Wyreema small projects |  | 13-03-2021 |
| Mary Adamson | Owner / sponsor 11 balfour st |  | 13-03-2021 |
| Fred Butt | Director -Wyreema small projects |  | 13-03-2021 |

| Revision # | Change Description | Approval Date | Author |
| --- | --- | --- | --- |
| 1 | Initial release | 13-03-2021 | Nigel Phillips |
| 2 | Change request 1 – addional lighting and power outlet | 20-11-2021 | Nigel phillips |

## Version Control

| Project Name | 11 Balfour st Backyard makeover |
| --- | --- |
| Project # | 101 |
| Creation Date | 13-03-2021 |
| Sponsor/Client | Mary Adamson |
| Project Manager | Nigel Phillips |

## Project registration

# Executive Summary

## Rationale

By renovating and upgrading the back yard the owners will have a more usable space , currently the space is not used , also they want to add extra value to the house if they choose to sell.

## Business Background

Wyreema small projects (WSP)

Wyreema small projects (WSP) was established in 2019 so that our clients can realise small projects, with the expertise and support that you would normally find in large scale projects and business . WSP makes a commitment to our clients to deliver projects efficiently and with a high level of finish.

WSP directors have over 27 years’ experience in the building and construction industries

WSP is focused on supporting local business and clientele in the local Wyreema area. And to use local suppliers and subcontractors whenever possible

WSP works closely with a team of specialist contractors to achieve the best outcome their clients.

## KEY Objectives

The key objectives of this project are to:

- Remove all existing structures in the rear of the yard and

- Level and clear the site for construction of the outdoor entertainment area,

- Construct a usable structure for all family members to enjoy year round

- To increase value to the property

## Benefits

The benefits of this project include:

During the project:

- Employment for the local contractors and suppliers.

After completion of the project:

- The owner of the property has many other properties that he owns.  this has the potential for more work for WSP if the project goes to plan and the client is happy

- A more usable back yard that adds value to the property

## Organisational Impacts

The project will impact the business in the following ways:

As WSP is only a small team (2 persons) all our resources will be used during this project , this may prevent us in servicing other customers while we are doing this project

# Authorisation

## Recommendation:

The recommendation is this project plan is approved

## Approval

Approved	  Postponed 	 Cancelled 	 Review

## Sign off

The project plan only becomes valid once signed off by the following members of the project steering committee.

| Name | Position | Signature | Date |
| --- | --- | --- | --- |
| Nigel Phillips | Project manager -Wyreema small projects |  | 13-03-2021 |
| Mary Adamson | Owner / sponsor - 11 balfour st |  | 13-03-2021 |
| Fred Butt | Director -Wyreema small projects |  | 13-03-2021 |

Table of Contents

Document Management	2

Distribution list	2

Version Control	2

Project registration	2

Executive Summary	3

Rationale	3

Business Background	3

KEY Objectives	3

Benefits	3

Organisational Impacts	3

Authorisation	4

Recommendation:	4

Approval	4

Sign off	4

Project Information	7

1.Integration Management Plan	7

1.1 Methodology	7

1.2. Project Dependencies	7

1.3. Change Control	7

1.4. Auditing	8

1.5. Performance Reporting	8

1.6. Project Closure	8

2. Scope Management Plan	10

2.1. Deliverables	10

2.2. Inclusions	10

2.3. Exclusions	11

2.4. Handover	11

3. Time Management Plan	12

3.1. Schedule	12

3.2. Milestones	12

4. Cost Management Plan	14

4.1. Budget	14

4.2. Estimating methodology	14

4.3. Confidence level	14

4.4. Contingency	14

4.5. Source of Funds	15

4.6. Cash Flow	16

5. Quality Management Plan	17

5.1. Overview of Quality Requirements	17

5.2.  Council Regulations	17

5.3. Building Regulations	17

5.4. Operation of Equipment	17

5.5. Quality Assurance	17

5.6. Quality Control	17

6. Human Resource Management Plan	18

6.1. Stakeholders	18

6.2. Resource Capability	18

7. Communications Management Plan	19

7.1. Organisational Structure	19

7.2. Escalation	19

8. Risk Management Plan	20

8.1. Constraints	20

8.2. Assumptions	20

8.3. Potential Issues	20

8.4. Risk	20

9. Procurement Management Plan	20

9.1. Procurement Planning and Solicitation Planning	20

9.2. Contract Administration	20

9.3. Contract Close-out	20

Appendices	21

# Project Information

## 1.Integration Management Plan

### 1.1 Methodology

This project will be managed using PMBOK methodology, as will the related to the back yard project. The PMBOK methodology will ensure all aspects of project management are covered:

- Scope – What the project will deliver.

- Time – When the deliverables will be delivered.

- Cost – The project budget and cash flow.

- Quality – Ensuring all Council building and environmental conditions and regulations are met.

- Human Resources – The staff involved in the delivery and management of the project.

- Communications – Ensuring all stakeholders are informed of requirements, progress and issues.

- Risk – Ensuring the project risks are managed.

- Procurement – The project contracts with subcontractors and suppliers.

- Integration – Integrating the other project aspects.

### 1.2. Project Dependencies

This project is closely dependent on the owners husband (Steven Adamson) to be able to do a lot of the work during his days off

### 1.3. Change Control

The change control process will adhere to the following procedure. This procedure ensures appropriate stakeholders approve any changes, and all stakeholders are equally informed of changes to the initial project plan:

- All suggestions for changes to the project scope, time, cost, quality, human resources, communications, risk, procurement and integration will be sent to the project manager (WSP) who will populate the information into a change request. The change request template provided with this project plan must be used.

- The details going into the change request will be negotiated between the project manager (WSP) and the project sponsor (Mary Adamson)

- The project plan must include all change requests (template provided in Appendix 38), along with an up-to-date change register (Appendix 37).

- The changes in the project documentation must be clearly colour coded by highlighted text as below. All omitted text must be formatted with strikethrough to show it has been deleted and must be highlighted with the colour relevant to the version.

  - Change request 1 – Yellow highlighting.

  - Change request 2 – Green highlighting

  - Change request 3 – Blue highlighting

  - Change request 4 – Pink highlighting

- The change request and all modified documentation is examined at a face-to-face meeting by Mary Adamson (project sponsor), Nigel phillips (Project manager -WSP), Fred Butt (director WSP) and any other stakeholders directly impacted on the change request.

- The change request is signed by Steven Adamson (project sponsor), Nigel phillips (Project manager -WSP), Fred Butt (director WSP)

- The changes are communicated and implemented by the project manager (WSP).

### 1.4. Auditing

All work will be regularly audited by Fred butt (director WSP). In order to foresee any issues, the project manager of (WSP) will conduct regular quality audits on the work completed. It is expected Fred Butt (director WSP) will come to site during key milestones of the project. Internal audits will therefore be conducted before the completion of each stage of the project. The audit report template in Appendix 36 will be used for all internal and external auditing. The report template will need to complete. The outcomes of all internal and external audits are to be included in the status reports, and as appendices at the back of updates to the project plan. Details of the auditing process is in the quality plan.

### 1.5. Performance Reporting

To ensure the steering committee is kept informed of the progress of the project, reports need to be created by the project manager.

Performance reporting will occur immediately after a change request has been signed.

The report must use the standard template provided in Appendix 39 of the project plan.

The project plan must be updated with a new version released showing the status report, and the Gantt chart (and any other relevant documentation) updated to the date of the report in the project plan.

A lesson learnt evaluation session must also be conducted at the end of the project. To assist with the process, a lessons learnt documentation template has been provided in Appendix 41.

A final report must be completed at the end of the project when all stages have been complete. The template for this report is in Appendix 42.

All reports are to be signed off by the project sponsor before being distributed to all members of the project steering committee.

### 1.6. Project Closure

Upon completion of phase 2, the project closure needs to commence as per the following procedure:

- Payment of Remaining Invoices

All invoices that have not yet been paid to suppliers and contractors are settled prior to the preparation of project closure documentation.

- Project Closure Meeting Documentation

A project completion report must be completed, showing the results of the project, lessons learnt, and an audit report. The project plan is to be updated with an additional change control version incorporated. The project plan must include the following:

- The version control table must indicate this is the final version at completion.

- The project Gantt chart must indicate the project has been completed.

- Lessons learnt documentation must be included in the project plan.

- All issues in the issues register have either been closed or documented in the project closure report.

- A copy of the project completion report must be included.

- A final audit report on the project, and particularly its costs must be included.

The project archives checklist must be complete.

The formal acceptance and closure must be complete to be signed off at the project closure meeting.

- Final Project Meeting

All project steering committee members are to attend the final project meeting. Each member will be provided with a copy of the project documentation, which includes:

- Project completion report.

- Final version of the project plan.

- Project archives checklist.

- Formal acceptance and closure

The meeting commences with confirmation of the accuracy of the report and updated project plan.

All the lessons learnt documentation is then reviewed with lessons applicable to future projects noted by the committee.

The completion report, project plan and formal acceptance and closure must all be signed off by the signatories of the project steering committee. The template used for the formal acceptance and closure is provided in Appendix 43.

Each steering committee member takes their copy of the project completion documentation for their own archiving.

- Final Project Invoice

Having successfully delivered the final project documentation, WSP may raise an invoice to Steven Adamson for the final contract payment

- Project Archival

Upon payment of the final contract payment by Steven Adamson, all project documentation may be archived. The project archive checklist found in Appendix 44 must be printed off and checked off as each piece of project documentation is archived in both hard and electronic copy. Ltd.

## 2. Scope Management Plan

### 2.1. Deliverables

The deliverables for the project include:

Stage 1 – site preparation.

- removal of existing structures

- clearing of site ready for construction

- installation of services and drainage

Stage 2 Building

- construction

- landscaping

- completion of the project

- lighting and power outlet

### 2.2. Inclusions

Stage 1 – Site preparation

- Removal of existing structures

  - Removeable of existing bird cage

  - Remove old edging

- Clearing of site ready for construction

  - level site

  - removal of rubbish

- Installation of services and drainage

  - install drainage

  - install electrical (undergrounds)

- Installation of footings

  - excavation of footings

  - installation of footings

- purchasing gear for project

  - order gear

Stage 2 Building

- Construction

  - Bricking of walls

  - Rendering of walls

  - Painting of walls

  - Paving

  - Construction of Timber shade roof

  - Construction of seating

  - Supply and installation of lighting and power outlet

- landscaping

  - Edging

  - Turf

  - Supply and installation of plants

- completion of the project

  - removal of all rubbish associated with the project

### 2.3. Exclusions

The project exclusions include:

- Removal of surplus materials or soil

- And repairs or modifications of new and existing services including electricity and water

- Any scope not covered in the approved plans

- Any labor or employment costs for Steven Adamson (sponsors husband)

### 2.4. Handover

The final handover to the client (Mary Adamson) is to occur upon completion of stage 2.

The project will be signed off as complete only when:

The client is satisfied all deliverables have been completed and delivered to the required quality.

The client has settled all outstanding contract payments.

A completion report has been written and provided with an updated version of the project plan showing all project activities have been complete.

5. The formal handover will be at a meeting where the final project report, finalised project plan and the final handover form has been signed off by Mary Adamson (Owner), Fred Butt (Director WSP).

## 3. Time Management Plan

### 3.1. Schedule

The schedule of this project needs to primarily work around the availability of Steven Adamson and his time off.

A summary of the schedule at each phase of the project appears below.

For further detail, refer to the following appendices:

- Appendix 1: WBS

- Appendix 2: Gantt Chart

- Appendix 3: Network Diagram

- Appendix 4: Effort and Duration of Tasks

- Appendix 5: Task Dependency Worksheet

Stage 1 – Site preparation

The Stage commences on Saturday 4 December 2021.

The Site preparation stage will need to be complete prior to the commencement of the Building Stage. The completion of this Stage will be on Thursday 16th December 2021.

Stage 2 Building

The Stage commences on Friday 17 December 2021.

During this time Steven Adamson is going away from the Sunday the 19th of December 2021 till Tuesday the 2nd January 2022 and site will not be available

This project is due for completion on the Tuesday 25th January 2022.

### 3.2. Milestones

Stage 1 – Site preparation

- Demolition and site preparation

  - Removal of old structures by 6th December 2021

  - Leveling of site by 13th December 2021

- Installation of footings by 16th December 2021

Stage 2 Building

- Construction of timber shade area by 17th January 2022

- Installation of plants and turf by 21st January 2022

## 4. Cost Management Plan

### 4.1. Budget

The following table provides a summary of the cost of each phase of the project:

| Stage | Labour | Procurement | Purchase | Total |
| --- | --- | --- | --- | --- |
| Site preparation | 2109 | 2160 | 4900 | 9169 |
| Building | 6710 7510 | 1440 | 2800 3400 | 10950 12390 |
| Total | 8819 9619 | 3600 | 7700 8300 | 20119 23167 |

### Estimating methodology

The estimating methodology for this project budget is covered in Appendix 7. The methodology used to calculate the figures are as follows:

Staff costs –This is the hourly charge out rate inc. GST has been calculated based on the staff.

All procurement and expenditure costs are as per quoted figures in provided quotes. The tender request documentation broke down the items of work as per the tasks in the Gantt chart. Suppliers were required to quote for each task to assist with the budgeting process.

### Confidence level

Provided there are no scope or time variations in the project, the budget in this project plan has a high level of confidence.

The procurement values have been based on a fixed cost basis with the suppliers. All suppliers have supplied quotes, But are only valid for 30days  , all suppliers foresee a change in supply pricing for at 15 months Unless there are changes to project scope, there won’t therefore be any changes to the procurement costs.

### Contingency

The sponsors (Mary adamson) have signed a contract for a fixed price of  $25000 $26440( including lighting and power outlet

The project budget as per this project plan is $20119  $26440.This leaves a surplus or contingency of $4881 to absorb any extra costs the project will incur. WSP has a cash reserve of $12000 for this project See Appendix 8.

The sponsors have allowed a total budget of $30000 to allow for any additional changes to the project.

### Source of Funds

As per project contract between  WSP and Mary Adamson, the funds of

$25000 $26440 -inc  GST will be paid for all  work done in this project. This is a fixed price contract, as per the original plans

any project extensions, variations in scope, or increases in cost of labour, procurement or purchases will have to be approved before any payments can be made

The funds will be paid by Massive Eco‐ Development Corporation at the following points in the project:

    - Payment 1: 10% initial payment at the signing of the contract

    - Payment 2: 40% progress payment upon completion of all Stage1 deliverables and delivery of project progress report.

    - Payment 3: 50% final payment upon completion of all phase 3 deliverables and delivery of the project final report.

As per contract with Mary Stevenson (sponsor), and as per WSP’s invoicing cycle, WSP will raise an invoice on the first working day following the due date of each progress payment.

The terms  of  al I invoices  are  7days.  All cash flow calculations are based on the funds being paid on the final day of the terms of the invoices.

| Expected payment date: | Payment | Proportion | Amount (pre‐GST) | Amount (GST incl.) |
| --- | --- | --- | --- | --- |
| 20th September 2021 | Payment 1 | 10% | $2272.73 | $2500 |
| 25th December 2021 | Payment 2 | 40% | $9090.90 | $10000 |
| 3rd February 2022 | Payment 3 | 50% | $11363.63$12672 | $12500$13940 |
|  | TOTAL | 100% | $22727.27$24036 | $25000$26440 |

The payments will be as follows:

### 4.6. Cash Flow

The project expenditure cashflow chart and S curve have been provided in Appendix 8. The methodology used to calculate the project cash flow is as follows:

Labour – All employees of WSP are paid on a weekly basis at the end of the week.

Procurement – As per contracts with sub-contractor payments will be made on the final week of each stage of the project, they are performing project tasks in. Payment to be made immediately upon completion of the work done for the stage.

Purchases – All purchases have been calculated to occur as they are needed

The S curve has been constructed from the results of the above calculations.

The project cashflow has been calculated from the S curve calculations above. These figures are subtracted from the cumulative income the project will receive from its four progress payments from Mary Adamson, on the dates when they are expected to be paid based on the invoicing cycle determined above.

## 5. Quality Management Plan

### 5.1. Overview of Quality Requirements

There are a number of sources of quality requirements for this project. These include:

    - General Building Regulations/design

    - Licenses for Operation of Equipment.

### 5.2.  Council Regulations

No council reequipments are needed due type and cost of the project

### 5.3. Building Regulations

There are no council building rules to be adhered too, the owners want the walls and timber frame to be structurally  sound , As such want a designer / engineer to be involved in the   design of the project (Fred Butt of WSP is a licenced structural & civil engineer)

### 5.4. Operation of Equipment

All contractors operating equipment must be appropriately qualified/certified as follows:

    - Construction induction card. All personnel working on, or otherwise accessing the site must be the holder of an appropriate construction induction card.

    - Bobcat operator ticket.

    - Excavator license.

### 5.5. Quality Assurance

The project integration processes will be audited on as needed basis.

Most quality assurance will be conducted by the project manager as the work progresses. Any issues will be reported to the director of WSP.

### 5.6. Quality Control

An internal audit will be conducted on the completed at certain stages throughout the project. This will be conducted by the project manager and director of WSP.

Quality audits to be completed

9.level site

14.concrete footings

19.bricking of wall

36.remove all rubbish (final site clean-up)

## 6. Human Resource Management Plan

### 6.1. Stakeholders

### 6.2. Resource Capability

## 7. Communications Management Plan

### 7.1. Organisational Structure

### 7.2. Escalation

## 8. Risk Management Plan

### 8.1. Constraints

Owners husband (Steven Adamson) to be able to do a lot of the work during his days off

Time frame to complete project

The project must be completed with minimal disruption to existing services and other parts of the site (as owner currently living on site )

### 8.2. Assumptions

All materials and plant will be available when needed at the costs quoted

All procurement of trades will be available when needed

No council approval is needed due to the type and cost of the project

### 8.3. Potential Issues

Adverse weather conditions (e.g heavy rain) delaying the project

Construction equipment breaking down

Delays in the delivery of materials

Cost increases

Availability of materials

Availability of additional Labour

These issues have been populated into the issues register in appendix 19

### 8.4. Risk

A risk management has also been developed (see Appendices 22,23,24,25,26,27,28,29,30, &31) for the primary identified risks to the project .

## 9. Procurement Management Plan

### 9.1. Procurement Planning and Solicitation Planning

### 9.2. Contract Administration

### 9.3. Contract Close-out

Appendices

Table of Contents	5

Appendices	21

Appendix 1 – WBS	23

Appendix 2 – Gantt Chart – Provided as a separate attachment	24

Appendix 3 – Network Diagram – Provided as a separate attachment	24

Appendix 4 - Effort and Duration of Tasks	25

Appendix 5 - Task Dependency Worksheet	26

Appendix 6 - Summary Costing per Phase	27

Appendix 7 - Detailed Costing per Task	28

Appendix 8 - Project Cashflow	30

Appendix 9 - Quality Analysis Tool	32

Appendix 10 - Quality Plan	34

Appendix 11 – Organisation Chart – WSP	36

Appendix 12 – Organisation Chart – Project	36

Appendix 13 - Responsibility Assignment Matrix Template	37

Appendix 14 - Staffing Management Plan	38

Appendix 15 - Resource Requirements Worksheet	40

Appendix 16 - Stakeholder Analysis Template	42

Appendix 17 - Resource Pool Description Template	43

Appendix 18 - Detailed Resource Allocation	44

Appendix 19 - Issues Register Template	45

Appendix 20 - Communications Plan Template	46

Appendix 21 - Communication Requirements Analysis Worksheet	47

Appendix 22 - Risk Management Plan Template	48

Appendix 23 - Risk Identification – SWOT Analysis	49

Appendix 24 - Rating Impacts for a Risk	50

Appendix 25 - Risk Rating Table	51

Appendix 26 - Risk Brainstorming Session Worksheet	52

Appendix 27 - Project Risk Categorisation Worksheet	54

Appendix 28 - Project Risk Prioritisation Worksheet	55

Appendix 29 - Risk Response Plan	59

Appendix 30 - Workaround Planning Worksheet Template	60

Appendix 31 - Project Risk Review Matrix Template	61

Appendix 32 - Statement of Work – mini dig	62

Appendix 33 - Statement of Work – 	63

Appendix 34 - Procurement Management Planning Checklist Template	64

Appendix 35 - Work Authorisation Form Template	65

Appendix 36 - Quality Audit Template	66

Appendix 37 - Change Register	67

Appendix 38 - Project Change Request Template and completed change requests 	68

Appendix 39 - Project Status Report Template	71

Appendix 40 - Work Results Guidelines	73

Appendix 41 - Lessons Learned Documentation Template	75

Appendix 42 - Project Completion Report Template	76

Appendix 43 - Formal Acceptance and Closure Template	77

Appendix 44 - Project Archives Checklist Template	78

Appendix 1 – WBS

Appendix 2 – Gantt Chart – Provided as a separate attachment

Appendix 3 – Network Diagram – Provided as a separate attachment

Appendix 4 - Effort and Duration of Tasks

| Task number | Task description | Task effort(hrs ) |  |  |  | Task duration (days ) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | To | Tp | Tm | Te | To | Tp | Tm | Te |
| 1 | Back yard project |  |  |  |  |  |  |  |  |
| 2 | design | 13.4 | 20 | 16.8 | 16.8 | 1.2 | 2 | 1.6 | 2 |
| 3 | site preperation (stage1) |  |  |  |  |  |  |  |  |
| 4 | demolition |  |  |  |  |  |  |  |  |
| 5 | remove old bird cage | 7 | 15 | 11 | 11 | .3 | 2 | 1 | 2 |
| 6 | remove old edgeing & pavers | 5 | 15 | 10 | 10 | 1 | 2 | .8 | 2 |
| 7 | remove rubbish | 4 | 6 | 5 | 5 | 1 | 2 | 1 | 2 |
| 8 | order materials | 7 | 9 | 8 | 8 | 1 | 2 | .8 | 2 |
| 9 | level site | 6.2 | 13 | 9.6 | 9.6 | .5 | 2 | .8 | 2 |
| 10 | install drainage | 6 | 10 | 8 | 8 | .5 | 2 | .6 | 1 |
| 11 | install electrical (undergounds ) | 3 | 5 | 4 | 4 | .2 | 1 | .4 | 1 |
| 12 | Footings |  |  |  |  |  |  |  |  |
| 13 | dig footing (mini dig) | 3.6 | 10 | 6.8 | 6.8 | .5 | 2 | .8 | 2 |
| 14 | concrete footings | 15 | 17 | 16 | 16 | .5 | 2 | .8 | 2 |
| 15 | construction (stage 2 ) |  |  |  |  |  |  |  |  |
| 16 | delivery of bricks and pavers |  |  |  |  |  |  |  |  |
| 17 | relocation of bricks etc to rear of | 12 | 20 | 16 | 16 | 1 | 2 | 1.6 | 2 |
| 18 | brick walls |  |  |  |  |  |  |  |  |
| 19 | bricking of wall | 28 | 40 | 34 | 34 | 3 | 4 | 2.4 | 4 |
| 20 | rendering of wall | 15 | 25 | 20 | 20 | 1 | 3 | 1.4 | 2 |
| 21 | painting of wall | 7 | 9 | 8 | 8 | .5 | 1 | .8 | 2 |
| 22 | edging | 26 | 40 | 32 | 32 | 1 | 2 | 1.6 | 2 |
| 23 | pavers | 15 | 25 | 20 | 20 | 1 | 2 | 1.6 | 2 |
| 24 | timber shade roof |  |  |  |  |  |  |  |  |
| 25 | install timber battens | 24 | 30 | 27 | 27 | 3 | 6 | 3.6 | 5 |
| 26 | paint timber battens | 10 | 12 | 11 | 11 | 1 | 2 | 1.1 | 2 |
| 27 | install shed cloth | 3 | 5 | 4 | 4 | .2 | 1 | .4 | 1 |
| 28 | seating |  |  |  |  |  |  |  |  |
| 29 | install timber seating around | 31 | 45 | 38 | 38 | 2 | 3 | 2.4 | 3 |
| 30 | seal/ paint timber seating | 7 | 9 | 8 | 8 | .5 | 1 | .8 | 1 |
| 31 | gardens and lawn |  |  |  |  |  |  |  |  |
| 32 | back fill soil in gardens | 7 | 9 | 8 | 8 | .5 | 1 | .8 | 2 |
| 33 | install turf | 14 | 30 | 22 | 22 | 1.5 | 2 | 1.9 | 2 |
| 34 | plant gardens | 8.8 | 10 | 9.4 | 9.4 | 8 | 10 | 8.6 | 9 |
| 35 | project completion |  |  |  |  |  |  |  |  |
| 36 | remove all rubbish | .3 | .3 | .3 | .3 | .1 | .5 | .3 | .5 |
| 37 | review with owner | 12 | 18 | 15 | 15 | .5 | 1 | .6 | 1 |
| 38 | Lighting and power outlet |  |  |  |  |  |  |  |  |
| 39 | Lighting and power outlet | 6 | 10 | 8 | 8 | .5 | 1 | .8 | 1 |

Appendix 5 - Task Dependency Worksheet

| Task number | Task description | Duration (days) | Predcessors |  |  |  |  | Constraints |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FS | SS | FF | SF | Lag | type | date |
| 1 | Back yard project |  |  |  |  |  |  |  |  |
| 2 | design | 2 |  |  |  |  |  |  |  |
| 3 | site preperation (stage1) |  |  |  |  |  |  |  |  |
| 4 | demolition |  |  |  |  |  |  |  |  |
| 5 | remove old bird cage | 2 | 2 |  |  |  |  |  |  |
| 6 | remove old edgeing & pavers | 2 | 5 |  |  |  |  |  |  |
| 7 | remove rubbish | 2 |  |  |  |  |  |  |  |
| 8 | order materials | 2 |  |  | 2 |  |  |  |  |
| 9 | level site | 2 | 6 |  |  |  |  |  |  |
| 10 | install drainage | 1 | 6,9 |  |  |  |  |  |  |
| 11 | install electrical (undergounds ) | 1 |  |  |  |  |  |  |  |
| 12 | Footings |  |  |  |  |  |  |  |  |
| 13 | dig footing (mini dig) | 2 | 9 |  |  |  |  |  |  |
| 14 | concrete footings | 2 | 13 |  |  |  |  |  |  |
| 15 | construction (stage 2 ) |  |  |  |  |  |  |  |  |
| 16 | delivery of bricks and pavers |  |  |  |  |  |  |  |  |
| 17 | relocation of bricks etc to rear of | 2 |  |  |  |  |  |  |  |
| 18 | brick walls |  |  |  |  |  |  |  |  |
| 19 | bricking of wall | 4 | 14 |  |  |  |  |  |  |
| 20 | rendering of wall | 2 | 19 |  |  |  |  |  |  |
| 21 | painting of wall | 2 | 20 |  |  |  |  |  |  |
| 22 | edging | 2 | 14 |  |  |  |  |  |  |
| 23 | pavers | 2 |  |  |  |  |  |  |  |
| 24 | timber shade roof |  |  |  |  |  |  |  |  |
| 25 | install timber battens | 5 | 20 |  |  |  |  |  |  |
| 26 | paint timber battens | 2 | 25 |  |  |  |  |  |  |
| 27 | install shed cloth | 1 | 26 |  |  |  |  |  |  |
| 28 | seating |  |  |  |  |  |  |  |  |
| 29 | install timber seating around | 3 |  |  |  |  |  |  |  |
| 30 | seal/ paint timber seating | 1 |  |  |  |  |  |  |  |
| 31 | gardens and lawn |  |  |  |  |  |  |  |  |
| 32 | back fill soil in gardens | 2 |  |  |  |  |  |  |  |
| 33 | install turf | 2 |  |  |  |  |  |  |  |
| 34 | plant gadens | 9 |  |  |  |  |  |  |  |
| 35 | project completion |  |  |  |  |  |  |  |  |
| 36 | remove all rubbish | .5 | 36 |  |  |  |  |  |  |
| 37 | review with owner | 1 |  |  |  |  |  |  |  |
| 38 | Lighting and power outlet |  |  |  |  |  |  |  |  |
| 39 | Lighting and power outlet | 1 | 25 |  |  |  |  |  |  |

FS = Finish to start – This task commences following the end of the listed tasks.

SS = Start to start – This task starts at the same time as the listed tasks.

FF = Finish to finish – This task finishes at the same time as the listed tasks.

SF – Start to finish – This task finishes at the same time the listed tasks commence. Lag = number of days between tasks.

Appendix 6 - Summary Costing per Stage

| Project description | Labour costs |  | Procurement costs | Purchase cost | Total cost |
| --- | --- | --- | --- | --- | --- |
|  | Time (hr) | cost |  |  |  |
| Stage 1 -Site preparation : |  |  |  |  |  |
| Demolition | 41.6 | $1311 | $1680 | $4300 | $7291 |
| Footings | 17.2 | $798 | $480 | $600 | $1878 |
| Stage 2 -Building : |  |  |  |  |  |
| Delivery of bricks etc | 16 | $0 | $0 | $0 | $0 |
| Brick walls | 90 | $855 | $1440 | $500 | $2795 |
| Timber shade roof | 45 | $1520 | $0 | $250 | $1770 |
| seating | 38 | $1425 | $0 | $250 | $1675 |
| Gardens and lawn | 39.4 | $855 | $0 | $1700 | $2555 |
| Project completion | 15 | $915 | $0 | $100 | $1015 |
| Lighting and power outlet | 8 | $800 | $0 | $640 | $1440 |

Appendix 7 - Detailed Costing per Task

| Task number | Task Description | Time |  |  | Hrly rate | Labour Cost | Procurement |  | Purchases |  | TOTAL COST |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Te | Who? | # |  |  | Description | Cost | Description | Cost |  |
| 1 | design | 16 .8 | NP FB | 1 1 | 95 110 | 1520 88 |  |  |  |  | 1608 |
| 2 | site preperation (stage1) |  |  |  |  | 2109 |  | 2160 |  | 4900 | 9169 |
| 3 | demolition | 41.6 |  |  |  | 1311 |  | 1680 |  | 4300 | 7291 |
| 4 | remove old bird cage | 11 | SA | 1 | 0 | 0 |  |  |  |  | 0 |
| 5 | remove old edgeing & pavers | 10 | SA | 1 | 0 | 0 |  |  |  |  | 0 |
| 6 | remove rubbish | 5 | SA | 1 | 0 | 0 |  |  | Removal fees | 100 | 100 |
| 7 | order materials | 8 | NP | 1 | 95 | 760 |  |  | Bricks pavers soil | 4200 | 4960 |
| 8 | level site | .8 .8 | NP SA | 1 1 | 95 0 | 76 0 | NH | 960 |  |  | 1036 |
| 9 | install drainage | 1 1 | NP SA | 1 1 | 95 0 | 95 0 | NH | 720 |  |  | 815 |
| 10 | install electrical (undergounds ) | 4 | NP | 1 | 95 | 380 |  |  |  |  | 380 |
| 11 | Footings | 17.2 |  |  |  | 798 |  | 480 |  | 600 | 1878 |
| 12 | dig footing (mini dig) | .4 2.4 | NP SA | 1 1 | 95 0 | 38 0 | NH | 480 |  |  | 518 |
| 13 | concrete footings | 8 8 | NP SA | 1 1 | 95 0 | 760 0 |  |  | Concrete | 600 |  |
| 14 | construction (stage 2 ) |  |  |  |  | 6710 7510 |  | 1440 |  | 2800 3440 | 10950 12390 |
| 15 | delivery of bricks and pavers | 16 |  |  |  | 0 |  | 0 |  | 0 | 0 |
| 16 | relocation of bricks etc to rear of | 16 | SA | 1 | 0 |  |  |  |  |  | 0 |
| 17 | brick walls | 90 |  |  |  | 855 |  | 1440 |  | 500 | 2795 |
| 18 | bricking of wall | 2 8 | NP SA | 1 1 | 95 0 | 190 | SP | 1440 | Sand and cement | 200 | 1830 |
| 20 | rendering of wall | 7 13 | NP SA | 1 0 | 95 0 | 665 0 |  |  | Sand & cement | 200 | 865 |
| 21 | painting of wall | 8 | SA | 1 | 0 | 0 |  |  | Paint | 100 | 100 |
| 22 | edgeing | 8 24 | NP SA | 1 1 | 95 0 | 760 0 |  |  |  |  | 760 |
| 23 | pavers | 4 16 | Np SA | 1 1 | 95 0 | 380 0 |  |  |  |  | 380 |
| 24 | timber shade roof | 45 |  |  |  | 1520 |  |  |  | 250 | 1770 |
| 25 | install timber battens | 15 15 | NP SA | 1 1 | 95 0 | 1290 0 |  |  | Timber & consumables | 150 | 1290 |
| 26 | paint timber battens | 11 | SA | 1 | 0 | 0 |  |  | paint | 100 | 100 |
| 27 | install shed cloth | 4 | NP | 1 | 95 | 380 |  |  |  |  | 380 |
| 28 | seating | 38 |  |  |  | 1425 |  |  |  | 250 | 1675 |
| 29 | install timber seating around | 15 15 | NP SA | 1 1 | 95 0 | 1425 0 |  |  | Timber& consumables | 150 | 1575 |
| 30 | seal/ paint timber seating | 8 | SA | 1 | 0 | 0 |  |  | paint | 100 | 100 |
| 31 | gardens and lawn | 39.4 |  |  |  | 855 |  |  |  | 1700 | 2555 |
| 32 | back fill soil in gardens | 4 4 | NP SA | 1 1 | 95 0 | 380 0 |  |  | Soil | 200 | 580 |
| 33 | install turf | 3 19 | Np SA | 1 1 | 95 0 | 285 0 |  |  | turf | 1000 | 1285 |
| 34 | plant gardens | 2 7.4 | NP SA | 1 1 | 95 0 | 190 0 |  |  | Plants | 500 | 690 |
| 35 | project completion | 15 |  |  |  | 915 |  |  |  | 100 | 1015 |
| 36 | remove all rubbish |  | SA | 1 | 0 | 0 |  |  | Rubbish removal fee | 100 | 100 |
| 37 | review with owner | 4 6 5 | FB SA NP | 1 1 1 | 110 0 95 | 440 0 475 |  |  |  |  | 915 |
| 38 | Lighting and power |  |  |  |  | 800 |  |  |  | 640 | 1440 |
| 39 | Lighting and power outlet | 8 | NP | 1 | 100 | 800 |  |  | Electrical fittings | 640 | 1440 |
|  | Total |  |  |  |  |  |  |  |  |  | 21727 23167 |

Key of resources:

FB  =  Fred Butt -Director

NP = Nigel phillips -project manager

SA = Steven Adamson ( owner / laborer- husband of sponsor)

Sub contractors

NH = Neil Hole – mini dig SEQ

SP = stan peters- brick layer

Appendix 8 - Project Cashflow

| Week ending | Weekly Cashflow | Expenses |
| --- | --- | --- |
| 03/09/2021 | $12000 | $0 |
| 10/09/2021 | $12000 | $0 |
| 17/09/2021 | $12000 | $0 |
| 24/09/2021 | $12000 | $0 |
| 01/10/2021 | $14500 ( contract sign deposit -$2500) | $0 |
| 08/10/2021 | $14500 | $0 |
| 15/10/2021 | $14500 | $0 |
| 22/10/2021 | $14500 | $0 |
| 29/10/2021 | $14500 | $0 |
| 5/11/2021 | $14500 | $0 |
| 12/11/2021 | $14500 | $0 |
| 19/11/2021 | $14500 | $0 |
| 26/11/2021 | $12892 | $1608 |
| 3/12/2021 | $12032 | $860 |
| 10/12/2021 | $7832 | $4200 |
| 17/12/2021 | $3723 | $4190 |
| 24/12/2021 | $3723 | $0 |
| 31/12/2021 | $13723 ( 1st stage payment -$10000) | $0 |
| 07/01/2022 | $10833 | $2890 |
| 14/01/2022 | $9063 | $1770 |
| 21/01/2022 | $6143$4703 | $2920$4360 |
| 28/01/2022 | $3153$1713 | $2990 |
| 04/02/2022 | $15653 (final payment $12500 $13940) | $0 |

Appendix 9 - Quality Analysis Tool

| Task (From Gantt chart) | People Standard | Process Standard | Product/Service Standard | Strategy (Action Plan) |
| --- | --- | --- | --- | --- |
| 5.remove old bird cage | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 6.remove old edging & pavers | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 7.remove rubbish | General labourer | N/A | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 8.order materials | Project manager | N/A | Building construction plan | WSP director to check quantities before placeing order |
| 9.level site | Earth moving licence | Earth moving standard | Building construction plan | Site supervisor to ensure procedure is followed. PM to conduct QA audit |
| 10. install drainage | Contruction /plumbing licence | Plumbing standards | Building construction plan | Site supervisor to ensure procedure is followed. |
| 11.install electrical (undergounds ) | Electrical licence | As3000 electrical standards | Building construction plan | Site supervisor to ensure procedure is followed. |
| 13.dig footing (mini dig) | Earth moving licence | Earth moving standard | Building construction plan | Site supervisor to ensure procedure is followed |
| 14.concrete footings | construction qualification/ skills | Construction / building standards | Building construction plan | Site supervisor to ensure procedure is followed. PM to conduct QA audit |
| 17.relocation of bricks etc to rear of | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 19.bricking of wall | construction qualification/ skills | Construction / building standards | Building construction plan | Site supervisor to ensure procedure is followed. PM to conduct QA audit |
| 20.rendering of wall | construction qualification/ skills | Construction / building standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 21.painting of wall | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 22.edging | General labourer | Workplace and construction standards | Building construction plan | Site supervisor to ensure it is done safely and as per plans |
| 23.pavers | General labourer | Workplace and construction standards | Building construction plan | Site supervisor to ensure it is done safely and as per plans |
| 25.install timber battens | construction qualification/ skills | Construction / building standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 26.paint timber battens | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 27.install shed cloth | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 29.install timber seating around | construction qualification/ skills | Construction / building standards | Building construction plan | Site supervisor to ensure procedure is followed. |
| 30.seal/ paint timber seating | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 32.back fill soil in gardens | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 33.Install turf | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 34.plant gardens | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans |
| 36.remove all rubbish | General labourer | Workplace and construction standards | Site plan WSP SWMS | Site supervisor to ensure it is done safely and as per plans PM to conduct QA audit |
| 37.review with owner | Project management team | N/A | Project closure documents | Site supervisor to ensure procedure is followed. |

Appendix 10 - Quality Plan

| Activity | Items/Individual Deliverables | Standard(s) to be applied | Strategy/Action Plan to meet the standards specified | Responsibility |
| --- | --- | --- | --- | --- |
| 5.remove old bird cage | Clean site ready for leveling | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 6.remove old edging & pavers | Clean site ready for leveling | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 7.remove rubbish | Clean site ready for leveling | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 8.order materials | Ordrer gear for job that has long lead time | WSP ordering procedures | WSP director to check quantities before placing order | Fred Butt |
| 9.level site | Flat clear level site ready for construction | Work place standards, inc safety | Site supervisor to ensure procedure is followed. PM to conduct QA audit | Nigel phillips Fred Butt |
| 10. install drainage | Install drainage to allow storm water to get away quickly | Work place standards, inc safety, and plumbing | Site supervisor to ensure procedure is followed. | Nigel phillips |
| 11.install electrical (undergounds ) | Install underground conduits and cables for future power to area | Work place standards, inc safety and electrical | Site supervisor to ensure procedure is followed. | Nigel phillips |
| 13.dig footing (mini dig) | Dig trench for footing | Work place and construction standards, inc safety | Site supervisor to ensure procedure is followed | Nigel phillips |
| 14.concrete footings | Concrete footings for walls and edging | Work place and construction standards, inc safety | Site supervisor to ensure procedure is followed. PM to conduct QA audit | Nigel phillips Fred Butt |
| 17.relocation of bricks etc to rear of | Relocate bricks from delivery area to work area | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 19.bricking of wall | Construction of brick walls for gardens and seats | Work place and construction standards, inc safety | Site supervisor to ensure procedure is followed. PM to conduct QA audit | Nigel phillips Fred Butt |
| 20.rendering of wall | Concrete rendering of walls | Work place and construction standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 21.painting of wall | Painting | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 22.edging | edging for garden beds | Work place and construction standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 23.pavers | pavers for fire pit area | Work place and construction standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 25.install timber battens | Structure to hold shade cloth | Work place and construction standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 26.paint timber battens | painting | Work place and construction standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 27.install shed cloth | Sun cover | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 29.install timber seating around | Seating | Work place and construction standards, inc safety | Site supervisor to ensure procedure is followed. | Nigel phillips |
| 30.seal/ paint timber seating | Weather protection of timber | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 32.back fill soil in gardens | Quality Soil for gardens | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 33.Install turf | Replace damaged turf during construction | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 34.plant gardens | Easy to maintain gardens | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans | Nigel phillips |
| 36.remove all rubbish | Final site clean up | Work place standards, inc safety | Site supervisor to ensure it is done safely and as per plans PM to conduct QA audit | Nigel phillips Fred Butt |
| 37.review with owner | Hand over to client | WSP project closure documents | Site supervisor to ensure procedure is followed. PM to conduct QA audit | Fred butt & Nigel phillips |

Appendix 11 – Organisation Chart – WSP

Appendix 12 – Organisation Chart – Project

Appendix 13 - Responsibility Assignment Matrix Template

| PERSON PHASE | Fred Butt (WSP) | Nigel phillips (WSP) | Mary Adamson (sponsor) | Sub constructors | Steven Adamson ( additional labour and husband of mary) |  |
| --- | --- | --- | --- | --- | --- | --- |
| Scoping | A | P | A |  |  |  |
| Planning | S | P | SP | I | I |  |
| - site preparation (stage1) | R | A |  | P | P |  |
| - construction (stage 2) | R | A |  | P | P |  |
| Finalization | AS | P | S |  |  |  |

P = Participant	A = Accountable	    R = Review Required

I = Input Required	   	S = Sign-off Required

Appendix 14 - Staffing Management Plan

Project Name: 11 Balfour st backyard makeover project

Prepared by: Nigel phillips

Date:

Project Manager: Nigel phillips

Staffing Management Plan Number: 1

Project Team Role: oversee and construct entire project

Approach to Identifying Human Resource Needs: Employees of WSP will be utilized where possible. Additional labor to be supplied by Steven Adamson (husband of sponsor ) to keep costs down, steven is also a licensed plumber. External contractors will be utilised for skillsets that cannot be fulfilled by WSP. External contractors will be covered separately in the procurement plan

Approach to Determining Timing Needs for Adding and Removing Project Personnel: This project has a large amount of labour supplied by steven Adamson (husband of Sponsor ), steven has time off in December and January , Also this project will span the Christmas holiday break , all resources will have to work with the schedule

| Human Resource Needs: |  |  |  |
| --- | --- | --- | --- |
| Description | Estimated Number | Projected Commencement | Projected Completion |
| Project manger | 1 | 24th 11-2021 | 25th 01-2022 |
| Additional labourers | 1 | 4th 12-2021 | 25th 01-2022 |

| Projected Approach and Schedule for Updating Staffing Management Plan: |  |
| --- | --- |
| Triggering Event | Expected Timing |
| - Resignation of project manager. | 2-4 weeks downtime. |
| - Injury or change of plans by to Steven Adamson | 2-4 weeks downtime. |
| Additional Notes: |  |
| 1. |  |
| 2. |  |

Appendix 15 - Resource Requirements Worksheet

| Work Breakdown Structure Element | Type of Resource Required: | Quantity | Involve Staff Acquisition? (Notes) | Involve Procurement? (Notes) |
| --- | --- | --- | --- | --- |

Appendix 16 - Stakeholder Analysis Template

| Project Stakeholder | Specific Information Needs | Best Source of Information Needed | Planned Method of Delivery | Timing Considerations |
| --- | --- | --- | --- | --- |

Appendix 17 - Resource Pool Description Template

| Project Name: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PROJECT PERIODS (Months) (Shade in periods of resource availability) |  |  |  |  |  |  |  |  |  |  |
| Resource # | Needed Resources | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| 1 | Fred Butt (director WSP) |  |  |  |  |  |  |  |  |  |
| 2 | Nigel phillips (PM WSP) |  |  |  |  |  |  |  |  |  |
| 3 | Steven Adamson (additional labour) |  |  |  |  |  |  |  |  |  |
| 4 | Neil hole (digger)_ |  |  |  |  |  |  |  |  |  |
| 5 | Stan peters (brick layer |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |
| Remaining Resource Issues: NIL |  |  |  |  |  |  |  |  |  |  |  |

Appendix 18 - Detailed Resource Allocation

| Work Breakdown Structure Element | Type of Resource Required: | Quantity | Involve Staff Acquisition? (Notes) | Involve Procurement? (Notes) |
| --- | --- | --- | --- | --- |

Appendix 19 - Issues Register Template

| Issue # | Date/time raised | Description | Who raised | Action History | Status open/closed |
| --- | --- | --- | --- | --- | --- |

Appendix 20 - Communications Plan Template

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |
| Key Stakeholders (Distribution Schedule) | Stakeholder Issues | Key Messages to Communicate | Communication Methods to be Used (written, one-on-one, electronic, meetings, etc.) | Description of Specific Communications (content, format, level of detail, etc.) | Timing Issues (see also Bar Chart, Project Schedule) | Other |

Appendix 21 - Communication Requirements Analysis Worksheet

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |
| --- | --- | --- | --- | --- |
| General Area of Communication Need | Information Needed, and for Whom? | Optimum Information Format(s) | How is this communication essential to success of project? | Decision to implement Yes/No |
| Project Organisation Relationships |  |  |  |  |
| Stakeholder Responsibility Relationships |  |  |  |  |
| Sponsor Relationships |  |  |  |  |
| Logistics of Project Staffing by Location |  |  |  |  |
| External: Media |  |  |  |  |
| External: Community |  |  |  |  |
| External: Government, Regulatory Agencies |  |  |  |  |

Appendix 22 - Risk Management Plan Template

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: Nigel phillips |  |  |  |  |  |
| Date: 30-05-2021 |  |  |  |  |  |
| Evaluating Impact of a Risk on Major Project Objectives (ordinal scale or cardinal, non-linear scale) |  |  |  |  |  |  |
| Project Objective | Very Low .05 | Low .1 | Moderate .2 | High .4 | Very High .8 |
| Cost | Insignificant Cost Increase | <5% Cost Increase | 5–10% Cost Increase | 10–20% Cost Increase | >20% Cost Increase |
| Schedule | Insignificant Schedule Slippage | Schedule Slippage <5% | Overall Project Slippage 5–10% | Overall Project Slippage 10–20% | Overall Project Schedule Slips >20% |
| Scope | Scope Decrease Barely Noticeable | Minor Areas of Scope Are Affected | Major Areas of Scope Are Affected | Scope Reduction Unacceptable to the Client | Project End Item Is Effectively Useless |
| Quality | Quality Degradation Barely Noticeable | Only Very Demanding Applications Are Affected | Quality Reduction Requires Client Approval | Quality Reduction Unacceptable to the Client | Project End Item Is Effectively Unusable |

The impacts on project objectives can be assessed on a scale from Very Low to Very High or on a numerical scale.

The numerical (cardinal) scale shown here is non-linear, indicating that the organisation wishes specifically to avoid risks with high and very-high impact.

Appendix 23 - Risk Identification – SWOT Analysis

Project Name: 11 Balfour st backyard makeover project

Prepared by: Nigel phillips

Date: 30-05-12

Project Manager: Nigel phillips

SWOT Analysis Facilitator: Nigel Phillips

SWOT Analysis Participants: - Nigel phillips – PM - Fred butt Director WSP - Stan peters – bricklayer - Steven Adamson – owners husband (additional labour )

SWOT Analysis Recorder: Nigel phillips

Date of SWOT Analysis: 30-05-2021

Project Strengths: WSP have a strong history of delivering similar projects on time and on budget. WSP have known Mary Adamson from minor jobs done in the past and know what is expected from each party WSP have a proven history of delivery quality.

Project Weaknesses: the project will rely heavily on the sponsors husband (Steven Adamson) to supply labour and do parts of the project Dependence of external contractors being available when needed

Project Opportunities:1.Ongoing projects with the sponsor on other properties that they own - Other work in the local area

Project Threats: - Severe weather is likely to cause delays - Steven Adamson (sponsors husband) being unavailable to do work when required. - The supply of materials when needed at the price quoted (due to building boom)

Appendix 24 - Rating Impacts for a Risk

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: Nigel Phillips |  |  |  |  |  |
| Date: 30-05-2021 |  |  |  |  |  |
| Evaluating Impact of a Risk on Major Project Objectives (ordinal scale or cardinal, non-linear scale) |  |  |  |  |  |  |
| Project Objective | Very Low .05 | Low .1 | Moderate .2 | High .4 | Very High .8 |
| Cost | Insignificant Cost Increase | <5% Cost Increase | 5–10% Cost Increase | 10–20% Cost Increase | >20% Cost Increase |
| Schedule | Insignificant Schedule Slippage | Schedule Slippage <5% | Overall Project Slippage 5–10% | Overall Project Slippage 10–20% | Overall Project Schedule Slips >20% |
| Scope | Scope Decrease Barely Noticeable | Minor Areas of Scope Are Affected | Major Areas of Scope Are Affected | Scope Reduction Unacceptable to the Client | Project End Item Is Effectively Useless |
| Quality | Quality Degradation Barely Noticeable | Only Very Demanding Applications Are Affected | Quality Reduction Requires Client Approval | Quality Reduction Unacceptable to the Client | Project End Item Is Effectively Unusable |

The impacts on project objectives can be assessed on a scale from Very Low to Very High or on a numerical scale.

The numerical (cardinal) scale shown here is non-linear, indicating that the organisation wishes specifically to avoid risks with high and very-high impact.

Appendix 25 - Risk Rating Table

| Level | Descriptor | Description |
| --- | --- | --- |
| E | Extreme | Immediate action required, senior management involvement necessary now. |
| H | High | Action is required in the short term, strategies to treat the risk must be identified. |
| M | Moderate | Responses need to be identified and the risks monitored. |
| L | Low | Monitor by routine procedures. |

| Likelihood | Consequence |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5 |
| A (Almost certain) | High | High | Extreme | Extreme | Extreme |
| B (Likely) | Moderate | High | High | Extreme | Extreme |
| C (Moderate) | Low | Moderate | High | Extreme | Extreme |
| D (Unlikely) | Low | Low | Moderate | High | Extreme |
| E (Rare) | Low | Low | Moderate | High | High |

Hierarchy of Controls

| Elimination | Most effective. |
| --- | --- |
| Substitution | Use something else or a less hazardous process. |
| Isolation | Use barriers to shield or isolate the hazard. |
| Engineering Control | Design and install equipment to counteract the hazard. |
| Administrative Control | Arrange work to reduce exposure to the hazard and provide training and assessment. |
| Personal Protective Equipment | Wear PPE while exposed to the hazard – Least effective. |

Appendix 26 - Risk Brainstorming Session Worksheet

Project Name: 11 Balfour st backyard makeover project

Prepared by: Nigel phillips

Date: 30-05-2021

Session Facilitator: Nigel phillips

Title/Position: Project manager

Participating Group: - Stan peters – bricklayer - Fred Butt – director WSP - Steven Adamson – sponsor husband (additional labour ) - Stan peters – bricklayer contractor - Nigel phillips- PM for WSP

| Identified Risk | Probability of | Potential | Inherent Risk | Controls to be used on risk | Residual Risk | Proposed Actions | Identified by Whom? | Who is responsible? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Occurrence | Impact | Rating |  | Rating |  |  |  |
| Delay in the supply of materials | E | 4 | High | Admin : quotes and constant contact with suppliers | Mod | Nigel to inform Fred of any changes And source different suppliers or negotiate better pricing | Fred | Nigel |
| Existing Underground utilities not being identified or installed correctly | E | 3 | MOD. | Admin : ensure all plans of existing is supplied | MOD. | Nigel and Steven to familiarize themselves with existing plans, services , and standards & closely supervise any digging work on site | Nigel | Nigel |
| Time frames not being correctly communicated | C | 3 | High | Constantly keep in contact with supplires , contractors & delivery companies | Mod | Nigel to inform Fred of any delays | Stan | Nigel |
| Project manager leaving the company | C | 3 | High | Constantly keep in contact with suppliers and check on supply | Low | Fred to Advertise for position immediately as soon as they hand in their notice | steve | Fred |
| Injury to staff on site | D | 4 | High | Ensure all person on site are inducted and understand site specific risks | Mod | A daily risk assessment has to be undertaken prior to starting work by all person on site | Steven | Nigel |
| Supply of additional labour (Steven Adamson) | E | 3 | Mod | Ensure steven understands what is required and when closely supervise steven -Nigel | Low | Nigel to check stevens workflow and availability weekly And plan accordingly , if delays are going to occur fred will need to contacted | Stan | Nigel |
| Council requiring approval | E | 3 | Mod | Check council does not need approval prior to starting | Low | Contact council if rules change and Fred to adjust contract to suit | Fred | FRED |
| Cost increase in materials | C | 3 | High | Regular contact with suppliers get quotes of supplies for the date required | Mod | regular contact with supplies at least 1 month before and then 1 week before any cost increases to passed on to fred butt and then the sponsor –Nigel | Fred | Nigel |
| Adverse weather conditions | B | 2 | High | Plan other things that can be done Under cover & ensure weather sensitive tasks are | Mod | , keep an eye on weather forecasts inform Fred if delays are likely | Nigel | Nigel |
| Availability of subcontractors when needed | C | 2 | Mod | Ensure contractors have a schedule of the proposed dates | MOD | regular contact with contractors at least 1 month before and then 1 week before to ensure availability | Fred | Nigel |

Appendix 27 - Project Risk Categorisation Worksheet

Project Name: 11 Balfour st backyard makeover project

Prepared by: Nigel phillips

Date: 30-05-2021

NOTE: List all identified project risks within each category. Retain this information for reference throughout the risk management process:

Technical, quality, or performance risks—such as reliance on unproven or complex technology, unrealistic performance goals, changes to the technology used or to industry standards during the project. - Delay in the supply of materials - Existing Underground utilities not being identified or installed correctly

Project-management risks—such as poor allocation of time and resources, inadequate quality of the project plan, poor use of project management disciplines. - Time frames not being correctly communicated to sub-contractors, Steven Adamson and suppliers

Organisational risks—such as cost, time, and scope objectives that are internally inconsistent, lack of prioritisation of projects, inadequacy or interruption of funding, and resource conflicts with other projects in the organisation. - Project manager leaving the company - Injury to staff on site

External risks—such as shifting legal or regulatory environment, labour issues, changing owner priorities, country risk, and weather. Force majeure risks such as earthquakes, floods, and civil unrest generally require disaster recovery actions rather than risk management. - Supply of additional labour - Council requiring approval - Delays in the supply materials - Availability of subcontractors when needed - Adverse weather conditions

Appendix 28 - Project Risk Prioritisation Worksheet

Project Name: 11 Balfour st backyard makeover project

Prepared by: Nigel phillips

Date: 30-05-2021

By Rank:

| Identified Risk | Low Risk (Check √) | Medium Risk (Check √) | High Risk (Check √) | Work Breakdown Structure Level |
| --- | --- | --- | --- | --- |
| Delay in the supply of materials |  | X |  | All phases |
| Existing Underground utilities not being identified or installed correctly |  | x |  | All phases |
| Time frames not being correctly communicated |  | x |  | All phases |
| Project manager leaving the company | x |  |  | All phases |
| Injury to staff on site |  | x |  | All phases |
| Supply of additional labour | x |  |  | All phases |
| Council requiring approval | x |  |  | All phases |
| Cost increase in materials |  | x |  | All phases |
| Adverse weather conditions |  | x |  | All phases |
| Availability of subcontractors when needed |  | x |  | All phases |

By Required Response:

| Identified Risk | Can Be Handled Later (specify planned response) | Requires Immediate Response! (specify planned actions and who is assigned responsibility) |
| --- | --- | --- |
| Delay in the supply of materials | Contact the supplier at least 2 week prior to delivery and also each month before month before -Nigel | Nigel to inform Fred of any changes And source different suppliers or negotiate better pricing |
| Adverse weather conditions | Plan other things that can be done Under cover & ensure weather sensitive tasks are | , keep an eye on weather forecasts inform Fred if delays are likely -NIGEL |
| Existing Underground utilities not being identified or installed correctly | Closely monitor project and subcontractors and report to Fred if any major issues | Nigel and Steven to familiarize themselves with existing plans, services , and standards & closely supervise any digging work on site |
| Time frames not being correctly communicated |  | Closely liaise with all contractors and suppliers weekly - NIGEL |
| Injury to staff on site | Ensure all person on site are inducted and understand site specific risks | A daily risk assessment has to be undertaken prior to starting work by all person on site |
| Project manager leaving the company | Advertise for position immediately as soon as they hand in their notice | Ensure Pm is happy and not stressed, keep in contact and see how he is performing - FRED |
| Supply of additional labour (labour supplied by steven Adamson) | Keep in contact with steven to ensure he knows when he needs to work | Ensure steven understands what is required and when closely supervise steven -Nigel |
| Council requiring approval |  | Contact council if rules change and Fred to adjust contract to suit -Fred |
| Cost increase in materials | Regular contact with suppliers get quotes of supplies for the date required | regular contact with supplies at least 1 month before and then 1 week before any cost increases to passed on to fred butt and then the sponsor –Nigel |
| Availability of subcontractors when needed | Ensure contractors have a schedule of the proposed dates | regular contact with contractors at least 1 month before and then 1 week before to ensure avalabilty |

By Area of Expected Impact:

| Area of Impact | Identified Risks affecting this area | Level of Risk: High, Medium, Low | Basis for High-Risk Assessments |
| --- | --- | --- | --- |
| Cost | - Cost increase in materials - Adverse weather conditions - Supply of additional labour | Medium |  |
| Schedule | - Delay in the supply of materials - Adverse weather conditions - Time frames not being correctly communicated | Medium |  |
| Quality | - Adverse weather conditions - Project manager leaving the company - Existing Underground utilities not being identified or installed correctly | Medium |  |
| Functionality | - Council requiring approval - Availability of subcontractors when needed - Existing Underground utilities not being identified or installed correctly | Medium |  |

Appendix 29 - Risk Response Plan

Project Name: 11 Balfour st backyard makeover project

Prepared by: Nigel Phillips

Date: 30-05 02021

Description of Risk Identified: Adverse weather conditions

Person(s) Responsible: Nigel phillips

Results from Risk Analysis: Delay in project as most work is outside

Agreed Responses (avoidance, transference, mitigation, acceptance):

Response #1: acceptance: due to the long time frame of the project and most work being outside, delays and reschedules will happen, by monitoring the predicted weather, weather sensitive stages can be organized to avoid rework , owner have under cover area that can be used to prep timbers etc in bad weather

Response #2: mitigation, have weather protected pop up covers if schedule require work to be done

Residual Risk Level: High loss of time and the possibility of rework for item that sound not get wet till sealed

Action Steps: - Plan around weather forecasts (the area has on average 280 sun days per year) ensure critical tasks are planed for the sun days - Ensure owners are ok with using undercover are to do prep work ‘ - Ensure rain proof shelters are available (could also be used as sun shelters)

Budget & Time for Response: nil

Contingency/Fallback Plans: Should rain affect the project: - The project manager (nigel)to inform the director of WSP of the delays - The WSP director to liaise with sponsors to organize an extension of time if needed - Ensure all materials left on site can be left in the weather, and if not, they are covers to prevent damage each day.

Appendix 30 - Workaround Planning Worksheet Template

Project Name: 11 Balfour st backyard makeover project

Prepared by:

Date:

Description of Emerging Risk Identified:

Person(s) Responsible:

Results from Risk Analysis (if applicable):

Description of Plan to Respond (avoidance, transference, mitigation, acceptance):

Description of Residual Risk Level:

Action Steps:

Budget & Time for Response:

Contingency/Fallback Plans:

Additional Notes:

Appendix 31 - Project Risk Review Matrix

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: Nigel Phillips |  |  |  |  |  |
| Date: 21-11-2021 |  |  |  |  |  |
| Meeting Date: 21-11-2021 |  |  |  |  |  |
| Purpose of Meeting: review of project at about half way |  |  |  |  |  |
| CHANGES IN RISK FACTORS: Notes |  |  |  |  |  |
| Identified Risk |  | Changes in Probability of Occurrence | Changes in Priority | Changes in Ownership/ Responsibility | Changes in Needed Response |
| Delay in the supply of materials |  | nil | nil | nil | nil |
| Existing Underground utilities not being identified or installed correctly |  | Change from E to C | nil | Nil(as nigel is a licenced &qualified electrician | Electrical conduits to be installed and connected to comply with standards (nigel), extra cost to be requested (Fred) |
| Time frames not being correctly communicated |  | nil | nil | nil | nil |
| Project manager leaving the company |  | nil | nil | nil | nil |
| Injury to staff on site |  | nil | nil | nil | nil |
| Supply of additional labour |  | Change from E to C | nil | nil | nil |
| Council requiring approval |  | nil | nil | nil | nil |
| Cost increase in materials |  | Change from C to A | nil | FRED & Nigel (Building boom has caused cost increase | FRED & Nigel to contact other suppliers at see if there is an alternative |
| Adverse weather conditions |  | nil | nil | nil | nil |
| Availability of subcontractors when needed |  | nil | nil | nil | Nil |

Additional Notes/Comments/Agreements/Next Steps:  Steven Adamson has to work more days away and has said that it should not affect the project  but not sure , also the sponsors want lights and power installed

Appendix 32 - Statement of Work – mini dig

Project Name: 11 Balfour st backyard makeover project

Prepared by:

Date:

Vendor Name:

Description of Deliverables or Procurement Items (in as much detail as needed to accurately define the proposed work):

Required Timeline and Milestone Dates:

Collateral Services Required of Vendor (e.g., performance reporting, post-project operational support, etc.):

Cost Parameters:

Appendix 33 - Statement of Work – mini dig

Project Name: 11 Balfour st backyard makeover project

Prepared by:

Date:

Vendor Name:

Description of Deliverables or Procurement Items (in as much detail as needed to accurately define the proposed work):

Required Timeline and Milestone Dates:

Collateral Services Required of Vendor (e.g., performance reporting, post-project operational support, etc.):

Cost Parameters:

Appendix 34 - Procurement Management Planning Checklist Template

| Project Name: 11 Balfour st backyard makeover project |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| Date: |  |  |
| Identify types of contracts being used: |  |  |
| Independent estimates required? | Yes | No |
| If Yes, who will prepare? |  |  |
| By when? |  |  |
| Actions that Project Management Team can take independent of Procurement Department: |  |  |
| Source of standardized procurement documents, if needed: |  |  |
| How will multiple providers be managed? |  |  |
| How will you coordinate Procurement with the following aspects of the project? |  |  |
| Scheduling |  |  |
| Performance Reporting |  |  |
| Human Resources |  |  |
| Other |  |  |

Appendix 35 - Work Authorisation Form Template

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| Date: |  |  |  |  |
| Specific Activity or Work Package: |  |  |  |  |
| The commencement of the above Project Activity or Work Package is hereby authorised, to begin on: |  |  |  |  |
| Remarks or special issues to be addressed: |  |  |  |  |
| Authorising Person(s): |  |  |  |  |
| Name: | Title: |  | Date: |  |
| Name: | Title: |  | Date: |  |
| Person(s) receiving this authorisation form: |  |  |  |  |
| Name: | Title: | Date: |  | Rec'd (initial): |
| Name: | Title: | Date: |  | Rec'd (initial): |
| Name: | Title: | Date: |  | Rec'd (initial): |

Appendix 36 - Quality Audit Template

| Project Name: 11 Balfour st backyard makeover project |  |  |  |
| --- | --- | --- | --- |
| Prepared by: |  |  |  |
| Date: |  |  |  |
| Project Manager: |  |  |  |
| Project Phase: | Overall Project Status: |  |  |
| Audit Date: | Audit Number: |  | Audit Leader: |
| Audit Team: |  |  |  |
| Goal(s) of This Specific Audit: |  |  |  |
| Audit of Management of Project: |  |  |  |
| 1. (required project objective #1) |  | Assessment: | Comment: |
| 2. (required project objective #2) |  | Assessment: | Comment: |
| 3. (required project objective #3) |  | Assessment: | Comment: |
| 4. (required project objective #4) |  | Assessment: | Comment: |
| n. (required project objective #n) |  | Assessment: | Comment: |
| Overall Assessment of Management of Project: |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. 2. 3. |  |  |  |

Appendix 37 - Change Register

| Request No. | Date | Originator | Brief Description | Responsibility | Time frame | Completed |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 20-11-21 | Mary Stevenson | Extra lights and power outlet | Nigel Phillips |  |  |

Appendix 38 - Project Change Request Template And completed change requests

Change request 1

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Prepared by: Nigel phillips |  |  |  |  |  |  |  |  |  |  |  |
| Date: 20-11-2021 |  |  |  |  |  |  |  |  |  |  |  |
| Changes are being made to the following: |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Project Charter |  |  |  |  | Project Management Approach |  |  |  |  |
|  |  | Scope Statement |  |  |  |  | Work Breakdown Structure |  |  |  |  |
|  |  | Performance Measurement Baselines |  |  |  |  | Major Milestones and Target Dates |  |  |  |  |
|  |  | Key Staff |  |  |  |  | Risk Management Plan |  |  |  |  |
| X |  | Scope Management Plan |  |  | X |  | Schedule Management Plan |  |  |  |  |
| X |  | Cost Management Plan |  |  |  |  | Quality Management Plan |  |  |  |  |
|  |  | Staffing Management Plan |  |  |  |  | Communications Management Plan |  |  |  |  |
|  |  | Risk Response Plan |  |  |  |  | Procurement Management Plan |  |  |  |  |
| Type of change: |  |  |  |  |  |  |  |  |  |  |  |
| X | Scope |  | X | Time |  |  |  | Cost |  | Quality |  |
|  | Communications |  |  | Resources |  |  |  | Risk |  | Procurement |  |
| Areas impacted: |  |  |  |  |  |  |  |  |  |  |  |
|  | Scope |  |  | Time |  | X |  | Cost |  | Quality |  |
|  | Communications |  |  | Resources |  |  |  | Risk |  | Procurement |  |
| Changes to Supporting Detail? (explain): Mary Adamson has decided that she would like lighting and a poweroutlet. This will require nigel to work and extra day and will need extra materials |  |  |  |  |  |  |  |  |  |  |  |
| Description of Changes being made: 1. Risk Issues Prompting Changes: extra time to install lights already on a tight schedule Corrective Action: nigel to work 1 Saturday |  |  |  |  |  |  |  |  |  |  |  |
| Stakeholders being notified: |  |  |  |  |  |  |  |  |  |  |  |
| Name/Title: Mary Adamson (sponsor) |  |  |  |  |  | Signature: |  |  |  |  | Date:20-11-2021 |
| Name/Title: Fred Butt (WSP) |  |  |  |  |  | Signature: |  |  |  |  | Date:20-11-2021 |

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |  |
| Changes are being made to the following: |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Project Charter |  |  |  |  | Project Management Approach |  |  |  |  |
|  |  | Scope Statement |  |  |  |  | Work Breakdown Structure |  |  |  |  |
|  |  | Performance Measurement Baselines |  |  |  |  | Major Milestones and Target Dates |  |  |  |  |
|  |  | Key Staff |  |  |  |  | Risk Management Plan |  |  |  |  |
|  |  | Scope Management Plan |  |  |  |  | Schedule Management Plan |  |  |  |  |
|  |  | Cost Management Plan |  |  |  |  | Quality Management Plan |  |  |  |  |
|  |  | Staffing Management Plan |  |  |  |  | Communications Management Plan |  |  |  |  |
|  |  | Risk Response Plan |  |  |  |  | Procurement Management Plan |  |  |  |  |
| Type of change: |  |  |  |  |  |  |  |  |  |  |  |
|  | Scope |  |  | Time |  |  |  | Cost |  | Quality |  |
|  | Communications |  |  | Resources |  |  |  | Risk |  | Procurement |  |
| Areas impacted: |  |  |  |  |  |  |  |  |  |  |  |
|  | Scope |  |  | Time |  |  |  | Cost |  | Quality |  |
|  | Communications |  |  | Resources |  |  |  | Risk |  | Procurement |  |
| Changes to Supporting Detail? (explain): |  |  |  |  |  |  |  |  |  |  |  |
| Description of Changes being made: 1. Risk Issues Prompting Changes: Corrective Action: |  |  |  |  |  |  |  |  |  |  |  |
| 2.Risk Issues Prompting Changes: Corrective Ation: |  |  |  |  |  |  |  |  |  |  |  |
| 3.Risk Issues Prompting Changes: Corrective Action: |  |  |  |  |  |  |  |  |  |  |  |
| Stakeholders being notified: |  |  |  |  |  |  |  |  |  |  |  |
| Name/Title: |  |  |  |  |  | Signature: |  |  |  |  | Date: |
| Name/Title: |  |  |  |  |  | Signature: |  |  |  |  | Date: |
| Name/Title: |  |  |  |  |  | Signature: |  |  |  |  | Date: |

Appendix 39 - Project Status Report Template

| Project Name: 11 Balfour st backyard makeover project |  |  |  |
| --- | --- | --- | --- |
| Prepared by: |  |  |  |
| Date: |  |  |  |
| Status of Project Relative to Project Objectives: |  |  |  |
| Scope (On scope? If off scope, how serious?): |  |  |  |
| Schedule (On schedule? Ahead or behind by how much, etc.): |  |  |  |
| Cost (On budget? Under or over by how much, etc.): |  |  |  |
| Quality: |  |  |  |
| Communications: |  |  |  |
| HR: |  |  |  |
| Risk: |  |  |  |
| Procurement: |  |  |  |
| Integration: |  |  |  |
| Progress Report: (what is completed, what is in process, key changes made, when and why, etc.) |  |  |  |
| Forecasting: (estimate of future project status and progress) |  |  |  |
| Other issues or comments: |  |  |  |
| Issue: |  | Who Will Address: |  |
| Project Report Submitted to: |  |  |  |
| Name: | Title: |  | Date: |
| Name: | Title: |  | Date: |
| Name: | Title: |  | Date: |

Appendix 40 - Work Results Guidelines

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |
| Date: |  |  |  |  |  |
| Deliverable #1 |  |  |  |  |  |
| Completed as of Scheduled Date: |  |  |  |  |  |
| Not completed as of Scheduled Date: |  |  |  |  |  |
| Reason, if not completed |  |  |  |  |  |
| Quality Standards: |  | Met |  | Not Met |  |
| Quality Issues |  |  |  |  |  |
| Costs Incurred |  |  |  |  |  |
| On Budget | Under Budget by |  |  |  | Over Budget by |
| Additional Remarks: |  |  |  |  |  |
| Deliverable #2 |  |  |  |  |  |
| Completed as of Scheduled Date: |  |  |  |  |  |
| Not completed as of Scheduled Date: |  |  |  |  |  |
| Reason, if not completed |  |  |  |  |  |
| Quality Standards: |  | Met |  | Not Met |  |
| Quality Issues |  |  |  |  |  |
| Costs Incurred |  |  |  |  |  |
| On Budget | Under Budget by |  |  |  | Over Budget by |
| Additional Remarks: |  |  |  |  |  |
| Reported by |  |  | Date |  |  |

Appendix 41 - Lessons Learned Documentation Template

| Project Name: 11 Balfour st backyard makeover project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Number: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group:* |  |  |  | Initiating |  | Planning |  | Executing |  |  |  | Controlling |  |  |  | Closing |  |  |  |  |
| Specific Project Management Process Being Used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific Practice, Tool or Technique Being Used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the action undertaken? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific Lesson Learned? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used in a future project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learned: (check one) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Executive(s) |  |  |  | Project Manager(s) |  |  |  | Project Team(s) |  |  |  |  |  |  | All Staff |  |  |  |
|  |  | Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learned be disseminated? (check all that apply) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | e-mail |  |  |  | Intranet/Web site |  |  |  | Tip Sheet/FAQ |  |  |  |  |  |  |  | Library |  |  |
|  |  | Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Have you attached reference(s), example(s) and/or additional material(s)? |  |  |  |  |  |  |  |  |  |  |  |  |  | yes |  |  |  |  |  | no |
| Name(s) of attachment(s): 1. 2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Appendix 42 - Project Completion Report Template

| Project Name: 11 Balfour st backyard makeover project |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| Date: |  |  |
| Project Summary |  |  |
| Scope (what was included and excluded: |  |  |
| Cost (Budget vrs actual): |  |  |
| Time (Estimate vrs Actual): |  |  |
| Project Report Submitted to: |  |  |
| Name: | Title: | Date: |
| Name: | Title: | Date: |
| Name: | Title: | Date: |

Appendix 43 - Formal Acceptance and Closure Template

| Project Name: 11 Balfour st backyard makeover project |  |
| --- | --- |
| Prepared by: |  |
| Date: |  |
| Name of Client or Sponsor: |  |
| Statement of Formal Acceptance: |  |
| The undersigned formally accept as complete the above-identified project, and do hereby state that this project, project phase, or major deliverable meets or exceeds agreed-upon performance standards for scope, quality, schedule, and cost, and state that we have seen documentation that all relevant legal and regulatory requirements have been met or exceeded. |  |
| Additional Remarks: |  |
| Accepted by (name of client, sponsor, or other official) | Date |
| Accepted by (name of client, sponsor, or other official) | Date |
| Accepted by (name of client, sponsor, or other official) | Date |
| Signed form distributed to: |  |
| Stakeholder name | Date |
| Stakeholder name | Date |
| Stakeholder name | Date |

Appendix 44 - Project Archives Checklist Template

Project Name: 11 Balfour st backyard makeover project

Prepared by:

Date:

|  | Project Documents Located: | Indexed | Submitted for Archives | Date | Comments | Initials |
| --- | --- | --- | --- | --- | --- | --- |