## Original Jobpac Budget
Coded Budget | $ Amount | Cost Code | Cost Type | QS Submitted | Gain/Loss
BULK EARTHWORKS | 201242 | T06 | ST | yes | 340
PILING | 1349563 | T08 | ST | yes | 5118.02
TERMITE TREATMENT | 8580 | T091TT | ST |  | 8580
DETAILED EXCAVATION | 91545 | T06DE | ST
CONCRETE SUPPLY | 538076 | T091 | MT |  | -91237
CONCRETE LABOUR | 529368 | T091 | ST |  | -12432.75
CONCRETE PUMPING | 143597 | T091PU | XP |  | -10000
CONCRETE TESTING & SUNDRIES | 62421 | T091T | MT
REINFORCEMENT SUPPLY | 727261 | TO92 | MT | yes | -143431
REINFORCEMENT PLACING | 214152 | T092 | ST |  | -65000
12 - POST TENSIONING | 0
FORMWORK | 994001 | T093 | ST | yes | -251929
14 - PRECAST CONCRETE | 0
MASONRY - BLOCKWORK | 1817765 | T11 | ST |  | -35000
16 - MASONRY - BRICK | 0
WATERPROOFING & TANKING | 256310 | T15 | ST
STRUCTURAL STEEL | 176000 | T12 | ST
ROOFING | 255327 | T14 | ST |  | -30000
ROOF ACCESS & SAFETY | 28265 | T14RS | ST
ALUMINIUM WINDOWS & DOORS | 1189248 | T17 | ST
22 - BALUSTRADES | 0
23 - TIMBER WINDOWS & DOORS | 0
METALWORK | 646695 | T13 | ST
RUBBISH/LAUNDRY CHUTE SYSTEM | 20530 | T13RC | ST
SCREENS, AWNINGS & FAÇADE ELEMENTS | 0
ROLLER DOORS | 5697 | T18RD | ST
28 - OPERABLE WALLS | 0
CARPENTRY - MISCELLANEOUS | 124888 | T16 | ST
TRUSSES | 196190 | T16TT | ST
TIMBER DOORS & FRAMES | 252679 | T18 | ST
DOOR & SUNDRY HARDWARE | 144710 | T18 | MT
CEILINGS & PARTITIONS | 3016797 | T19 | ST |  | -180000
TOILET PARTITIONS | 1557 | 19TP | ST | [10 empty] | 4104531
TILING SUPPLY | 155550 | T23 | MT | [10 empty] | 139640
TILING INSTALL | 383457 | T23 | ST |  |  |  | ` | [6 empty] | 25560286
CLADDING | 64499 | T23C | ST | [10 empty] | 867000
FLOOR COVERINGS | 1057328 | T22 | ST | [10 empty] | 30671457
JOINERY & BENCHTOPS | 1497650 | T20 | ST | [10 empty] | 75000
STAINLESS STEEL | 281266 | T21 | ST | [10 empty] | 30746457
COMMERCIAL LAUNDRY & EQUIPMENT
41 - APPLIANCES | 0
HYDRAULIC SERVICES | 2420741 | T25 | ST | yes | 1907 |  |  | was this | should be this CORRECT* | Revised MP Confirmation | Final Difference
SANITARY HARDWARE/HYDRAULIC FFE | 735256 | T25HF | MT |  |  |  | margin | 3520943 | 3507943 | 3108400 | 399543
ELECTRICAL SERVICES | 2186001 | T26 | ST | yes | -112500 |  | base costs | 24334019 | 24347019 | 24535540.5 | -188521.5 | 13000 | moved from design fees to trade contingency
NURSE CALL (Provisonal Sum) | [6 empty] | prelims | 4104531 | 4104531 | 4315552.5 | -211021.5 | 22500 | went to BG figure
MECHANICAL SERVICES | 1556200 | T27 | ST |  |  |  | joinery | 1497651 | 1497651 | 1497651 | 0
FIRE SERVICES | 618960 | T29 | ST | yes | 4960 |  | pc fixtures | 735256 | 735256 | 735256 | 0 |  |  |  | 4104531
LIFT SERVICES | 363688 | T28 | ST |  |  |  | development fees | 75000 | 75000 | 75000 | 0 |  |  |  | 139640
LANDSCAPING | 428931 | T30 | ST |  |  |  | contract figure | 34267400 | 34267400 | 34267400 | 0 |  |  |  | 25560286
PAINTING | 496356 | T24 | ST | [11 empty] | 867000
RENDER | 283729 | T24R | ST
SIGNAGE | 38210 | T32 | ST | [11 empty] | 3520943
TRADE CONTINGENCY | 201521.5 | T98 | ST |  | 201521.5
DESIGN FEES | 139640 | D1 | [12 empty] | 75000
PROVISIONAL SUMS | 867000 | T99 | [12 empty] | 34267400
SUB TOTAL TRADE COSTS | 26768447.5 |  |  |  | -709103.23 |  | 34267400 |  |  |  | 188521.5
SUBTOTAL PRELIMINARIES | 4315552.5
DEVELOPMENT FEES |  | D2
Development Management Fee | 75000
Margin | 3108400 |  |  |  |  | 9.071%
TOTAL (EXCLUDING GST) | 34267400 | [9 empty] | 34267400
75000
Prov Sums Breakdown | [10 empty] | 34192400
Corporate Signage | 35000 | T9901 | ST
Wayfinding Signage | 30000 | T9902 | ST
Corner and Door Protection | 30000 | T9903 | ST
Reception, Hairsalon and Private Dining Stonework | 22000 | T9904 | ST
Nurse Call, Electronic Access Control and Security Cameras | 600000 | T9905 | ST
Interior Designer Lounge Screens inc. Option2 as a Prov Sum | 50000 | T9906 | ST
Metalwork AL1 Design Rationalisation | 100000 | T9907 | ST
| 867000 | (sanity check)
Design Fees Breakdown
Web FM | 24875 | D1WF | CT
Landscaping | 7415 | D1LD | CT
Civil Engineer | 11300 | D1CE | CT
Traffic Engineer | 5500 | D1TM | CT
Acoustic Engineer | 6950 | D1AE | CT
Structural Engineer | 32600 | D1SE | CT
NCC/ Section J/ JV3 | 6500 | D1NC | CT
Fire Engineer | 5000 | D1FE | CT
Building Certifier |  | D1BC | CT |  | 13000 ddt post tender
Hydraulic Engineer | 1000 | D1HE | CT
Fire Services | 1000 | D1FS | CT
Mechanical Engineer | 1000 | D1ME | CT
Electrical/ VT Engineer | 1000 | D1EE | CT
Specialist Lighting | 1000 | D1SL | CT
Kitchen and Laundry Specialist | 8000 | D1KS | CT
Waste Management Consultant | 3500 | D1WM | CT
Access Consultant | 500 | D1A | CT
HV Electrical Engineer | 7500 | D1HV | CT
Façade (Compliance Peer Review) | 7500 | D1F | CT
Survey | 3000 | D1SU | CT
Structural Peer Review | 4500 | D1SP | CT
| 139640 | (sanity check)
Preliminaries Breakdown
PROJECT WAGES |  | P10
Building Cadet | 120916 | P10BC | LW
Project Manager | 338580 | P10PM | LW
Contracts Administrator | 218556 | P10CA | LW
Contracts Administrator - Procurement | 37392 | P10CA1 | LW
Estimator/ Cost Planner | 5563.2 | P10ES | LW
HSEQ Co-Ordinator | 44232 | P10HS | LW
Site Manager | 287432 | P10SM | LW
Foreman - Structure/ Façade | 193648 | P10FM | LW
Foreman - Fitout | 126616 | P10FM1 | LW
Foreman - Fitout | 126616 | P10FM2 | LW
HSE Advisor | 193192 | P10WH | LW
Site Labourer | 126480 | P10SL | LW
External Labour Hire | 85680 | P10SL | ST
CONTRACT PRELIMINARIES |  | P01
Contract Works Insurance | 82800 | PO1CW | PF
Bank Gaurantee Fees | 45000 | P01BG | PF |  |  | was $22500 and amended with Matt P last negotiation
CONSULTANTS |  | P02
Geotechnical Consultant | 2500 | PO2GO | CT
TEMPORARY SERVICES |  | P03
Temporary Sewer & Water Connection | 13700 | PO3TS | OT
Temporary Electricity | 25250 | P03TE | OT
Fire Extinguishers | 7500 | P03FE | OT
SITE PRELIMINARIES |  | P04
Dilap Report Subcontract | 1500 | P04DI | ST
Temporary Fencing | 4987 | P04TF | XP
Temporary Signage & Banners | 5000 | P04TS | MT
Temporary Roads | 5218 | P04TR | MT
Temporary Harstanding | 31311 | P04HS | MT
Site Expenses | 15500 | PO4SE | MT
AMENITIES & SITE SETUP |  | P05
Office Sheds & Furnishings | 138902 | P05OS | MT
Site Communications | 13376 | PO5SC | MT
Temporary Electricity | 40550 | PO5TE | MT
Temporary Lighting | 16876 | P05TL | OT
Temporary Water | 17700 | PO5TW | MT
Covered Areas & Walkways | 12500 | PO5CA | MT
Traffic Control | 54597 | PO5TT | ST
Traffic Management Signage | 1860 | PO5TM | MT
OFFICE SUPPLIES AND MARKETING |  | P06
Stationary and Office Supplies | 9300 | PO6 | OT
SITE EQUIPMENT |  | P07
McNab Equipment Hire | 69610 | PO7 | IP
Dewatering | 2050 | PO7 | MT
Small Tools | 24800 | PO7 | XP
WH&S |  | P08
Site Safety Equipment | 9400 | PO8 | MT
Surveyor | 52500 | P12 | ST
External Scaffolding Hire | 539663 | P13ES | XP
Mobile Crane Hire | 45075 | P14MC | XP
Cranes, Gantries & Hoists | 649485 | P14TC | ST
Cleaning | 72788 | P15 | ST
Final Clean | 109190 | P15FC | ST
Bin Hire | 101640 | P15 | XP
PRELIM CONTINGENCY |  | P99
Prelim Contingency | 188521.5 | P99 | ST
| 4315552.7 | (sanity check)

## Budget Transfers
Budget From |  |  |  | $ Amount | Budget To
PILING | 1349563 | T08 | ST | 119244 | BULK EARTHWORKS | 201242 | T06 | ST |  | transferred | Forecast Checked
Temporary Harstanding | 31311 | P04HS | MT | 31311 | BULK EARTHWORKS | 201242 | T06 | ST |  | transferred | Forecast Checked
Temporary Roads | 5218 | P04TR | MT | 5218 | BULK EARTHWORKS | 201242 | T06 | ST |  | transferred | Forecast Checked
DETAILED EXCAVATION | 91545 | T06DE | ST | 41470 | CONCRETE LABOUR | 529368 | T091 | ST |  | transferred | Forecast Checked
CONCRETE TESTING & SUNDRIES | 62421 | T091T | MT | 41448 | CONCRETE SUPPLY | 538076 | T091 | MT |  | transferred | Forecast Checked
METALWORK | 646695 | T13 | ST | 107000 | FORMWORK | 994001 | T093 | ST |  | transferred | Forecast Checked
JOINERY & BENCHTOPS | 1497650 | T20 | ST | 86597 | CEILINGS & PARTITIONS | 3016797 | T19 | ST |  | transferred | Forecast Checked
LIFT SERVICES | 363688 | T28 | ST | 12000 | External Scaffolding Hire | 539663 | P13ES | XP |  | transferred | Forecast Checked
Cranes, Gantries & Hoists | 649485 | P14TC | ST | 32500 | CONCRETE LABOUR | 529368 | T091 | ST |  | transferred | Forecast Checked
CONCRETE LABOUR | 529368 | T091 | ST | 32500 | Cranes, Gantries & Hoists | 649485 | P14TC | ST |  | transferred | Forecast Checked
PILING | 1349563 | T08 | ST | 22200 | CONCRETE SUPPLY | 538076 | T091 | MT |  | transferred | Forecast Checked
DETAILED EXCAVATION | 91545 | T06DE | ST | 4571.87 | BULK EARTHWORKS | 201242 | T06 | ST |  | transferred | Forecast Checked
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 55959 | PERMANENT FORMWORK | 0 | T094 | MT |  | transferred | Forecast Checked
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 37059 | PERMANENT FORMWORK | 0 | T094 | ST |  | transferred | Forecast Checked
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 24622 | CONCRETE SUPPLY | 538076 | T091 | MT |  | transferred | Forecast Checked
PERMANENT FORMWORK | 0 | T094 | MT | 1 | MASONRY - BLOCKWORK | 1817765 | T11 | ST |  | transferred | Forecast Checked
HYDRAULICS | 2420741 | T25 | ST | 28434 | GLAZING | 1189248 | T17 | ST | drains | transferred | Forecast Checked
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 64092 | PERMANENT FORMWORK | 0 | T094 | MT | AFS Supply
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 5386 | PERMANENT FORMWORK | 0 | T094 | ST | AFS Revised Install Extra over
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 3362 | CONCRETE SUPPLY | 538076 | T091 | MT
PERMANENT FORMWORK | 0 | T094 | MT | 55959 | MASONRY - BLOCKWORK | 1817765 | T11 | ST
REINFORCEMENT SUPPLY | 727261 | TO92 | MT | 725261 | REINFORCEMENT SUPPLY | 727261 | T092 | MT
BULK EARTHWORKS | 201242 | T06 | ST | 5218 | Temporary Roads | 5218 | P04TR | MT | temp roads prelim amount back to prelims
DETAILED EXCAVATION | 91545 | T06DE | ST | 4345 | CONCRETE LABOUR | 529368 | T091 | ST | Blinder excavation works
METALWORK | 646695 | T13 | ST | 1891 | FORMWORK | 994001 | T093 | ST
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 242295.2 | REINFORCEMENT SUPPLY | 727261 | T092 | MT | Blockwork Reo | transferred | Forecast Checked
BULK EARTHWORKS | 201242 | T06 | ST | 31311 | Temporary Harstanding | 31311 | P04HS | MT
External Scaffolding Hire | 539663 | P13ES | XP | 12000 | LIFT SERVICES | 363688 | T28 | ST
Temporary Sewer & Water Connection | 13700 | PO3TS | OT | 13700 | Temporary Water | 17700 | PO5TW | MT
STRUCTURAL STEEL | 176000 | T12 | ST | 90000 | CEILINGS & PARTITIONS | 3016797 | T19 | ST |  | transferred | Forecast Checked
Temporary Lighting | 16876 | P05TL | OT | 16876 | Site Safety Equipment | 9400 | PO8 | MT
CEILINGS & PARTITIONS | 3016797 | T19 | ST | 160000 | CARPENTRY - MISCELLANEOUS | 124888 | T16 | ST | FFE Items and Sanitary hardware
CARPENTRY - MISCELLANEOUS | 124888 | T16 | ST | 15957.72 | CEILINGS & PARTITIONS | 3016797 | T19 | ST | Silicon to Skirting
LANDSCAPING | 428931 | T30 | ST | 75626 | METALWORK | 646695 | T13 | ST | fencing | transferred | Forecast Checked
CONCRETE SUPPLY | 538076 | T091 | MT | 4301 | STRUCTURAL STEEL | 176000 | T12 | ST
REINFORCEMENT SUPPLY | 727261 | T092 | MT | 12146.25 | STRUCTURAL STEEL | 176000 | T12 | ST
MASONRY - BLOCKWORK | 1817765 | T11 | ST | 2900 | STRUCTURAL STEEL | 176000 | T12 | ST
CONCRETE LABOUR | 529368 | T091 | ST | 1770 | STRUCTURAL STEEL | 176000 | T12 | ST
FORMWORK | 994001 | T093 | ST | 13926.4 | STRUCTURAL STEEL | 176000 | T12 | ST
BULK EARTHWORKS | 201242 | T06 | ST | 1499.5 | PAINTING | 496356 | T24 | ST | line marking
FLOOR COVERINGS | 1057328 | T22 | ST | 110889 | TILING INSTALL | 383457 | T23 | ST |  | transferred | Forecast Checked
CLADDING | 64499 | T23C | ST | 52725 | TILING INSTALL | 383457 | T23 | ST | cladding install
FLOOR COVERINGS | 1057328 | T22 | ST | 15000 | PAINTING | 496356 | T24 | ST |  | transferred | Forecast Checked
CARPENTRY - MISCELLANEOUS | 124888 | T16 | ST | 35389.8 | CARPENTRY - MISCELLANEOUS | 124888 | T16 | LW | Self Perform trusses allowance
METALWORK | 646695 | T13 | ST | 7912.77 | LANDSCAPING | 428931 | T30 | ST | chemical cage
McNab Equipment Hire | 69610 | PO7 | IP | 14000 | Generators |  | PO5TE | MT
McNab Equipment Hire | 69610 | PO7 | IP | 17000 | Site Communications | 13376 | PO5SC | MT
Generators |  | PO5TE | MT | 1500 | McNab Equipment Hire | 69610 | PO7 | IP