RIICWM402E

Supervise civil works contractors

ASSESSMENT SUMMARY

The assessment activities for RIICWM402E Supervise civil works contractors cover all aspects of the unit of competency. For Apprentices/Trainees, this includes supervisor completion of the Apprentice/Trainee Record (ATR).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be fair, flexible, valid and reliable. If a Participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a Participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the Participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a Participant does not answer all questions or perform all tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency.

The Trainer/Assessor can provide the Participant with additional information on interpreting the assessment outcomes and guide the Participant’s options. If a Participant is still deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result as per the process in the Student Handbook.

By signing below, the Participant acknowledges:

- They understand the assessment instructions and requirements, and consent to being assessed.

- The work submitted is to be their own work – with the work of/with others needing to be clearly acknowledged and documented.

- They consent to any photo/video recording of their work that occurs during assessment.

| Participant name | Joshua Ferguson |
| --- | --- |
| Participant signature | Joshua Ferguson |

Pre-requisite unit(s) to be achieved and authenticated prior to undertaking assessment

Not applicable

| Task | Date completed | Assessment Results |  |
| --- | --- | --- | --- |
| Theory Exam | Select Date. | Satisfactory | Not Satisfactory |
| Practical Assessment | Select Date. | Satisfactory | Not Satisfactory |
| Outcome for RIICWM402E | Select Date. | Competent | Not Yet Competent |

| Evidence requirements checklist (ticked by assessor and evidence supplied to RTO) |  |
| --- | --- |
| Theory Exam Practical Assessment | Completed team WHS training need Completed job plan |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |

RIICWM402E

Supervise civil works contractors

THEORY EXAM

| Participant name | Joshua Ferguson |
| --- | --- |

FOR THE PARTICIPANT

Instructions

- You will complete written questions as outlined on the following pages. You must attempt all questions and provide enough detail in your responses to demonstrate your knowledge. - It is anticipated that you should complete this assessment within two (2) hours, but additional time may be allowed upon negotiation with the Assessor. - You must complete all questions unassisted by the Assessor or other personnel but may refer to reference material as needed. All questions must be answered correctly for a ‘Satisfactory’ assessment outcome to be awarded. - An oral examination may be allowed under certain circumstances, whereby your answers will be documented by another party. - Any written questions that are incomplete, or not answered satisfactorily will need to be completed again after further training support. - If you answer a question incorrectly but modify your response, put your initials next to the written change (or the Assessor must initial a verbal change).

Resources required

Pen

FOR THE ASSESSOR

Instructions

- Where oral examination has occurred, ensure that this is acknowledged in writing (e.g. FT001 and Assessor Comments) - All questions must be satisfactorily demonstrated by the Participant for a Satisfactory determination (indicated by an Assessor tick to the right of the question). - Assessors are to complete marking in pen of a different colour to the Participant. - If the Participant verbally modifies their response, write in the modified response verbatim and put your initials next to the written change.

ASSESSOR COMMENTS

As necessary, outline: - Details on reattempts, alternative arrangements or reasonable adjustments made. - Where a Participant is deemed ‘Not Satisfactory’, provide recommendations for future training.

What preparation is required to determine a job plan for a contractor?

| Answer | - Defining the Contracts scope and limitation of works - Compliancy requirements for the project - Detailed breakdown of works with in the project/contract - Project schedule - Costs/budget for the works - Site assessments - Communication guidelines - chain of command etc - Prepare safety and environmental plans |  |
| --- | --- | --- |

How will you share emergency response information relevant to the site and various tasks with sub-contractors?

| Answer | - Toolbox talks - Pre-starts - inductions - posters displaying emergency exits, muster points, designated routes - List of first aiders |  |
| --- | --- | --- |

Which on-going risk management procedures do you follow and access when supervising civil work contractors and how do these link to legislative requirements?

| Answer | - Work method statements - Permit to work - Risk assessments - Incident and accident reports - Inspection and audit reports By managing these procedures and the ongoing continuation of using these it helps to make sure you are a maintaining a safe workplace & meeting legislative requirements with in the workplace. |  |
| --- | --- | --- |

What are (1) the objectives of the Environmental Management Plan (EMP) and (2) why should you read this EMP as part of planning the job?

| Answer 1. 2. | Objectives of an EMP are to ensure the project has a plan in place to stay compliant to all environmental policies procedures & legislations By reading and understanding you EMP this will help with planning your day to day works will still ensuring your meeting environmental policies and procedures. This will help eliminate any extra costs due to reworks or having to stop works to rectify issues to comply with your EMP |  |
| --- | --- | --- |

In the general principles of surveying, what is the importance of ‘working from the whole to the part’ (1) when surveying and (2) how this is achieved?

| Answer 1. 2. | To localise the errors and control the accumulation of errors The whole area is surveyed and then broken down into smaller easier defined areas |  |
| --- | --- | --- |

Why is it important to coordinate tasks with other work supervisors and schedule contractor activities?

| Answer | Helps the flow of the project, minimises risks of delays to works, minimise confusion with in the team, helps with allocating resources and costs. |  |
| --- | --- | --- |

What processes must you follow to acquire and confirm the acquisition of, required resources at your workplace?

| Answer | You must follow the company procedure & guideline to acquiring resources. This may be through - purchase orders - verifying the quality, availability and delivery of the resource - Identifying approved suppliers or gaining approval to use non approved suppliers - Gaining approvals for purchases above your limit |  |
| --- | --- | --- |

How do you communicate site safety requirements to ensure contractors wear PPE suited to the site and task?

| Answer | - Induction - Mandatory PPE signage at Entrance to site - Toolboxs - Regular training |  |
| --- | --- | --- |

What is the ‘rule of thumb’ basis for matching a machine to a job?

| Answer | Power/speed to Distance Higher powered machine over small distance Faster and more capable machine over bigger distance |  |
| --- | --- | --- |

Supervisors must have knowledge of factors affecting plant performance. What are four (4) factors that can affect plant performance and output and why must supervisors monitor each of these?

| Answer 1. 2. 3. 4. | Equipment maintenance and condition Environmental conditions Operators skill level Quality & supply of materials Constant monitoring of these will help minimise downtime, controlling costs & maintaining efficiency with in the work place |  |
| --- | --- | --- |

How do you confirm that the contractor has a job plan available that meets task requirements?

| Answer | Through reviewing, assessing and monitoring of the job plan. Assessing background of client/contractor will also help for further validation of there work and capabilities |  |
| --- | --- | --- |

What methods can you apply to confirm contractors have communicated instructions to team members and others involved?

| Answer | This can be done through reviewing and assessing of documentation and communication with in the work group. Also can be done through regular weekly/daily meetings, one on one conversations with members of the work group. |  |
| --- | --- | --- |

What is required when setting out for work tasks?

| Answer | - Boundary limits - Clearing limits - Setting out of earthworks limits - pavements etc |  |
| --- | --- | --- |

What is the importance of the survey pegs during the road set out?

| Answer | The importance of survey pegs during the road set out will help show limit of works and clearing limits, while also helping to ensure the road is built in the correct location, level and shape. |  |
| --- | --- | --- |

What methods do you apply when monitoring civil works to ensure the required outcomes or met on a daily basis?

| Answer | This is down through daily diaries/reports. This can also be shown throw spreadsheets, flow charts etc making it more open for everyone to review. Daily meetings is another way of catching up and logging progress aswell |  |
| --- | --- | --- |

Name and explain the purpose for three (3) of the different test results the supervisor must be able to read and understand at different hold or witness points of a project.

| Answer 1. 2. 3. | Compaction test - this assist with making sure that required compaction is being met during construction phase while also making sure its meeting the required specs Concrete slump tests - Slump tests are conduct before concrete is used in a pour this is to make sure that the concrete is meeting the required specs for the pour. Subgrade & Subbase testing - Most commonly done through proof roll, this helps to show of any unsuitable material or faults with in your subgrade prior to placing material on it. This helps to remove these faults prior to any works eliminating reworks at a later date |  |
| --- | --- | --- |

What is the purpose of road surface drainage and what are four (4) elements used to achieve this effectively?

| Answer Purpose Element 1. 2. 3. 4. | Road surface drainage is used to remove water on the surface of roads to an appropriate receiving location as quickly as possible reducing the risk to road users. Table drains Kerb & Channelling Batter drains Drainage pipe networks |  |
| --- | --- | --- |

What are the effects of inappropriate road drainage infrastructure?

| Answer | - Long term inundation during flood events - Erosion - Flood heights can increase - Flooding patterns can change - Damage to local fauna |  |
| --- | --- | --- |

What are the three (3) main parts of roadway design and the importance of these features?

| Answer 1. 2. 3. | Alignment - Alignment is essential to minimise risks and ensure efficient vehicle movement Profile - road profile is important to ensuring a road is built to a safe, functional and durable way Cross section - Cross section refers to a roads design ensuring that there is enough space required for vehicles to travel safely while also factoring in effective drainage |  |
| --- | --- | --- |

What are four (4) events that might occur on a normal working day that may significantly affect progress of civil works tasks and force the use of contingency plans.

| Answer 1. 2. 3. 4. | Unavailability of materials Sickness Plant break down Weather |  |
| --- | --- | --- |

What are four (4) contingency plans that may be in place to support a civil construction operational plan?

| Answer 1. 2. 3. 4. | Have alternative works planned for days of wet weather Maintain good relationships with subcontractors for times of neeed - shortage of workers/plant on short notice Plant breakdown or maintenance - regular maintenance schedules to help with monitoring, have service/repair personal contracts in place for times of need, back up equipment options on stand by Set rosters - to minimise the risk of labour shortage |  |
| --- | --- | --- |

What methods do you apply when monitoring worker and contractor performance for safety and compliance?

| Answer | This is done through regular site inspections conducted on a daily/weekly basis. By completing these inspections we can monitor the site for safety and compliancy. Also helps with creating the conversation with the workers in regards to the reasons behind site safety and compliancy. |  |
| --- | --- | --- |

What is the relationship between waste management and environmental protection?

| Answer | Bad waste management can cause damage to the environment. Waste management is important the job to make sure you are adhering to your EMP aswell as minimising/eliminating any risk to the environment |  |
| --- | --- | --- |

Describe why supervisors access each of the following types of data.

| Answer | Geological Data: Geological data helps understand ground conditions, faults/unstable ground or rocks with in the project building area. This will help determine the sustainability of the work/building area. Hydrological Data: Hydrological data includes information about the distribution, movement, and quality of water in the area. This is helps with managing water resources, especially for projects that impact or rely on water bodies, such as, dams, and wastewater treatment facilities. Having this knowledge also can help with compliancy as some projects you have to track water usage etcHydrological data includes information about the distribution, movement, and quality of water in a region. This is crucial for managing water resources, especially for projects that impact or rely on water bodies, such as irrigation systems, dams, and wastewater treatment facilities.Hydrological data includes information about the distribution, movement, and quality of water in a region. This is crucial for managing water resources, especially for projects that impact or rely on water bodies, such as irrigation systems, dams, and wastewater treatment facilities. Meteorological Data: Meteorological data provides information about the weather with in the region. This information is great knowledge towards planning and scheduling works to ensure your minimising the effect it has on the works or utilising the weather in the best ways to complete works more efficiently. |  |
| --- | --- | --- |

RIICWM402E

Supervise civil works contractors

PRACTICAL ASSESSMENT

| Participant name | Joshua Ferguson |
| --- | --- |

FOR THE PARTICIPANT

Instructions

- The tasks outlined on the following pages will require performance of normal workplace activities, as a result of a structured activity set by an Observer in the workplace or a simulated activity set by your Assessor/Observer. - The timeframe for these tasks will be established by your Assessor/Observer, in consideration of location conditions and industry requirements. - You must complete all tasks unassisted by the Assessor or other personnel unless the steps note this assistance. - You must attempt all tasks (and itemised steps) for a ‘Satisfactory’ assessment outcome to be awarded. - For any observation conducted that is incomplete, or without satisfactory performance, the observation will need to be completed again after further training support.

FOR THE ASSESSOR/OBSERVER

Instructions

- The following observation record should be used to judge and record your observations of the Participant as they complete the task(s) set. You must record your observations of the Participant’s performance. - For each occasion, indicate the task performed and whether it was a simulation or workplace-based task. - Any simulated assessment must ensure the Participant still performs under workplace conditions which reflect industry standards. - In the comments, provide clear detail regarding the task that the Participant was required to do (e.g. PPE used, materials handled, attachments connected, plant types). - All steps must be satisfactorily demonstrated by the Participant for a ‘Satisfactory’ determination (indicated by an Assessor tick to the right of each itemised step, or an Observer tick to the right of each itemised step, and confirmation by an Assessor in the Assessor Comments). - Where you have determined that one or more task steps have not been satisfactorily demonstrated, provide the Participant with additional support and outline details of such assistance in the Assessor/Observer Comments. Allow the Participant two (2) further opportunities to demonstrate the task again to allow an opportunity for a ‘Satisfactory’ assessment outcome to be achieved. - If after three (3) attempts the Assessor determines that the Participant cannot demonstrate the required steps, a ‘Not Satisfactory’ outcome is to be determined.

| TASK OUTCOME |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task | Date | Task Type (Tick) | Location | Task outcome (Tick) |  |
|  |  |  |  | Satisfactory | Not Satisfactory |
| Task 1 | Select Date. | Workplace Simulation |  |  |  |
| Task 2 (Occasion 1) | Select Date. | Workplace Simulation |  |  |  |
| Task 2 (Occasion 2) | Select Date. | Workplace Simulation |  |  |  |

ASSESSOR COMMENTS

As necessary, outline: - Details on reattempts, alternative arrangements or reasonable adjustments made. - Where a Participant is deemed ‘Not Satisfactory’, provide recommendations for future training.

| ASSESSOR COMMENTS: PRACTICAL TASK 2: OCCASION 1 |  |
| --- | --- |
| Individual student (as named on cover page) Multiple students [ All from Attendance Report, Specific students involved – identify students] |  |
| Task | Provide detail |
| 2.1.B. | Specify task to be completed: |
| 2.1.C. | Completed Task 1 meets these requirements: |
| 2.1.E. | Specify tool and method applied to address potential risks, hazards and environmental issues and implement control measures. |
| 2.1.F. | PPE worn/applied (tick or specify): Hi-viz Helmet Gloves Safety boots Eye protection Ear protection Other (please specify): |
| 2.1.G. | Specify method used to consult with contractors: |
| 2.1.J. | Specify method applied to confirm resources are available: |
| 2.2L. | Specify new potential hazards recognised and controlled: |
| 2.2N. | Specify what has been set out: |
| 2.3A. | Specify checks/measurements made: |
| 2.3D. | Communication applied (tick or specify): Face to face Marking on pegs Stringlines UHF Hand signals Whistles Other (please specify): |
| 2.3G. | Specify adjustments made: |
| 2.4D. | Outline recommendations made: |

| ASSESSOR COMMENTS: PRACTICAL TASK 2: OCCASION 2 |  |
| --- | --- |
| Individual student (as named on cover page) Multiple students [ All from Attendance Report, Specific students involved – identify students] |  |
| Task | Provide detail |
| 2.1.B. | Specify task to be completed: |
| 2.1.E. | Specify tool and method applied to address potential risks, hazards and environmental issues and implement control measures: |
| 2.1.F. | PPE worn/applied (tick or specify): Hi-viz Helmet Gloves Safety boots Eye protection Ear protection Other (please specify): |
| 2.1.G. | Specify method used to consult with contractors: |
| 2.1.J. | Specify method applied to confirm resources are available: |
| 2.2L. | Specify new potential hazards recognised and controlled: |
| 2.2N. | Specify what has been set out: |
| 2.3A. | Specify checks/measurements made: |
| 2.3D. | Communication applied (tick or specify): Face to face Marking on pegs Stringlines UHF Hand signals Whistles Other (please specify): |
| 2.3G. | Specify adjustments made: |
| 2.4D. | Outline recommendations made: |

RIICWM402E

Supervise civil works contractors

Practical Task 1

Description of task: The participant must demonstrate undertaking the role of a civil construction supervisor and prepare a job plan which is to be carried out as part of Practical Task 2. The participant must include documentation demonstrating collating of information. If they do not have adequate existing documentation, they will be required to develop a new template for use or one from another job which illustrates the type of information they require. As part of this task, the participant is required to demonstrate the skills and knowledge to: - access, read and correctly interpret work documentation to ensure all work to be completed is compliant - identify and address potential risks, hazards and environmental issues, and implement control measures including selecting and wearing site appropriate PPE - consult with team members to confirm the task requirements - organise for the acquisition and availability of required resources - implement a job plan that meets task requirements Tasks are at the Assessor’s Discretion, but detail of tasks undertaken must be recorded in the Assessor’s Comments (on the back of the Practical Assessment cover page).

Resources required: Work team, work site, organisational policies, standard operating procedures and plans, safety processes, hazard and risk assessment documents relevant to the area of work, Project plans and specifications, EMP, TMP, Engineering survey, Testing schedule requirements, relevant SDS for any chemicals used as part of the work task being assessed.

| When completing the task, did the Participant: | Tick if satisfactorily completed. Provide comments if left unticked. |
| --- | --- |
| 1 Human resource requirements |  |
| A clear and accurate overall number of workers required to undertake the construction task. |  |
| Identify appropriate types of workers required for the task (e.g. skilled or unskilled labour, concreters, carpenters, road crews). |  |
| 2 Plant and machinery requirements |  |
| Identify appropriate types of plant and machinery required to complete the task, and justification their selection. |  |
| Identify the plant and machinery requiring a trained or licensed operator and any legislative document or note providing this information. |  |
| Identify how plant and equipment will be procured for the job and what procedures will be followed to undertake this (e.g. hire company, plant hired after requisition form submitted to the site engineer and accounts officer). |  |
| 3 Construction material requirements |  |
| Interpret site plans and specifications to identify the types of construction materials to be used. |  |
| Apply accurate calculations of material quantities to be used during the task showing areas, volume or tonnage and wastage factors from plan requirements and engineer requirements. |  |
| Identify the total value of materials to be used. |  |
| Document contingency planning in place regarding ordering materials from alternate suppliers. |  |
| 4 Sub-contractor support requirements |  |
| Describe the requirement for all sub-contractor to undergo induction training prior to entering site. |  |
| Identify key personnel that sub-contractors will refer to. |  |
| Provide documentation from site including schedules or charts identifying: - the use of sub-contractors over a given period of time - plans of drawing of work to be completed by sub-contractors - sub-contractor induction records - organisational chart indicating who sub-contractors will report to. |  |
| 5 Waste disposal requirements |  |
| Identify relevant state authority acts, regulations, codes of practice and standards relating to waste removal (e.g. Environmental Protection Act). |  |
| Identify and explain how materials will be removed from site (e.g. Will they be taken to landfill, decontaminated). |  |
| Describe any specific organisational requirements for waste disposal.(as applicable). |  |
| 6 Coordination requirements |  |
| Identify and describe tasks that occur simultaneously on the job plan. |  |
| Accurately identify the time required to undertake the main construction steps. |  |
| Identify the persons required to monitor to different aspects of the project. |  |
| 7 Activity scheduling |  |
| Clearly identify the overall length of time assigned to the project and significant milestones from production schedules, construction sequence drawings, Gannt charts or similar. |  |
| Sequence steps effectively with an efficient use of time. |  |
| 8. Materials delivery scheduling |  |
| Clearly identify the key delivery dates for materials to be used. |  |
| Identify the locations for site deliveries. |  |
| Clearly explain the types of trucks, plant and machinery used during the materials delivery process. |  |
| 9. Risk assessment and management requirements |  |
| Describe methods for prioritising risks onsite (e.g. using risks calculators, incident reports). |  |
| Describe the processes involved with respect to deciding upon control measures. |  |
| 10. Work health and safety requirements |  |
| - Identify appropriate safety personnel for the site and their roles in the safety system. |  |
| Provide examples of how hazards may be identified on site through inspections, conducting on going risk assessments, checking reports. |  |
| Explain the reporting requirements for hazards and incidents on site. |  |
| Identify the requirements for all workers on site to undergo site specific inductions. |  |
| Explain procedures for identifying non-hazardous and hazardous materials. |  |
| Explain procedures for handling substances/ materials onsite (e.g. SDS). |  |
| Explain the site evacuation procedure including meeting points using the site evacuation plans. |  |
| Identify and explain the location of firefighting and first aid equipment. |  |
| Identify and explain the roles of emergency personnel on site (e.g. Fire warden, Chief fire warden). |  |
| 11. Quality management requirements, including testing scheduling requirements |  |
| Identify the tolerances applicable to the civil construction task from plans and specifications. |  |
| Determine from specifications and schedule testing milestones, the types of testing required. |  |
| Identify the personnel required to monitor and confirm testing. |  |
| 12. Traffic management requirements |  |
| - Identify exclusion zones, signage and barriers required for the project from the traffic management plan. |  |
| - Document the personnel required to implement and monitor the traffic management plan. |  |
| 13. Environmental requirements |  |
| - Identify and document how noise, erosion, water quality, waste disposal, flora and fauna and cultural heritage artefacts/ sites were intended to be controlled on site |  |
| 14. Task monitoring requirements |  |
| - Identify the persons required to monitor to different aspects of the project. |  |
| - Provide production charts, toolbox meeting schedule, briefing note, emails, charts diagrams or work instruction requirements for addressing issues with safety/performance. |  |
| 15. Task performance monitoring requirements |  |
| - Provide example documents including production charts, briefing note, emails, charts diagrams or work instruction indicating milestones or timeframes for the construction, organisation charts/diagrams or notes. |  |
| 16. Communication requirements |  |
| - Identify how regularly toolbox meetings occur on site. |  |
| - Explain the procedures for recording attendance and topics during toolbox meeting (agenda, sign on sheets). |  |
| - Identify communication technology which may be used onsite. |  |
| 17. Reporting requirements |  |
| - Document milestones and reporting requirements including reporting to who. |  |

RIICWM402E

Supervise civil works contractors

Practical Task 2 (2X)

Description of task: The participant must demonstrate undertaking the role of a civil construction supervisor, supervising contractors on two (2) occasions. Occasion 1 of this task will relate to the plan prepared in Practical Task 1. During this task, the participant the participant must display the skills and knowledge to effectively, safely and efficiently: - prepare to supervise contractors of civil works - confirm task initiation - confirm contractor has communicated instructions to team members and others involved during pre-start meeting - set out tasks as required for the effective completion of the civil works - while overseeing the execution of tasks: - monitor task performance for safety effectiveness and efficiency - implement adjustments to civil works practice and job plan as required - oversee plant equipment and tools maintenance and confirm maintenance requirements are carried out and recorded according to manufacturer and site requirements - report on the execution of tasks - complete and submit written and verbal reports according to site requirements - recommend improvements to civil works practice. Tasks are at the Assessor’s Discretion, but detail of tasks undertaken must be recorded in the Assessor’s Comments (on the back of the Practical Assessment cover page).

Resources required: Work team, work site, organisational policies, standard operating procedures and plans, safety processes, hazard and risk assessment documents relevant to the area of work, Project plans and specifications, EMP, TMP, Engineering survey, Testing schedule requirements, relevant SDS for any chemicals used as part of the work task being assessed, all materials, tools, plant or equipment required to complete the task, required PPE and relevant safety equipment.

| When completing the task, did the Participant: | Tick if satisfactorily completed. Provide comments if left unticked. |  |
| --- | --- | --- |
|  | 1st Occasion | 2nd Occasion |
| 1 Plan and prepare to supervise contractors of civil works |  |  |
| - Identify the location of the site using appropriate project plans. |  |  |
| - Determine the scope of the work task from plans, drawings and specifications. |  |  |
| - Complete a job plan demonstrating ability to access, read and apply workplace documentation to confirm legislative, statutory and workplace compliance. |  |  |
| - Confirm contractor has a job plan available that meets task and compliance requirements |  |  |
| - Determine and address potential risks, hazards and environmental issues and implement control measures. |  |  |
| - Select and wear PPE suited to site and tasks. |  |  |
| - Consult contractors and team members regarding resource requirements for task. |  |  |
| - Communicate with other supervisors/ team leaders to resolve potential coordination requirements. |  |  |
| - Identify specific council, state or federal requirements for the site including those relating to finishes, quality, reporting and safety. |  |  |
| - Confirm required resources including human resources are acquired and made available for task. |  |  |
| - Explain any specific organisational, client and site requirements from site plans, specifications, geological, geotechnical data. |  |  |
| - Clearly explain the meteorological data available for the site (rainfall, humidity, temperature and wind), and identify any issues in production (e.g. If a possibility of rain was evident), quality or safe work practices arising from the forecast. |  |  |
| - Interpret site plans or environmental plans to clearly indicate the location of site wash down facilities. |  |  |
| 2 Confirm task initiation |  |  |
| - Facilitate a pre-start meeting with contractor and team. |  |  |
| - Monitor contractor participation in pre-start meeting to confirm contractor has communicated instructions to team members and others involved to workplace requirements. |  |  |
| - Discuss any possible construction problems (or lack of), regarding the type of rock found onsite. |  |  |
| - Discuss any possible construction problems (or lack of), regarding the type of soil types found onsite. |  |  |
| - Discuss weather conditions and recommend actions. |  |  |
| - Discuss site hydrological data and associated drainage requirements. |  |  |
| - Explain the log book, or scheduled servicing procedure for plant and machinery used on the site. |  |  |
| - Concisely explain how faulty or defective equipment will be reported and recorded onsite using example hazard identification forms. |  |  |
| - Explain any environmental hazards posed from the use of plant and machinery including control measures to be used to control these environmental hazards. |  |  |
| - Listen to and respond effectively to questions and queries. |  |  |
| - Ensure all workers understand the SWMS for the task and have signed their understanding. |  |  |
| - Walk the work area with contractors and the team, identifying new potential risks, hazards and environmental issues and suitable controls. |  |  |
| - Ensure signs and barriers have been installed to protect work area as required. |  |  |
| - Set out task correctly from engineers’ survey pegs using plans, drawings and specifications. |  |  |
| 3 Oversee execution of tasks |  |  |
| - Watch workers undertake tasks, checking that tolerances are met as required. |  |  |
| - Monitor workers for safety concerns, making sure manual handling procedures are followed and work activities are conducted safely. |  |  |
| - Watch plant and equipment used to confirm machinery is used safely and within machine capabilities and limitations. |  |  |
| - Clearly communicate with workers regarding task execution using approved and understood communication methods. |  |  |
| - Write notes in diary if safety or compliance issues arise. |  |  |
| - Write notes of measurements made, material quality, deliveries and docket checks. |  |  |
| - Organise and make adjustments to civil works practice and job plan as required and confirm required outcomes are achieved. |  |  |
| - Confirm personnel allocated has checked that log books have been filled out and scheduled servicing has been undertaken on plant and equipment. |  |  |
| - Confirm that faulty or defective equipment is reported and recorded according to site requirements. |  |  |
| 4 Report on execution of tasks |  |  |
| - Make verbal reports to relevant personnel regarding completion of stages, reaching milestones, testing required. |  |  |
| - Complete all diary entries clearly and legibly. |  |  |
| - Ensure all test results and checks are documented and stored according to site requirements. |  |  |
| - Make verbal or written recommendations regarding changes to task execution. |  |  |