CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Henry Erratt |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | 20/06/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 30 |  | Yes | No |

Assessor Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Sand and Gravel | Landscaper |  |
|  | Steel Fixer | Formworker |  |
|  | Concrete | Concreter |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | A builder can closely direct the work to be undertaken by an employee A contractor can decide what work they do, how it is to be carried out and the hours when the work is to be completed It is important to schedule works as builders will not always have employees on hand who have the specialist skills required to complete a project. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Council, Environmental Regulators |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | Colour requests may require a special order to be made |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | - Monday to Friday - 7am to 5pm - Saturday - 8am to 1pm - Sunday and Public Holidays - no work is permitted - Applicants can apply to Council for work outside of these hours, approval is only granted in special circumstances, like shop fit-outs overnight or where demolition/erection of structures may be a risk to public safety during daylight hours (eg. cranes, hoardings). |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Architectural Drawings | Identify the materials of construction to be used, heights and measurement of different building components |  |
|  | Excavation Drawings | Represent the footing excavation, dimension, column position, footing plan, and grid line of columns. These drawings would identify the types of plant and operators needed. |  |
|  | Product specifications | Include items such as whitegoods, electrical goods, lights and switch types. Will allow for an indication of lead times for certain product that are not standard. |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | - Make changes to the schedule, Notify the suppliers/ contractors, Make changes to the call forward sheet. |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | A change of mind when a client views the developing construction site | Changes in progress and cost |  |
|  | The need to do something that was not expected but is now required by a local authority | Added scope prolongs the work and has unforeseen costs |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Something is found on site after construction begins which was concealed or unexpected given the information at the time of tender | Delay in progress and cost |  |
|  | Weather has delayed work | Delay in progress and cost |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | Overlay drawings are drawings that show further detail on top of any existing plans and specifications. Overlay drawings are generally designed to: - Provide more visual clarity about a building process - Provide advice if there have been changes that require subsequent engineering redesign/specialist changes (e.g. from architects, soil experts) |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | - Work - Time period - Agreed rates |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | - Order Date and delivery date - Purchase Order Number - Supplier Details - Delivery Details - Supplier Contract information - Project manager details - Product Description - Terms and conditions - Total order cost |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet is a sheet used to track when materials are needed and when they should be ordered. This tool allows site personnel to schedule and coordinate activities that are to be undertaken on-site. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Architectural, land survey, service locations |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | 250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Concrete | 5 Days | 18/06/19 | 12/06/19 | Volume of concrete |  |
|  | Brick Veneer | 3 weeks | 18/07/19 | 25/06/19 | Colour |  |
|  | Timber | 3 weeks | 18/07/19 | 25/06/19 | Treatment of timber |  |
|  | Roof Tiles | 1 week | 4/09/2019 | 11/09/19 | Colour |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | Get quotes, select best tender prices and setup contract Purchase order and select best delivery date construct call forward sheet | Lead time (availability of material), Cost, Risk when order is delayed (should it be stored) |  |
|  | Wall frame | Get quotes, select best tender prices and setup contract Purchase order and select best delivery date construct call forward sheet | Lead time (availability of material), Cost, Risk when order is delayed (should it be stored) |  |
|  | Windows | Get quotes, select best tender prices and setup contract Purchase order and select best delivery date construct call forward sheet | Possible Damage in Transit, Lead time (availability of material), Cost, Risk when order is delayed (should it be stored) |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer | Email to Client: Client, The unsuitable soil below the supporting foundations of the residential building has not been included in the current scope of works as shown in the contract. I am formally raising a variation to the original contract to accommodate for the increase in time and cost that will be associated with the removal of the unsuitable material and replacement with the required foundation material. Cost of variation= $20,000 Delay in programme = 1 week. I will be awaiting your response to formalise the variation. Regards, Contractor |  |
| --- | --- | --- |