## General Business
ABC Flooring Services
Meeting Objective: Project Hand Over
Project Name: Nambour General Hospital Redevelopment
Job Number #130258
19th June 2019
10:30am - 11:15am
Boardroom
Meeting Attendance:
Jonathon Diehm - Project Manager
Tara Gilson - Senior Estimator
Sara Vaninetti - Project Assistant
Leanne Cameron - Safety Officer/Material Ordering Clerk
Sarah Camenzind - Finance Manager
Discussion Item | Details | Action | Completed | Comments
Overview of Project | Nambour General Hospital Redevelopment is a 10 stage Refurbishment of the existing Hospital. Works are to commence 25th August 2019 with the expected completion date of all 10 stages approx November 2021. | Tara Gilson - provide overview | Completed | Project Folder also provided to Jonathon with supporting information
Contract Execution | Contract has been signed and sent back for counter signing by builder | Tara Gilson - confirm when counter signed copy received | Partially Completed | Fully executed copy to be given to Sarah Camenzind
Material Orders | Material Orders have been placed for the 10 project stages, order confirmations to be followed up with material manufacturer and lead times confirmed. IF materials are unavailble, confirm equal IN STOCK alternatives to present to builder for sign off. Request Technical Data Sheets from Manufacturers for sample submission sign off. | Leanne Cameron - to track order confirmations and lead times and submit material samples/tech data sheets for approval | Partially Completed | Order confirmations and lead times to be confirmed at the next Project Support Meeting, along with any problems with sample submissions/sign offs and material availability.
SWMS and supporting safety documentation | SWMS have been submitted to the Builder for review, amendments are required based on the Builders feedback/notes | Leanne Cameron - to review and resubmit | In review | Revised SWMS documents to be provided at the next Project Support Meeting
Aboriginal Participation | 7% aboriginal participation required for this contract | Sarah Camenzind - to track for progress claim requirements | On-going | Confirmation of labour to be used on project as noted below, to be provided by Jonathon Diehm
Progress Claims | Draft progress claims are due on 20th of each month for review with main progress claim submission required 25th of each month, Jonathon Diehm to provide Sarah Camenzind with a mark up of areas completed to send with the progress claim | Sarah Camenzind - completing progress claim submission, with documented evidence provided by Jonathon Diehm | On-going | Sara Vaninetti to support Jonathon Diehm with marked up drawings if required
Labour Sourcing | Labour sourcing is to commence, confirmation on labour teams required so inductions can be organised | Jonathon Diehm to confirm labour, Sara Vaninetti to organise inductions | Outstanding | Sara Vaninetti to confirm ID or trade cerficates required to complete inductions
Document Transittal Program | Aconex is being utilised for this project, Sara Vaninetti to review tender vs. construction issue documents uploaded onto Aconex to confirm any changes made after going to contract and confirm | Sara Vaninetti to review construction issue documents | Outstanding | Sara Vaninetti to confirm if any changes have been made and update material orders with Leanne Cameron to reflect these changes and work with Tara Gilson to update Project Folder given to Jonathon Diehm where needed.
Purchase Orders | Purchase orders need to be sent to Gold Medal Safety Padding, Gabba Waterproofing and Legion Tiling for their portion of works | Leanne Cameron to complete with support from Sara Vaninetti | Outstanding | Follow up confirmation these Purchase Orders have been received and actioned - to be reviewed at next meeting
Next Project Support Meeting:
26th June 2019 - 10:00am
Boardroom
One on One catch up before 26th June with Tara Gilson:
Leanne Cameron: 22nd June 2019 @ 9:00am
Sara Vaninetti: 22nd June 2019 @ 9:30am
Sarah Camenzind: 22nd June 2019 @ 10:00am
In Tara's Office

## Current Projects
Current Projects
Date | 2020-11-18
Attendees | Jon, Sarah, Aaron, Glenn, Leanne, Craig, Clare, Tara and Sara
Absent | Nicole
Job Number | Builder | Project | Project Manager | Contract Value | Est. Mark Up % | MYOB Invoiced | Current Month Claim | Invoiced Value | Current Costs | Profit | Markup% | Estimated Completion | Comments | Action required by
130713 | ADCO | Pimpama Sports Hub and Community Precinct | Jon | 177910 | 20% | 8750.97 |  | 8750.97 | 71270.86 | -62519.89 | -87.72% | 2021-05-01 | Stage 2 commensing Marcch, all materials purchased
130407 | CPB | Coffs Harbour Hospital | Aaron | 1636000 | 20% | 1109962.01 |  | 1109962.01 | 944501.03 | 165460.98 | 17.52%
130942 | John Holland | Greenslopes Private Hospital Redevelopment | Craig | 553591 | 37% | 254738.81 |  | 254738.81 | 294660.63 | -39921.82 | -13.55% | 2021-12-01 | 60% Complete - Stages
130504 | Multiplex | Maitland Hospital | Aaron | 4266560.07 | 30% | 3763809.8 |  | 3763809.8 | 2712436.42 | 1051373.38 | 38.76%
118637 | McNab | Treehouse Residences | Jon | 307512 | 15% | 404345.86 |  | 404345.86 | 332281.52 | 72064.34 | 21.69% | Complete | 100% Complete
130110 | 5 Point Projects | Alta Vista Apartments | Craig | 30488 | 19% | 14622 |  | 14622 | 23413.36 | -8791.36 | -37.55% | 2021-03-01 | 100% Complete end of Mar 2021
130801 | Paynters | Gold Cost Youth Foyer | Craig | 89744 | 18% | 37176.1 |  | 37176.1 | 73116.4 | -35940.3 | -49.15% | 2021-04-01 | Tracking well - 20% complete
130716 | Nano | Anne St Southport | Craig | 19165 | 19% |  |  | 0 | 11267.55 | -11267.55 | -100% | 2021-04-01 | 50% Complete Mar 2021
130717 | Nano | Winstanley St, Carina | Glenn | 22970 | 18% | 21683 |  | 21683 | 15094.73 | 6588.27 | 43.65%
118676 | McNab Developments (Qld) Pty Ltd | Anthology Apartments | Jon | 55545 | 18% | 58685 |  | 58685 | 50085.78 | 8599.22 | 17.17% | Complete
130951 | Warrell | Lords Lutheran - Ormeau | Craig | 54000 | 18% | 28528 |  | 28528 | 38674.02 | -10146.02 | -26.23% | 2021-05-01 | Second Stage
130835 | Kane Construction | Lawnton State School | Craig | 69317 | 23% |  |  | 0 | 39681.28 | -39681.28 | -100% | 2021-04-01 | Set down + Vinyl next week - Starting in 1 month
130394 | Newlands | MSQ Toowoomba | Jon | 82980 | 20% |  |  | 0 | 2700 | -2700 | -100% | Mid Jun 2021 | Starting next week
130015 | Lend Lease | Nambour General Hospital Refurbishment | Craig | 2095000 | 25% | 20895 |  | 20895 | 23878.6 | -2983.6 | -12.49% | on going 2023 | 2 vinyl + 1 Comm Room
130978 | Precision Interior Walls/Ceilings Pty Ltd | Dakabin Train Station | Craig | 21276 | 21% |  |  | 0 | 1240 | -1240 | -100% | 2021-04-01 | Yet to start
131034 | Precision Interior Walls/Ceilings Pty Ltd | Greenslopes Private Hospital GMRD Office Refurb | Craig | 12000 | 18% | 7200 |  | 7200 | 3134 | 4066 | 129.7% | Complete | Claim in full - Day dockets
130847 | Kane Constructions | Ithica Creek State School | Jon | 75000 | 18% | 14912 |  | 14912 | 44064.1 | -29152.1 | -66.16% | 2021-06-01 | Stage 1 Complete - Stage 2 on hold
130640 | Paynters | Ipswich Hospital 26 bed ward refurbishment | Jon | 314872 | 18% | 23526.75 |  | 23526.75 | 59353.92 | -35827.17 | -60.36% | 2021-06-01 | Tracking well
131118 | Dickinson Constructions | Merrimac SHS | Craig | 35700 | 18% | 37050 |  | 37050 | 31982.34 | 5067.66 | 15.85% | Complete
130900 | Stokes Wheeler | SCCC Admin, Wellness, Tuckshop | Craig | 46990 | 18% | 26415.2 |  | 26415.2 | 38369.49 | -11954.29 | -31.16% |  | Heavily staged, change from orginal job - Starts in 2 weeks
131144 | Tomkins Commercial | Iona College Mutlipurpose - win | Jon | 170780 | 18% |  |  | 0 |  | 0 | 0% | 2021-06-01 | Yet to start
131070 | Aligned Management Pty Ltd | Kruger SS Block 2 | Jon | 6790 | 18% | 6998.22 |  | 6998.22 | 5257.85 | 1740.37 | 33.1% | Complete | Variations to claim
131208 | Future Fitouts | Clarity Hearing Fitout | Jon | 5280 | 18% | 5208 |  | 5208 | 4291.69 | 916.31 | 21.35% | Complete
130663 | McNab NQ | Warwick East SS | Jon | 49175 | 18% | 13663 |  | 13663 | 41053.67 | -27390.67 | -66.72% | 2021-03-01
130780 | St Hilliers | Ipswich Depot Building Works | Jon | 22500 | 18% |  |  | 0 | 9152.2 | -9152.2 | -100% | 2021-05-01 | Yet to start
130846 | McQueen Projects | Mumo Tea Chermside | Craig | 7540 | 18% | 7844.73 |  | 7844.73 | 4944.01 | 2900.72 | 58.67% | Complete | Clare to follow up with Craig & Client
131206 | Bailey & Peddle | 618 Brunswick St | Glenn | 13631 | 18% | 16546 |  | 16546 | 11758.18 | 4787.82 | 40.72%
131204 | McNab Sunshine Coast | Charleville Hospital Warooma | Craig | 50478 | 18% |  |  | 0 | 18780.95 | -18780.95 | -100% | 2021-05-01 | Stage 1 complete and claimed - Stage 2 start 16 mar 2021
130495 | Moreton Bay Regional Council | Morayfield Sports & Events Centre | Craig | 42718 | 18% |  |  | 0 |  | 0 | 0% |  | Yet to start -May 2021
130457 | Stokes Wheeler | Anchorage Apartments | Lost Quote | 109000 | 18% |  |  | 0 |  | 0 | 0% |  | Yet to start -May 2022 - Claim July-Oct 1/4 each
131140 | Boss Construction | Unity College Auditorium | Jon | 12880 | [8 empty] | Starting March 2021
131080 | Boss Construction | Mary Mackillop | Jon | 11360 | [8 empty] | Staring March 2021
131243 | Hutchinsons | Caboolture Retail Warehouse | Craig | 16524 | [8 empty] | Starting April 2021
131224 | Kane | Sunshine Coast Grammar School | Craig | 13500 | [8 empty] | Starting April 2021
130410 | Watpac | Gotzinger Smallgoods | Craig | 40000 | [8 empty] | Starting April 2021
131284 | Hutchinsons | Helensvale Bowls Club | Glenn | 89110 | [8 empty] | Starting March 2021 - Claim 20K Mar - 39110 April - 30K May
| Newlands | USQ Toowoomba R Block | Jon | 214000 | [8 empty] | Starting late March - Claim April 50K - May 114K
|  |  |  | 10841886.07 | 21.19% | 5882560.45 | 0 | 5882560.45 | 4906444.58 | 976115.87 | 19.89% |  | 0 | 0

## Completed Job
Completed Projects / Outstanding Retentions
Job Number | Builder / Developer | Project | Project Manager | Comments | Marked as completed | Completed Margin | Total Contract Value | Total Retention Held in MYOB 5% | R1 Due for Payment | R2 Due for Payment | Retention Amount Due for Payment
TOTAL RETENTION DUE FOR PAYMENT | [10 empty] | #REF!
ALL OKAY
DUE FOR PAYMENT
IN ARREARS