CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Annamarie Dorin |
| --- | --- |
| Participant signature |  |

| Assessor name | Brett Stoward |
| --- | --- |
| Assessor signature |  |

| Date | 17/09/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 45 |  | Yes | No |

Assessor Comments

Question 13 I can not mark on the document – I mark True

Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | Specifications/building approval |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | Home Building Act 1989 No 147 Section 8 2(A) | Maximum deposit for residential building work 8 Maximum deposit for residential building work (1) The maximum amount of a deposit for residential building work is 10% of the contract price. A "deposit" for residential building work is a payment on account before work is commenced under a contract to do residential building work. (2) A person must not: (a) demand or receive payment of a deposit for residential building work if the amount of the payment exceeds the maximum imposed by this section, or (b) enter into a contract under which the person is entitled to demand or receive payment of a deposit for residential building work if the amount of the payment exceeds the maximum imposed by this section. Maximum penalty: 1,000 penalty units in the case of a corporation and 200 penalty units in any other case. (3) The regulations may make provision concerning how a contract price is to be determined for the purposes of this section. (4) This section does not apply to residential building work done under: (a) a contract that is made between parties who each hold a contractor licence and is for work that each party's contractor licence authorises the party to contract to do, or (b) a contract to do specialist work that is not also residential building work. |  |

Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Waterproofing | Prepares wet area surfaces |  |
|  | Plastering | Installs internal linings |  |
|  | Painting | Paints areas, such as walls and ceilings |  |

Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

Explain the importance of determining subcontractor or plant availability for a job.

| Answer | Plant availability is important if there is a certain task that needs to be required for the site. Also cost can vary if it is hired or if the equipment is required last minute. |  |
| --- | --- | --- |

Identify two (2) methods you might use to find a supplier for materials.

| Answer | Phone and ask around Liaise with known suppliers |  |
| --- | --- | --- |

Name two (2) factors that may impact on the availability of materials.

| Answer | Budget of the project (to purchase the materials) Supplier is out of stock – supply and demand |  |
| --- | --- | --- |

Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | NCC Volume One Part J6, NCC Volume Two Part 3.12.5 AS only - 1680 |  |
| --- | --- | --- |

Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Scaffold | To be able to put up frames/panals/bricks etc that is safer than ladders as an example |  |
|  | Dump Truck | To be able to take spoil etc away |  |

Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | Ladder | Used to access for ceiling lights etc |  |
|  | Wheelbarrow | To remove/move materials that are too heavy to carry |  |

Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | Insurances Deposits |  |
| --- | --- | --- |

Name five (5) temporary services that need to be organised for a building site.

| Answer | Electricity Water Lighting Security ie cameras/fences etc Site Office |  |
| --- | --- | --- |

True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

Identify one (1) action you might take to facilitate site access for machinery.

| Answer | Delivery? Online register? Excavation |  |
| --- | --- | --- |

Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | Vol 2 part 2.5 | Vol 1 Section D |  |

You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | Local City Council for approval for timeframe and approval |  |
| --- | --- | --- |

In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | Electricity Supplier | Sydney Water |  |
|  | Waste Disposal | AGL |  |

True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What document should be developed when purchasing supplies or construction materials?

| Answer | Purcahse order |  |
| --- | --- | --- |

True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Who should be contacted if items are missing from a delivery?

| Answer | Supplier |  |
| --- | --- | --- |

Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | WHS Act section 17 | A duty impsed on a person to ensure health and safety requires elimination of risks etc |  |

Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | WHS 2011 |  |
| --- | --- | --- |

What document should be followed when disposing of hazardous materials?

| Answer | SDS |  |
| --- | --- | --- |

An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10 |  |
| --- | --- | --- |

True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | Saves time. Subbies are already on the job and do not have to leave and come back for the next stage of the project. |  |
| --- | --- | --- |

Provide one (1) example to explain why construction operations must be sequenced.

| Answer | To determine the sequence of the project. Ie electrician and plumbers/concreter |  |
| --- | --- | --- |

Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 4 | Floor frame |  |
|  | 3 | Installing brick base |  |
|  | 6 | Roof trusses |  |
|  | 1 | Set out |  |
|  | 5 | Wall frames |  |

Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| - Task ID | - Task | - Preceding event | - Nodes |
| --- | --- | --- | --- |
| - A | - Make enquiries and order all materials required | - Start | - 1 |
| - B | - Wait for bricks, sand and cement to arrive | - A | - 2 |
| - C | - Clear vegetation from the site | - A | - 2 |
| - D | - Order concrete to be delivered | - A | - 2 |
| - E | - Dig the trench | - C | - 4 |
| - F | - Pour the footings | - E | - 5 |
| - G | - Footings curing time | - F | - 6 |
| - H | - Load the bricks on the site | - B | - 3 |
| - I | - Mix the mortar and lay the bricks | - H | - 7 |
| - J | - Clean rubbish from the area | - I | - 8 |
|  | - Finish | - J | - 9 |

G

F

H

E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | PS6 |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

Describe the critical path.

| Answer | 1 2 4 5 6 7 8 9 |  |
| --- | --- | --- |

True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | No materials No labour Weather |  |
| --- | --- | --- |

Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

Why should you take photographs of site boundaries with neighbouring properties?

| Answer | Support report Dispute |  |
| --- | --- | --- |

When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

When might a neighbouring property owner be required to refer to a condition report?

| Answer | When in the event of damage of damage occurring with the property |  |
| --- | --- | --- |