Assessment Workbook 5

BSB51415 Diploma

of Project Management

Integration Management

Version 1.01 Produced 18 October 2018

Copyright © 2022 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following assessment validation. | 1.0 |
| 18 October 2018 | Version 1.01 Change to Practical Assessment | 1.01 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Case Study	5

Instructions to Student	5

Introduction	6

Workbook Checklist	17

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 5 |  |  |
| --- | --- | --- | --- |
| TITLE: | Integration Management |  |  |
| FIRST AND SURNAME: | Mark Sztybel |  |  |
| PHONE: | 0418799990 |  |  |
| EMAIL: | msztybel5@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Mark Sztybel |  | Signature: MSZ | Date: 1/4/22 |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant advisor to the project team at Awesome Landscapes Pty Ltd. Specifically you are required to provide independent advice on seeing their current project through the entire life cycle. You have already provided advice to them in the previous four workbooks. The project manager has advised the project is now complete, and is about to archive all the project documentation. Your task is to evaluate the supplied project documentation and to ensure all due diligence has been completed. You will need to compare the project plan with the previous version to ensure it is ready for closure. Project Charter version 4 (.pdf) Project Plan version 4 (.pdf) Project Gantt Chart version 4 (.mpp) Project Gantt Chart version 4 (.pdf) Project Network Diagram version 4 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- Sam has asked to you check the Project Plan for anything that is missing. He has been very busy but appears to have done all the necessary finalisation of the plan ready for sign off. He has mentioned the final report or lessons learnt documentation has not been included, and the project archiving checklist have not been completed either. You will be assigned to complete these later. Examine the Project Charter (version 4) and Project Plan (version 4) and identify four (4) things that are missing. Guidance: - Assume the Project Gantt Chart and the financial figures in the summary/detailed costing tables are up to date as these have already been audited. Also remember this final project plan is in draft, and will not be signed off until the final acceptance meeting in a few days’ time. - Take note of the following: - Version control. - The updates from the project in the other workbooks you have completed in previous workbooks. - Check the project archiving checklist for everything that should be included

- issue register needs to updated from rev 3 - Project risk review needs to be updated from rev 3. Whilst the project is complete and risks have been mitigated these documents are important for lessons learnt/auditing etc - Procurement management template from previous revs - Version control needs to be amended to final version ready for sign off, Gantt chart finalised, lessons learnt and project archive document complete, project completion report finalised.

- Sam is in the process of developing a set of Lessons Learnt Documentation for the project. - Access and review the four (4) previous workbooks you have completed and derive three (3) different lessons learnt throughout the project. - Document each lessons learnt using the Lessons Learnt Documentation Template provided. Use one template for each lessons learnt.

| Lessons Learnt Documentation Template 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peaks Chalet |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Mark Sztybel |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 20/april/20xx |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Remove Contractor |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Director and project manager |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract Law |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | remove a contractor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Contract was terminated. New contractor instated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Work through issues and maintain current contractor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Negotiation between Cascade peak management and JP digging |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Failure to arrive at an agreement cost all parties. More outlay for the developer, delayed timeframes. Additional legals in contract renegotiations for us |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Careful vetting and interviewing of potential contractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Early in negotiations with stakeholder ask for prefered contractors or excluded contractors. Always being aware about open tender processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project is complete. Future tenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  | Post job team de-brief meeting/workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peaks Chalet |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Mark Sztybel |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 20/april/20xx |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Retention of staff |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | senior managment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Human resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HR monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Loss of good staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Time and energy spent sourcing and training new staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | retain current |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Meeting with staff/ open and honest communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Whilst the loss of staff is sometimes unavoidable could we have identified earlier when the job stalled who we needed to work with to retain them |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| One on one meetings with staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can we look at ways we cann retain staff in downturns - Book training? LWOP? annual leave, office duties, wage advances if wage agreement allows if employee is short |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Schedule meetings individually shortly after final sign off. All staff top down. Talk about jobs in the pipeline. Review entitlements which may be banked and employee future goals. Develop individual development plans and review 1/2 yearly. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  | Re-iterate in Post job team de-brief meeting/workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peaks Chalet |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Mark Sztybel |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 20/april/20xx |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Site damage from errosion |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Andrew |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Managment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Engineering control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Incorrect/ insufficient errosion management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | additional cost and time to the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | nil or minimal errosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Careful planning and design possibly engaging an expert in the field to minimize damage when site is demobilized for a period. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Our Errosion and silt risk management procedures were inadequate to prevent or minimize damage. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Careful weather watching with regard to open workfaces etc. We understand that this was a site shut down due to sponser issues but a similar thing may happen over extended breaks such as Christmas and Easter. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Minimize workfaces. Risk manage errosion control in inclement weather. Can we seek a course out for Andrew to better be able to plan silt management? without the cost of engaging external experts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Job complete. For consideration in future works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  | Errosion control tool box topic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Sam has asked you to write the final report for the project. Complete the final report using the template below, assuming the things missing from the project plan in the question above have been included. Guidance: - Access and carefully review the project documentation you were provided with along with the case study scenario and populate all the fields with the required information. - Provide a date that is later than the last date in the Project Gantt Chart version 4. - Assume that this report will be submitted to Terrence Mackay, Stephen Lyons, Kate Chan, and Kim Nguyen. - Provide a brief summary of the project in terms of the four project constraints (Scope, Cost, Time, and Quality). - Provide a detailed summary of the project covering the functions of project management listed below. Further guidance is provided for you within the template.

| Project Name: | Cascade Peaks Chalet |  |  |
| --- | --- | --- | --- |
| Prepared by: | Mark Sztybel |  |  |
| Date: | 21/april/20xx |  |  |
| Project Summary |  |  |  |
| Scope (What was included and excluded) |  |  |  |
| Inclusions: Pre Build - Site access roads and retaining walls for construction of log cabin chalets Excavate for underground utility services and maintain access roads and retaining walls Planting and landscaping |  |  |  |
| Exclusions Milling and delivery of timber or delivery of other material used to build the chalet Sourcing, Purchasing or delivery of services (Cable, pipe, fittings etc) Any Scope not covered in the initial council approved plans |  |  |  |
| Cost (Budget vs. actual) |  |  |  |
| Project budget fixed $650000 Actual after CR1,2,3 $514892 |  |  |  |
| Time (Estimate vs. Actual) |  |  |  |
| 3/Aug/16 - 11/Mar/17 Actual 27/Jul/16 - 12/Apr/17 |  |  |  |
| Project Report Submitted to: |  |  |  |
| Name: Terrence Mackay |  | Title: General manager Cascade peak hotel | Date: 25/April 20XX |
| Name: Stephan Lyons |  | Title: Planning Manager Cascade peak Council | Date: 25/April 20XX |
| Name: Kate Chan |  | Title: Project Manager Timber Home construction LTD | Date: 25/April 20XX |
| Name: Kim Nguyen |  | Title: Director Awesome Landscape PTY LTD | Date: 25/April 20XX |
| Analysis of Project Guidance: - Process Review - Describe all of the processes used during the planning, implementation and closure stages. - Lessons Learnt - Describe what went right and or what went wrong and how effective were the management and the processes you used. If necessary, state how you overcame any problems. - Recommendations – Make recommendations as a result of the lessons learned. |  |  |  |
| Scope |  |  |  |
| Process Review Scope changed early on with the addition of retaining walls. Changes to project sponser and damage to site during changeover process. |  |  |  |
| Lessons Learnt Considerable cost and time involved in changes these were in the pre build stage so could they have been better managed at tender. More careful management around erosion control |  |  |  |
| Recommendations Careful preplanning with the developer during the tender process could have flushed out the additional retaining walls. In future develop a working relationship during tender and suggest potential problems or value adds |  |  |  |
| Time |  |  |  |
| Process Review Project started 1 week early and planned around native replanting. 1 month delay due to sponsor change |  |  |  |
| Lessons Learnt Careful dealings with council expidited the approval process. Extra time was needed to get materials |  |  |  |
| Recommendations Correct management of changes to scope like additional labour help maintain program. |  |  |  |
| Cost |  |  |  |
| Process Review Cost was managed well. Change requests were well documented. Change of sponsor costs were unavoidable as in part was the change of digging contractor due to new sponsor clash. All significant purchases were in the first week of each stage |  |  |  |
| Lessons Learnt Careful and concise documentation around changes benificial. Erosion repair may have been avoidable or minimised with more careful management. |  |  |  |
| Recommendations Continued careful management of change requests and cashflow. Payment made on completion of work for each stage. |  |  |  |
| Quality |  |  |  |
| Process Review Quality management plan was followed and all regulations and licencing were followed |  |  |  |
| Lessons Learnt Internal audits prior to council audits helped minimise non conformances |  |  |  |
| Recommendations Maintain a accurate QA plan regularly audited by project Manager |  |  |  |
| Human Resources |  |  |  |
| Process Review Organisational charts, resource requirement plans, staffing management plans |  |  |  |
| Lessons Learnt We had good retention of management. Lost some landscapers due to non-continuation of work. Overall we believe a positive experience considering some challenges and remote work which can have a high turnover |  |  |  |
| Recommendations Develop leads and regularly review and communicate to potential landscapers so that there is a pool of resources that we may be able to contact in the event of loosing workers. Try to plan ahead to minimize downtime. Continue regular employee reviews to flush out problems |  |  |  |
| Communications |  |  |  |
| Process Review Communication management plan |  |  |  |
| Lessons Learnt Strong communication processes assisted with a smooth delivery |  |  |  |
| Recommendations Continue to develop and review communication processes. |  |  |  |
| Procurement |  |  |  |
| Process Review Procurement management plan |  |  |  |
| Lessons Learnt Potential procurement problems were identified early using risk anaylsis. The procurement management team worked closely with the site supervisor to deliver in a timely manner |  |  |  |
| Recommendations Careful development and review of procurement contracts assist in accurate supply of time dependent materials. Regular communication with subcontractors and suppliers can help ID problems with supply early. Have back up plans ready in the event of critical items are unavailable. |  |  |  |
| Risk |  |  |  |
| Process Review Risk Management plan |  |  |  |
| Lessons Learnt Thorough use of risk management tools are essential to identify risks and help plan around these issues |  |  |  |
| Recommendations Continue to use risk management tools and review and update lessons learned so the risks can be minimized on future projects. |  |  |  |
| Project Integration |  |  |  |
| Process Review PMBOK methodology |  |  |  |
| Lessons Learnt Strong, consistant, thorough use of the templates, resources, and practices avaiable will help provide a well managed project regardless of changes and issues. |  |  |  |
| Recommendations Can we provide PMBOK training further down our team structure so they know and can assist with job management. A lesson learned brain storm correctly documented should be held. |  |  |  |

- Sam has approved the report in the above question to be distributed. He has also updated the project plan following your advice. Now he is ready for the project closure meeting. He has assigned you the task of organising this meeting. Answer the questions that follow.

- Who will attend this meeting? Guidance: List the attendees by name, job title, and organisation).

Terrence Mackay General Manager Cascade peak Hotel Pty Ltd Stephen Lyons Planning Manager Cascade peak Shire Council Kate Chan Project Manager Timber home construction Ltd Kim Nguyen Director Awesome landscapes Pty Ltd Sam Ng Project Manager Awesome landscapes Pty Ltd

- What information will each person need before the meeting?

Project completion report, Final project plan,project archive checklist,formal acceptance

- Which documents (and which version number of each document) will need to be printed off for the meeting?

Project plan version 4 updated with missing information, Gantt chart 4 indicating project completion, project archive checklist

- Which of these documents will require signatures?

Completion report, project paln and formal acceptance

- Who will need to sign off on these documents?

Steering commitee

- Do you believe the project objectives aligned with the objectives of Awesome Landscapes throughout the entire project life cycle? Explain your answer.

Yes the project closely aligned with Awesome landscapes core buisness. We developed a new working relationship with the Hotel direct with ongoing maintenance and future projects. It came in under budget. There were issues with erosion and some native plant loss during a laydown but was managed well. And we gained further experience in large scale landscaping jobs and native plant management.

- What needs to be done after the meeting to complete the closure of the project?

Project Archival

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document