## Construction Project Timeline
CONSTRUCTION PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  |  | START
8 Rees Court Palm Beach |  |  | 2021-08-01 |  | PROJECT DURATION
PROJECT MANAGER |  |  | END |  | in days
John Doe |  |  | 2021-12-12 |  | 134
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
Foundation | Not Started |  | 2021-08-01 | 2021-08-19 | 19 |  | Not Started
Framing | Not Started |  | 2021-08-20 | 2021-10-01 | 43 |  | In Progress
Roof/Exterior Finishes | Not Started |  | 2021-09-24 | 2021-10-16 | 23 |  | Complete
Plumbing - Rough In | Not Started |  | 2021-08-10 | 2021-10-07 | 59 | Initial Slab work 2 days 10/8-12/8 | On Hold
Electrical - Rough In | Not Started |  | 2021-10-08 | 2021-10-11 | 4
Insulation/Gyprock | Not Started |  | 2021-10-12 | 2021-10-26 | 15
Flooring | Not Started |  | 2021-10-14 | 2021-11-07 | 25
Painting | Not Started |  | 2021-10-27 | 2021-11-11 | 16
Interior Finishes | Not Started |  | 2021-11-12 | 2021-11-25 | 14
Fixtures/Appliances | Not Started |  | 2021-11-12 | 2021-11-25 | 14 | inclues plumbing & electrical fitoff
Landscaping | Not Started |  | 2021-11-09 | 2021-11-25 | 17
Schedule Buffer | Not Started |  | 2021-11-26 | 2021-12-05 | 10
FINAL Inspections | Not Started |  | 2021-12-06 | 2021-12-06 | 1
Cleaning | Not Started |  | 2021-12-06 | 2021-12-11 | 6
Handover | Not Started |  | 2021-12-12 | 2021-12-12 | 1
SUBCONTRACTOR LETTING & SERVICES | STATUS | COMPANY | REQUEST DATE | ACCEPTANCE/AWARD DEADLINE | DAYS FROM REQUEST TO AWARD | ACCEPTANCE/AWARD DATE/COMMENTS
Earth Works | Not Started | 123 Earthworks 456 Earthworks 789 Earthworkds | 2021-06-16 | 2021-07-16 | 31
Concreter/Steelfixer | Not Started | 123 Concrete 456 Concrete 789 Concrete | 2021-06-16 | 2021-07-23 | 38
Roofer | Not Started | 123 Roofer 456 Roofer 789 Roofer | 2021-06-16 | 2021-09-10 | 87
Plumbing | Not Started | 123 Plumbing 456 Plumbing 789 Plumbing | 2021-06-16 | 2021-07-23 | 38
Electrical | Not Started | 123 Electrical 456 Electrical 789 Electrical | 2021-06-16 | 2021-09-24 | 101
Joinery | Not Started | 123 Joinery 456 Joinery 789 Joinery | 2021-06-16 | 2021-07-16 | 31
Tiler | Not Started | 123 Tiler 456 Tiler 789 Tiler | 2021-06-16 | 2021-07-16 | 31
Glass | Not Started | 123 Glass 456 Glass 789 Glass | 2021-06-16 | 2021-07-16 | 31
Energex Connection | Not Started |  | 2021-11-19 | 2021-11-26 | 8
Plaster | Not Started | 123 Plaster 456 Plaster 789 Plaster | 2021-09-01 | 2021-09-29 | 29
Painting | Not Started | 123 Paitner 456 Painter 789 Painter | 2021-09-13 | 2021-10-13 | 31
Landscaping | Not Started | 123 Landscape 456 Landscape 789 Landscape | 2021-09-28 | 2021-10-27 | 30