## Sheet1
BATHROOM RENOVATION TIMELINE
TASK NAME | DURATION IN DAYS |  | START DATE | COMPLETION DATE
Demolition of old bathroom |  | 2 | 2020-08-03 | 2020-08-04
Builder to complete structrual changes to bathroom |  | 1 | 2020-08-05 | 2020-08-05
Plumbing rough in |  | 1 | 2020-08-06 | 2020-08-06
Electrical rough in |  | 1 | 2020-08-06 | 2020-08-06
Cement sheeting and floor screed |  | 3 | 2020-08-07 | 2020-08-11
Waterproofing and curing |  | 4 | 2020-08-12 | 2020-08-16
Paint ceiling |  | 1 | 2020-08-17 | 2020-08-17
Tiling and grouting walls and floors |  | 4 | 2020-08-18 | 2020-08-21
Cabinetry installation |  | 2 | 2020-08-24 | 2020-08-25
Plumbing fit off |  | 1 | 2020-08-26 | 2020-08-26
Electrical fit off |  | 1 | 2020-08-26 | 2020-08-26
Free standing bath installation |  | 1 | 2020-08-26 | 2020-08-26
Shower screen installation |  | 1 | 2020-08-27 | 2020-08-27
Mirrors and accessories (towel rail, toilet |  | 1 | 2020-08-27 | 2020-08-27
roll holder etc) installation
Final clean and inspection |  | 1 | 2020-08-28 | 2020-08-28