Project Schedule Template

SIMULATION PROJECT - The information is fictional and provided for the purpose of this simulation.

Stage: Foundation and Structure

| Milestones to be completed | Site preparation, foundation laying, structural framework |
| --- | --- |
| Estimated project progress | 0-30% |
| Start date | 01/04/2023 |
| End date | 30/06/2023 |
| Labour start date | 02/04/2023 |
| Delivery date for materials | 10/04/2023 (Structural Steel), 08/04/2023 (Concrete) |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Site Excavation | 02/04/2023 | 07/04/2023 | N/A | Excavation team |
| Foundation Pouring | 08/04/2023 | 12/04/2023 | Ready-Mix Concrete | Concrete layers |
| Structural Steel Erection | 11/04/2023 | 30/06/2023 | Structural Steel Beams | Steelworkers, crane operators |

Contingency

| Summary of contingency | Weather delays - If weather delays occur, schedule weekend work to make up for lost time. |
| --- | --- |
| Materials needed | N/A |
| Labour needed | N/A |

Contingency

| Summary of contingency | Concrete delivery delays - Have a secondary supplier on standby in case of primary supplier issues. |
| --- | --- |
| Materials needed | Ready-Mix Concrete |
| Labour needed | Concrete layers |

Contingency

| Summary of contingency | Steel fabrication errors - Perform early quality checks on steel deliveries to allow time for refabrication if necessary. |
| --- | --- |
| Materials needed | N/A |
| Labour needed | N/A |

Stage:  Exterior and Interior

| Milestones to be completed | Enclosure of building, installation of windows, interior rough-in |
| --- | --- |
| Estimated project progress | 30-60% |
| Start date | 01/07/2023 |
| End date | 30/09/2023 |
| Labour start date | 01/07/2023 |
| Delivery date for materials | 01/07/2023 (Glass Panels), 05/07/2023 (Insulation) |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Window Installation | 01/07/2023 | 15/07/2023 | Window Glass Panels | Glaziers |
| Interior Framing and Insulation | 16/07/2023 | 15/08/2023 | Timber, Insulation Material | Carpenters, insulators |

Contingency

| Summary of contingency | Incorrect window sizing - Incorrect window sizing |
| --- | --- |
| Materials needed | More Window Glass Panels |
| Labour needed | Glaziers |

Contingency

| Summary of contingency | Material Shortages - Order extra 10% of materials to account for potential wastage or errors. |
| --- | --- |
| Materials needed | N/A |
| Labour needed | N/A |

Stage: Finishing and Commissioning

| Milestones to be completed | Painting, fixture installations, final inspections |
| --- | --- |
| Estimated project progress | 60-100% |
| Start date | 01/10/2023 |
| End date | 31/12/2023 |
| Labour start date | 01/10/2023 |
| Delivery date for materials | 25/09/2023 (Paint), 05/10/2023 (Fixtures) |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Painting | 01/10/2023 | 20/10/2023 | Paint | Painters |
| Fixture and Finishing Touches | 21/10/2023 | 30/11/2023 | Lighting fixtures, plumbing fixtures, hardware | Electricians, plumbers, general labor |

Contingency

| Summary of contingency | Delays in prior tasks - Utilize overtime and additional painters to catch up on the schedule if needed. |
| --- | --- |
| Materials needed | More Paint for extra painters to catch up |
| Labour needed | More Painters |

Contingency

| Summary of contingency | Supplier delivery issues - Establish agreements with suppliers for priority delivery and have a backup list of suppliers. |
| --- | --- |
| Materials needed | N/A |
| Labour needed | N/A |