CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Debbie Cremer |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | 2/06/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 30 |  | Yes | No |

Assessor Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Floor coverings | Tiler |  |
|  | Concrete | Concreter |  |
|  | Windows and doors | Carpenter |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | An employee works for the builder and will undertake any work directed by the builder. Builder is in control of directing the work carried out to stay within the schedule. A contractor will decide himself what, when and how works will be undertaken to remain on the schedule. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Local council Environmental Protection Agency |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | So that accurate timeframes and any special orders required can be taken into consideration when scheduling works. Colour selections can be made and agreed upon early and in writing to avoid variations later down the track. Clients will have the opportunity to make changes at the time of scheduling. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | 6.30am to 6.30pm Monday through Saturday in the Sunshine Coast region. Works should be scheduled between these times and the practical completion date adjusted to accordingly. |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Structural drawings | These drawings will show sizes, quantities and types of timber and framing to be used. The measurements can be used to calculate the amount of timber etc to be ordered and the staging of deliveries. |  |
|  | Colour Specifications | Shows colour selections for the building including application details and standards to be followed. This spec. will outline the specific colour and volume of paint required for the job to enable the correct product to be ordered and how much labour it will take to complete the activity. The same type of thing will be outlined for tiles, carpets etc |  |
|  | Product Specifications | Outline products like whitegoods, electrical fittings, light and switch types that are to be used in the building. This will be referred to ensure the correct items that have been agreed upon by the client are purchased. Installation timeframes will be able to be estimated and planned for. |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | Make changes to the schedule accordingly Notify major suppliers. Make changes to the call forward sheet. |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Upgrades to light fittings | Could be more difficult to source and therefore may delay the schedule. |  |
|  | Change in kitchen layout | Kitchen will have to be redesigned and may affect other work fronts e.g. plumbing. So a number of tasks may need to be rescheduled. |  |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Change in colour scheme | Paint will have to be cancelled and re-ordered and may not affect the schedule, unless it is a non-standard colour/finish and is difficult to source. Painter will have to be notified incase there is a change in price |  |
|  | Changes to whitegoods | Shouldn’t affect the schedule as long as they can be easily sourced and are selected prior to installation. If additional plumbing/electrical work is required, this will need to be added to the schedule. |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | An overlay drawing shows additional information above what is shown on the original plans. They provide clarity on the building process and advises if there have been changes that require additional specialist changes. |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | Work Time period Agreed rates |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | Product description Total price Order and delivery times Delivery details Project manager details Purchase number Supplier details Supplier contact information Terms and conditions |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet tracks when materials are needed and the dates to call suppliers and subcontractors to place orders and material delivery dates. This enables the scheduling of site activities. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Architectural plans Electrical plans |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | 250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Concrete for slab | 5 business days | 10/03/20 | 3/03/20 | Weather, labour availability, slab preparation |  |
|  | Windows | 3 weeks | 30/04/19 | 9/04/19 | Storage, construction program, labour availability |  |
|  | Paint | 2 business days | 20/05/19 | 18/05/19 | Labour availability, colour changes (variations), storage, colour availability (end of line) |  |
|  | Tiles | 3 business days | 20/05/19 | 15/05/19 | Labour availability, colour changes (variations), storage, colour availability (end of line) |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | Consult drawings & specs for specific details, measurements and quantities required. Produce overlay drawings where necessary. Refer to construction schedule to determine when cladding is required on site. Check there is sufficient room for storage if required. Source suppliers and request a quote including leadtime. Select suitable supplier and complete “call forward sheet”. Raise purchase order/subcontract and send. Follow up to confirm order has been received and can be supplied on time. Follow up on progress of order throughout lead time, confirming delivery date and address. | Any further details identified by overlay drawings. Construction program/staging. Suppliers price, leadtime and product availability. Storage for materials, under cover if required. Weather Subcontractor/employee availability. Call forward sheet is to be correctly completed and updated throughout the process. Ensure all applicable drawings, and any relevant information is included as part of the purchase order or subcontract. And the agreed rates, lead time and quality is noted. Copies are taken of all orders in their entirety and filed for future reference. |  |
|  | Wall frame | Consult drawings & specs for specific details, measurements and quantities required. Produce overlay drawings where necessary. Refer to construction schedule to determine when cladding is required on site. Check there is sufficient room for storage if required. Source suppliers and request a quote including leadtime. Select suitable supplier and complete “call forward sheet”. Raise purchase order/subcontract and send. Follow up to confirm order has been received and can be supplied on time. Follow up on progress of order throughout lead time, confirming delivery date and address | Any further details identified by overlay drawings. Construction program/staging. Suppliers price, leadtime and product availability. Storage for materials, under cover if required. Weather Subcontractor/employee availability. Call forward sheet is to be correctly completed and updated throughout the process. Ensure all applicable drawings, and any relevant information is included as part of the purchase order or subcontract. And the agreed rates, lead time and quality is noted. Copies are taken of all orders in their entirety and filed for future reference |  |
|  | Windows | Nominate supplier Consult drawings & specs Look at construction schedule Check storage room Source quote/lead time Raise order Follw up order progress | Any further details identified by overlay drawings. Construction program/staging. Suppliers price, leadtime and product availability. Storage for materials, under cover if required. Weather Subcontractor/employee availability. Call forward sheet is to be correctly completed and updated throughout the process. Ensure all applicable drawings, and any relevant information is included as part of the purchase order or subcontract. And the agreed rates, lead time and quality is noted. Copies are taken of all orders in their entirety and filed for future reference |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer |  |  |
| --- | --- | --- |